## Sheet 1
Name | Work ID # | Work Type | Line of Business | Project Manager/Owner | Sub-Portfolio | Sponsor. | Business Priority | Methodology | Part Of Program? | Capitalization Flag | Work Status | Current Gate | Stage | Status Reporting Frequency | Reported - This Period (d) | Reporting Period | Reporting Period - Fortnightly | Reporting Period - Weekly | Overall Status Assessment | Scope Status Assessment | Cost Status Assessment | Schedule Status Assessment | Resourcing Status Assessment | Benefit Status Assessment | OCM Status Assessment | Quality Status Assessment | Risks Status Assessment | Issues Status Assessment | Baseline Start | Baseline Finish | Baseline Duration (d) | Requested Start | Requested Finish | Duration at Complete (d) | Actual/Schedule Start | Actual/Schedule Finish | Schedule Start | Schedule Finish | Actual Start | Actual Finish | Late Finish | Percent Complete | Milestones, Total | Milestones,Completed | Milestones,Remain | Milestones, Scheduled | Milestones, Late | Milestones, Missed | Milestones, On Time | Changes, Active | Changes, Total | Risks, Active | Risks, Total | Are there changes to the business capability? | Are there changes to support arrangements? | Will there be Architecture changes? | Issues, Active | Issues, Total | Gate 0 Date | Gate 1 Date | Gate 2 Date | Gate 3 Date
Project 148 | 1001444 | Epic | Line of Business 9 | Project Manager 13 | Sub-Portfolio 7 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-05-03 | 2024-06-28 | [8 empty] | 0
Project 1 | 1000925 | Application Support |  | Project Manager 26 | Sub-Portfolio 5 | [5 empty] | Open/Active |  |  | Weekly | [17 empty] | 2023-12-01 | 2024-06-28 | 139.9 | 2023-11-27 | 2024-06-28 | 2023-11-27 | 2024-06-28 |  |  |  | 0
Project 2 | 1000923 | Application Support |  | Project Manager 37 | Sub-Portfolio 5 | [5 empty] | Open/Active | [20 empty] | 2023-12-01 | 2024-06-28 | 174.6 | 2023-11-01 | 2024-07-23 | 2023-11-01 | 2024-07-23 |  |  |  | 0
Project 3 | 1001277 | Project | Line of Business 13 | Project Manager 27 | Sub-Portfolio 7 |  |  |  | No | Capital | On Hold |  | 2. Concept | Monthly | [17 empty] | 2024-03-11 | 2025-06-30 | 320.9 | 2024-08-14 | 2025-11-28 | 2024-08-14 | 2025-11-28 |  |  |  | 0
Project 4 | 1001299 | Minor Work | Line of Business 20 | Project Manager 38 | Sub-Portfolio 7 |  |  |  | No | Capital | Requested |  | 2. Concept | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2024-03-18 | 2024-06-28 | 116 | 2024-03-18 | 2024-08-30 | 2024-03-18 | 2024-08-30 | 2024-03-18 |  |  | 29
Project 5 | 1001373 | Project | Line of Business 20 | Project Manager 27 | Sub-Portfolio 7 | Sponsor 31 |  | Agile | No | Capital | Open/Active | Gate 1 | 4. Analyse & Design | Monthly |  | Mar-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-03-18 | 2025-06-30 | 315.9 | 2024-03-25 | 2024-06-28 | 349.9 | 2024-03-18 | 2025-08-15 | 2024-03-18 | 2025-08-15 | 2024-04-09 |  | 2025-06-02 | 19 | 31 | 27 | 4 | 27 |  |  | 4 |  |  | 1 | 2 | Moderate Changes | Moderate Changes | No Changes |  |  | 2024-06-27 | 2024-09-17
Project 6 | 1001392 | Project | Line of Business 13 | Project Manager 27 | Sub-Portfolio 7 |  |  |  |  | Capital | On Hold |  | 2. Concept | Monthly | [17 empty] | 2024-04-02 | 2024-06-28 | 62 | 2024-04-02 | 2024-06-28 | 2024-04-02 | 2024-06-28 |  |  |  | 0
Project 7 | 1001430 | Project | Line of Business 20 | Project Manager 7 | Sub-Portfolio 7 |  |  |  | No | Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-04-22 | 2024-06-28 | 52.9 | 2024-04-15 | 2024-06-28 | 2024-04-15 | 2024-06-28 | 2024-05-20 |  |  | 26
Project 8 | 1001437 | Minor Work | Line of Business 13 | Project Manager 27 | Sub-Portfolio 7 | Sponsor 42 |  |  |  | Capital | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-04-29 | 2024-06-28 | 113.9 | 2024-04-22 | 2024-09-30 | 2024-04-22 | 2024-09-30 | 2024-04-29 |  |  | 18
Project 9 | 1001413 | Minor Work | Line of Business 23 | Project Manager 38 | Sub-Portfolio 7 |  |  |  | No | Capital | Requested |  | 2. Concept | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2024-04-15 | 2024-06-28 | 57.9 | 2024-04-08 | 2024-06-28 | 2024-04-08 | 2024-06-28 |  |  |  | 0
Project 10 | 1001458 | Minor Work |  | Project Manager 27 | Sub-Portfolio 7 |  |  |  |  | Opex | On Hold |  | 2. Concept | Monthly | [17 empty] | 2024-05-13 | 2024-07-31 | 61.1 | 2024-05-06 | 2024-07-31 | 2024-05-06 | 2024-07-31 |  |  |  | 0
Project 11 | 1001486 | Application Support | Line of Business 13 | Project Manager 7 | Sub-Portfolio 7 |  | High |  |  | Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-06-03 | 2024-10-31 | 110.1 | 2024-05-27 | 2024-10-30 | 2024-05-27 | 2024-10-30 |  |  |  | 0
Project 12 | 1001504 | Application Support | Line of Business 13 | Project Manager 7 | Sub-Portfolio 7 |  | High |  |  | Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-06-03 | 2024-10-31 | 106.1 | 2024-06-03 | 2024-10-31 | 2024-06-03 | 2024-10-31 |  |  |  | 0
Project 13 | 1001816 | Project |  | Project Manager 7 | Sub-Portfolio 7 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-12-09 | 2025-06-30 | 131 | 2024-12-09 | 2025-06-30 | 2024-12-09 | 2025-06-30 |  |  |  | 0
Project 14 | 1001566 | Project |  | Project Manager 27 | Sub-Portfolio 7 |  |  |  | No | Capex & Opex | Requested |  | 2. Concept | Weekly | [17 empty] | 2024-07-22 | 2025-01-31 | 225 | 2024-07-29 | 2025-06-30 | 2024-07-29 | 2025-06-30 |  |  |  | 0
Project 15 | 1001524 | Minor Work |  | Project Manager 7 | Sub-Portfolio 7 | [5 empty] | Requested |  | 2. Concept | Weekly | [17 empty] | 2024-07-01 | 2025-07-31 | 282 | 2024-08-09 | 2025-09-30 | 2024-08-09 | 2025-09-30 | 2024-08-09 |  |  | 42
Project 16 | 1001579 | Minor Work |  | Project Manager 27 | Sub-Portfolio 7 |  |  |  | No | Opex | Requested |  | 2. Concept | Weekly | [17 empty] | 2024-08-05 | 2024-12-20 | [8 empty] | 0
Project 17 | 1001602 | Project |  | Project Manager 27 | Sub-Portfolio 7 |  |  |  | No | Capital | Requested |  | 2. Concept | Weekly | [17 empty] | 2024-08-26 | 2025-03-31 | 325.9 | 2024-09-02 | 2025-12-24 | 2024-09-02 | 2025-12-24 |  |  |  | 0
Project 18 | 1001834 | Light Project |  | Project Manager 7 | Sub-Portfolio 7 | Sponsor 33 |  |  | No | Capital | Requested |  | 2. Concept | Monthly |  | Feb-2025 |  |  | Green | Green | Amber | Green | Green | Green | Green |  | Green | Amber |  |  |  | 2025-02-04 | 2025-06-30 | 141 | 2025-02-10 | 2025-08-29 | 2025-02-10 | 2025-08-29 |  |  |  | 0 | [9 empty] | 2 | 2 |  |  |  | 1 | 1
Project 19 | 1001765 | Minor Work |  | Project Manager 7 | Sub-Portfolio 7 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly | [17 empty] | 2024-10-21 | 2025-06-30 | 429.8 | 2024-10-21 | 2026-07-28 | 2024-10-21 | 2026-07-28 | 2024-10-21 |  |  | 3
Project 20 | 1001650 | Minor Work |  | Project Manager 7 | Sub-Portfolio 7 |  | Important |  |  |  | Open/Active |  | 6. Implement | Weekly | [17 empty] | 2024-10-08 | 2025-06-30 | 174.9 | 2024-10-08 | 2025-06-30 | 2024-10-08 | 2025-06-30 | 2024-11-22 |  |  | 1
Project 21 | 1001802 | Project | Line of Business 22 | Project Manager 7 | Sub-Portfolio 7 | Sponsor 15 |  |  |  |  | Requested |  | 2. Concept | Weekly | [17 empty] | 2024-11-15 | 2025-06-30 | 25 | 2024-12-09 | 2025-01-24 | 2024-12-09 | 2025-01-24 |  |  |  | 0
Project 22 | 1000872 | Project |  | Project Manager 7 | Sub-Portfolio 8 |  |  |  | No | Opex | Requested |  | 2. Concept | Monthly |  | May-2024 |  |  | Green | Green | Green | Amber | Green | Green | Green |  | Green | Green |  |  |  | 2023-03-01 | 2024-02-02 | 450 | 2024-03-04 | 2025-12-22 | 2024-03-07 | 2025-12-22 | 2024-03-04 |  | 2025-06-02 | 40 | 72 | 68 | 4 | [11 empty] | 1 | 1
Project 23 | 1001819 | Minor Work |  | Project Manager 24 | Sub-Portfolio 7 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-12-09 | 2025-09-30 | [8 empty] | 0
Project 24 | 1001817 | Project |  | Project Manager 7 | Sub-Portfolio 7 | Sponsor 12 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-12-09 | 2025-06-30 | 215 | 2024-12-09 | 2025-10-27 | 2024-12-09 | 2025-10-27 |  |  |  | 0
Project 25 | 1001818 | Project |  | Project Manager 7 | Sub-Portfolio 7 | Sponsor 41 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-12-09 | 2025-03-28 | 163.2 | 2024-12-09 | 2025-08-14 | 2024-12-09 | 2025-08-14 | 2024-12-09 |  |  | 13
Project 26 | 1001822 | Project |  | Project Manager 7 | Sub-Portfolio 7 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-12-13 | 2025-06-30 | 185 | 2025-01-06 | 2025-09-26 | 2025-01-06 | 2025-09-26 |  |  |  | 0
Project 27 | 1001860 | Project |  | Project Manager 7 | Sub-Portfolio 7 | Sponsor 27 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-02-24 | 2025-06-30 | 10 | 2025-03-03 | 2025-03-14 | 2025-03-03 | 2025-03-14 |  |  |  | 0
Project 28 | 1001873 | Minor Work |  | Project Manager 7 | Sub-Portfolio 7 | Sponsor 36 | Low |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-03-03 | 2025-06-30 | 82 | 2025-03-03 | 2025-06-30 | 2025-03-03 | 2025-06-30 |  |  |  | 0
Project 33 | 1001051 | Minor Work | Line of Business 21 | Project Manager 7 | Sub-Portfolio 1 | Sponsor 34 | High |  |  | Capital | Requested |  |  | Monthly |  | May-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2024-01-24 | 2024-06-28 | 121.1 | 2024-02-01 | 2024-07-25 | 2024-02-01 | 2024-07-25 | 2024-02-01 |  |  | 51 | 5 | 5 | [8 empty] | 1 |  |  |  |  | 3
Project 34 | 1001353 | Project |  | Project Manager 12 | Sub-Portfolio 8 |  |  | Waterfall | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 28 Feb 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-05-10 | 2025-08-29 | 323 | 2024-07-01 | 2025-06-30 | 323 | 2024-05-10 | 2025-08-29 | 2024-07-01 | 2025-08-29 | 2024-05-10 |  | 2025-06-30 | 26 | 66 | 42 | 24 | 41 | 2 | 2 | 22 |  |  | 5 | 8 | No Changes | No Changes | Minor Changes |  |  | 2024-08-29
Project 35 | 1000926 | Service | Line of Business 8 | Project Manager 18 | Sub-Portfolio 4 |  | Important |  |  | Capex & Opex | Requested |  |  | Weekly |  |  |  | 28 Feb 25 | Green | Amber | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2023-09-01 | 2024-06-28 | 199 | 2024-10-01 | 2025-07-28 | 2024-10-01 | 2025-07-28 |  |  |  | 0
Project 36 | 1000927 | Project | Line of Business 7 | Project Manager 18 | Sub-Portfolio 4 |  |  |  | No | Capex & Opex | Cancelled |  | 2. Concept | Weekly |  |  |  | 01 Dec 23 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2023-09-01 | 2024-06-28 | 200 | 2023-09-01 | 2024-06-28 |  |  | 2023-09-01 | 2024-06-28 |  | 100
Project 37 | 1000918 | Project | Line of Business 7 | Project Manager 18 | Sub-Portfolio 4 |  |  |  | No | Capex & Opex | Requested |  | 2. Concept | Weekly |  |  |  | 01 Dec 23 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2023-10-03 | 2024-05-31 | 160 | 2023-10-30 | 2024-06-28 | 2023-10-30 | 2024-06-28 |  |  |  | 0
Project 38 | 1001878 | Project |  | Project Manager 16 | Sub-Portfolio 8 | Sponsor 18 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-07-01 | 2026-06-30 | 244 | 2025-07-01 | 2026-06-30 | 2025-07-01 | 2026-06-30 |  |  |  | 0
Project 40 | 1000986 | Project | Line of Business 10 | Project Manager 17 | Sub-Portfolio 7 |  |  |  | No | Opex | Requested |  | 3. Evaluate | Weekly |  |  |  | 05 Jul 24 | Green | Green | Amber | Green | Green | Green | Green |  | Green | Green |  |  |  | 2023-12-18 | 2024-04-30 | 234 | 2023-12-18 | 2024-11-29 | 2023-12-18 | 2024-11-29 |  |  |  | 0
Project 41 | 1001242 | Project |  |  | Sub-Portfolio 7 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-03-07 | 2024-06-28 | 442 | 2024-03-18 | 2025-12-24 | 2024-03-18 | 2025-12-24 |  |  |  | 0
Project 42 | 1001122 | Project | Line of Business 12 | Project Manager 38 | Sub-Portfolio 4 |  |  |  | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 07 Mar 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2023-12-12 | 2024-11-29 | 238 | 2024-01-08 | 2024-12-18 | 292 | 2023-12-12 | 2025-02-28 | 2023-12-12 | 2025-02-28 | 2024-03-22 |  | 2025-06-02 | 57 | 75 | 74 | 1 | 75 |  | 1 | 1 |  |  |  | 4 |  |  |  |  | 2 | 2024-02-01 | 2024-05-30 | 2024-09-30 | 2025-03-30
Project 43 | 1001367 | Project | Line of Business 12 | Project Manager 39 | Sub-Portfolio 4 |  |  |  |  | Capex & Opex | Requested |  | 2. Concept | Weekly |  |  |  | 26 Jul 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2024-02-22 | 2024-06-28 | 87.1 | 2024-02-22 | 2024-06-28 | 2024-02-22 | 2024-06-28 |  |  |  | 0 | [10 empty] | 9
Project 45 | 1000294 | Project | Line of Business 12 | Project Manager 4 | Sub-Portfolio 4 | Sponsor 44 |  | Waterfall | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 07 Mar 25 | Green | Green | Green | Green | Amber | Green | Green |  | Amber | Green | 2021-11-01 | 2026-02-05 | 1062 | 2019-05-01 | 2025-06-30 | 1062 | 2021-11-01 | 2026-02-05 | 2023-10-16 | 2026-02-05 | 2021-11-01 |  | 2025-12-19 | 47 | 90 | 28 | 62 | 71 | 1 | 44 | 61 |  |  | 1 | 1 |  |  |  | 1 | 1 | 2024-08-29
Project 46 | 1000302 | Project | Line of Business 7 | Project Manager 17 | Sub-Portfolio 7 | Sponsor 23 |  | Hybrid | No | Opex | Open/Active | Gate 1 | 5. Build & Test | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Amber | Green | Green | Green |  | Amber | Amber | 2019-04-09 | 2025-06-30 | 1587 |  |  | 1713 | 2019-04-09 | 2025-12-24 | 2019-04-09 | 2025-12-24 | 2019-04-09 |  | 2025-06-02 | 13 | 122 | 99 | 23 | 60 | 3 | 2 |  |  |  | 2 | 8 | No Changes | No Changes | Minor Changes |  | 4
Project 47 | 1001879 | Project |  | Project Manager 31 | Sub-Portfolio 8 | Sponsor 18 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-07-01 | 2026-06-30 | 244 | 2025-07-01 | 2026-06-30 | 2025-07-01 | 2026-06-30 |  |  |  | 0
Project 48 | 1001460 | Epic | Line of Business 5 | Project Manager 35 | Sub-Portfolio 7 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-05-13 | 2024-06-28 | 41.9 | 2024-05-01 | 2024-06-28 | 2024-05-01 | 2024-06-28 |  |  |  | 0
Project 49 | 1001459 | Minor Work | Line of Business 5 | Project Manager 35 | Sub-Portfolio 7 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-05-13 | 2024-06-28 | 38.9 | 2024-05-06 | 2024-06-28 | 2024-05-06 | 2024-06-28 |  |  |  | 0
Project 50 | 1001280 | Light Project | Line of Business 20 | Project Manager 27 | Sub-Portfolio 7 | [5 empty] | Cancelled |  | 2. Concept | Monthly | [17 empty] | 2024-03-11 | 2024-06-28 | 76 | 2024-03-11 | 2024-06-28 |  |  | 2024-03-11 | 2024-06-28 |  | 100
Project 51 | 1001498 | Project |  | Project Manager 35 | Sub-Portfolio 7 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-05-24 | 2024-06-28 | 24.1 | 2024-05-24 | 2024-06-28 | 2024-05-24 | 2024-06-28 |  |  |  | 0
Project 57 | 1001360 | Project |  | Project Manager 21 | Sub-Portfolio 8 | Sponsor 18 |  | Hybrid | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 28 Feb 25 | Green | Green | Green | Green | Amber | Green | Green |  | Green | Green | 2024-03-26 | 2025-06-30 | 309 | 2024-07-01 | 2025-06-30 | 397 | 2024-03-26 | 2025-10-31 | 2025-01-06 | 2025-10-31 | 2024-03-26 |  | 2025-06-30 | 47 | 12 | 5 | 7 | 5 | [5 empty] | 2 | 2 | No Changes | No Changes | Minor Changes |  |  | 2024-03-26
Project 52 | 1001768 | Minor Work |  | Project Manager 35 | Sub-Portfolio 7 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly | [17 empty] | 2024-10-25 | 2025-06-30 | 1.1 | 2024-10-21 | 2024-10-22 | 2024-10-21 | 2024-10-22 |  |  |  | 0
Project 54 | 1000308 | Project | Line of Business 7 | Project Manager 4 | Sub-Portfolio 7 | Sponsor 37 |  | Hybrid | No | Opex | On Hold | Gate 1 | 4. Analyse & Design | Monthly |  | Sep-2024 |  |  | Red | Green | Amber | Red | Amber | Green | Green |  | Red | Red | 2023-03-23 | 2024-11-07 | 404 |  |  | 729 | 2023-03-23 | 2026-03-17 | 2023-06-01 | 2026-03-17 | 2023-03-23 |  | 2026-03-18 | 6 | 71 | 28 | 43 | 31 | 23 | 23 |  |  |  | 10 | 23 | Moderate Changes | Moderate Changes | Moderate Changes | 4 | 7
Project 55 | 1000311 | Project | Line of Business 7 | Project Manager 31 | Sub-Portfolio 8 | Sponsor 18 |  | Agile | Yes | Capital | Prepare for Closure | Gate 2 | 4. Analyse & Design | Monthly |  | Aug-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2023-07-17 | 2024-02-16 | 143 | 2023-09-28 | 2024-04-12 | 397 | 2023-07-17 | 2025-03-03 | 2024-01-15 | 2025-03-03 | 2023-07-17 |  | 2024-09-25 | 61 | 35 | 33 | 2 | 22 | 2 | 2 | [5 empty] | Minor Changes | Moderate Changes | Minor Changes
Project 56 | 1000299 | Project | Line of Business 12 | Project Manager 36 | Sub-Portfolio 4 | Sponsor 19 |  | Waterfall | Yes | Capital | Prepare for Closure | Gate 2 | 6. Implement | Weekly |  |  | 27 May 24 - 07 Jun 24 | 02 Aug 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2022-11-15 | 2024-07-22 | 418 |  |  | 511 | 2022-11-15 | 2024-11-29 | 2022-11-15 | 2024-07-22 | 2022-11-15 |  | 2025-06-02 | 24 | 23 | 23 |  | 10 |  | 1 |  |  |  |  | 3 | Minor Changes | Moderate Changes | Minor Changes |  | 5
Project 58 | 1001821 | Project |  | Project Manager 18 | Sub-Portfolio 4 | [5 empty] | Requested |  | 2. Concept | Weekly | [17 empty] | 2024-12-13 | 2025-06-30 | 127 | 2024-12-13 | 2025-06-30 | 2024-12-13 | 2025-06-30 |  |  |  | 0
Project 59 | 1001362 | Project | Line of Business 7 | Project Manager 18 | Sub-Portfolio 4 | Sponsor 49 |  | Waterfall | No | Capex & Opex | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Feb-2025 |  | 24 Jan 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-07-29 | 2025-07-01 | 224.1 | 2024-07-01 | 2026-06-29 | 884 | 2024-07-08 | 2028-01-27 | 2024-07-08 | 2028-01-27 | 2024-07-29 |  | 2025-06-02 | 7 | 52 | 27 | 25 | 50 | 13 | 26 | 12 |  |  | 10 | 10 | No Changes | Moderate Changes | Major Changes | 1 | 1 | 2024-08-24
Project 60 | 1000884 | Light Project | Line of Business 7 | Project Manager 18 | Sub-Portfolio 4 | Sponsor 30 |  |  | No | Opex | Cancelled |  | 2. Concept | Weekly |  |  |  | 01 Dec 23 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2023-12-01 | 2024-06-28 | 136 | 2023-09-11 | 2024-04-05 |  |  | 2023-09-11 |  |  | 100 | [7 empty] | 1 | 1
Project 61 | 1001820 | Minor Work |  | Project Manager 35 | Sub-Portfolio 7 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-12-13 | 2025-06-30 | 127 | 2024-12-13 | 2025-06-30 | 2024-12-13 | 2025-06-30 |  |  |  | 0
Project 62 | 1001548 | Minor Work |  | Project Manager 13 | Sub-Portfolio 7 |  | Low |  |  | Opex | Requested |  |  | Monthly | [17 empty] | 2023-09-01 | 2024-12-20 | 66 | 2024-07-01 | 2024-09-30 | 2024-07-01 | 2024-09-30 |  |  |  | 0
Project 63 | 1001626 | Minor Work | Line of Business 7 | Project Manager 13 | Sub-Portfolio 7 |  | High |  |  |  | Requested |  | 6. Implement | Monthly | [17 empty] | 2024-09-11 | 2025-03-31 | 137 | 2024-10-01 | 2025-04-30 | 2024-10-01 | 2025-04-30 |  |  |  | 0
Project 66 | 1001875 | Project |  | Project Manager 25 | Sub-Portfolio 8 | Sponsor 18 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-07-01 | 2026-06-30 | 244 | 2025-07-01 | 2026-06-30 | 2025-07-01 | 2026-06-30 |  |  |  | 0
Project 68 | 1001876 | Project |  | Project Manager 25 | Sub-Portfolio 8 | Sponsor 18 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-07-01 | 2026-06-30 | 244 | 2025-07-01 | 2026-06-30 | 2025-07-01 | 2026-06-30 |  |  |  | 0
Project 69 | 1001877 | Project |  | Project Manager 25 | Sub-Portfolio 8 | Sponsor 18 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-07-01 | 2026-06-30 | 244 | 2025-07-01 | 2026-06-30 | 2025-07-01 | 2026-06-30 |  |  |  | 0
Project 70 | 1001861 | Project |  |  | Sub-Portfolio 2 | Sponsor 35 |  |  |  | Capex & Opex | Requested |  | 2. Concept | Weekly | [17 empty] | 2025-07-01 | 2026-06-30 | 60 | 2025-07-01 | 2025-09-22 | 2025-07-01 | 2025-09-22 |  |  |  | 0
Project 72 | 1001361 | Project |  | Project Manager 28 | Sub-Portfolio 8 | Sponsor 18 |  | Agile | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Feb-2025 |  | 11 Oct 24 | Amber | Green | Amber | Amber | Amber | Green | Green |  | Green | Green | 2024-09-30 | 2025-06-30 | 180 | 2024-07-01 | 2025-06-30 | 180 | 2024-09-30 | 2025-06-30 | 2024-09-30 | 2025-06-30 | 2024-10-30 |  | 2025-06-27 | 0 | 42 | 9 | 33 | 21 | 10 | 12 | 23 |  |  | 2 | 2 | Minor Changes | Minor Changes | Minor Changes | 1 | 1 | 2024-10-30
Project 73 | 1001356 | Project | Line of Business 7 | Project Manager 18 | Sub-Portfolio 4 |  |  |  | No | Capital | Requested |  | 2. Concept | Weekly | [17 empty] | 2024-07-01 | 2025-06-30 | 1.1 | 2024-12-19 | 2024-12-20 | 2024-12-19 | 2024-12-20 |  |  |  | 0
Project 74 | 1001422 | Minor Work | Line of Business 7 | Project Manager 19 | Sub-Portfolio 4 |  | Medium |  | No | Capital | Requested |  | 2. Concept | Weekly | [17 empty] | 2024-04-02 | 2024-06-28 | 70 | 2024-04-15 | 2024-07-23 | 2024-04-15 | 2024-07-23 |  |  |  | 0
Project 75 | 1000871 | Project |  | Project Manager 25 | Sub-Portfolio 8 | Sponsor 18 |  |  | No | Capital | On Hold |  | 4. Analyse & Design | Monthly |  | Feb-2024 |  |  | Red | Amber | Red | Amber | Amber | Green | Green |  | Amber | Amber |  |  |  | 2024-01-15 | 2024-06-28 | 213 | 2023-11-13 | 2024-09-25 | 2023-11-13 | 2024-09-25 |  |  |  | 0 | [9 empty] | 5 | 5 | No Changes | No Changes | Moderate Changes
Project 76 | 1001429 | Program (admin) |  |  | Sub-Portfolio 4 |  | Important |  |  |  | Requested |  |  | Monthly | [17 empty] | 2024-04-15 | 2024-12-20 | 863.9 | 2022-07-27 | 2026-01-28 | 2022-07-27 | 2026-01-28 |  |  |  | 0
Project 77 | 1001388 | Project | Line of Business 1 | Project Manager 31 | Sub-Portfolio 8 |  |  |  |  | Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-03-18 | 2024-06-28 | 70.1 | 2024-03-18 | 2024-06-28 | 2024-03-18 | 2024-06-28 |  |  |  | 0
Project 78 | 1001374 | Project | Line of Business 8 | Project Manager 25 | Sub-Portfolio 8 |  |  |  |  | Capital | Requested |  | 2. Concept | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2024-03-01 | 2024-06-28 | 93.8 | 2024-03-01 | 2024-07-16 | 2024-03-01 | 2024-07-16 |  |  |  | 0 | [9 empty] | 1 | 1 |  |  |  | 1 | 1
Project 79 | 1001449 | Program (admin) |  |  | Sub-Portfolio 4 |  | Important |  |  |  | Requested |  |  | Weekly | [17 empty] | 2024-05-01 | 2024-12-20 | 162.9 | 2024-05-06 | 2024-12-20 | 2024-05-06 | 2024-12-20 |  |  |  | 0
Project 80 | 1001357 | Project |  | Project Manager 11 | Sub-Portfolio 1 |  |  |  | No | Capital | On Hold |  | 2. Concept | Weekly | [17 empty] | 2024-07-01 | 2025-06-30 | [8 empty] | 0
Project 81 | 1001354 | Project |  | Project Manager 2 | Sub-Portfolio 8 | Sponsor 18 |  |  | No | Opex | Cancelled |  | 2. Concept | Weekly | [17 empty] | 2024-07-01 | 2025-06-30 | [8 empty] | 0
Project 82 | 1000300 | Project | Line of Business 7 | Project Manager 12 | Sub-Portfolio 8 | Sponsor 18 |  | Waterfall | Yes | Capital | Prepare for Closure | Gate 2 | 7. Closure | Monthly |  | Sep-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2022-12-16 | 2024-10-31 | 466 |  |  | 481.8 | 2022-12-16 | 2024-11-22 | 2024-06-11 | 2024-11-22 | 2022-12-16 |  | 2024-11-01 | 93 | 64 | 64 |  | 64 | [6 empty] | 8 |  |  |  |  | 9 |  |  | 2024-09-25
Project 83 | 1001617 | Project | Line of Business 7 | Project Manager 22 | Sub-Portfolio 8 | Sponsor 18 |  |  | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Amber | Green |  |  |  | 2024-07-01 | 2025-06-30 | 278 | 2024-11-05 | 2025-12-19 | 2024-11-05 | 2025-12-19 | 2024-11-15 |  | 2025-11-13 | 0 | 77 | 10 | 67 | [6 empty] | 2 | 2 | [5 empty] | 2024-09-25
Project 84 | 1000297 | Project | Line of Business 7 | Project Manager 22 | Sub-Portfolio 8 | Sponsor 18 |  | Waterfall | Yes | Capital | On Hold | Gate 3 | 7. Closure | Monthly |  | Aug-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2020-07-01 | 2029-07-06 | 2276.4 | 2023-11-27 | 2024-06-28 | 2276.4 | 2020-07-01 | 2029-07-06 |  |  | 2020-07-01 |  |  | 100 | 29 | 29 |  | 29 | [6 empty] | 6 | Minor Changes | Minor Changes | Major Changes |  | 2 |  |  |  | 2024-09-27
Project 85 | 1001384 | Project |  | Project Manager 11 | Sub-Portfolio 8 |  |  |  | No | Capital | On Hold |  | 2. Concept | Weekly | [17 empty] | 2024-07-01 | 2026-11-27 | [8 empty] | 0
Project 86 | 1001806 | Minor Work |  | Project Manager 35 | Sub-Portfolio 7 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly | [17 empty] | 2024-11-15 | 2025-06-30 | [8 empty] | 0
Project 87 | 1000840 | Project | Line of Business 18 | Project Manager 38 | Sub-Portfolio 7 | Sponsor 22 |  | Hybrid | No | Capital | Requested | Gate 0 | 2. Concept | Monthly |  | Apr-2024 |  | 01 Mar 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2023-02-01 | 2025-06-30 | 593 | 2023-11-13 | 2025-05-30 | 837 | 2023-02-01 | 2026-06-30 | 2023-02-01 | 2026-06-30 | 2024-07-09 |  | 2025-06-02 | 0 | 42 | 19 | 23 | 27 |  | 8 |  |  |  |  | 2 | Moderate Changes | Moderate Changes | Moderate Changes |  | 4 | 2024-07-09
Project 88 | 1001279 | Project | Line of Business 13 | Project Manager 1 | Sub-Portfolio 7 |  |  |  |  | Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-03-11 | 2024-06-28 | 200 | 2024-03-11 | 2024-12-20 | 2024-03-11 | 2024-12-20 |  |  |  | 0
Project 89 | 1001870 | Project |  | Project Manager 18 | Sub-Portfolio 4 | Sponsor 43 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-03-03 | 2025-06-30 | 82 | 2025-03-03 | 2025-06-30 | 2025-03-03 | 2025-06-30 |  |  |  | 0
Project 90 | 1001493 | Project |  |  | Sub-Portfolio 2 |  |  | Agile | No | Opex | On Hold | Gate 0 | 2. Concept | Weekly | [14 empty] | 2022-08-01 | 2025-07-11 | 731 | 2024-06-03 | 2025-06-02 | 822 | 2022-08-01 | 2025-11-17 | 2025-01-17 | 2025-11-17 | 2022-08-01 |  | 2025-11-13 | 5 | 83 |  | 83 | 53 | 51 | 53 | 22 |  |  |  |  | Major Changes | Major Changes | Major Changes |  |  | 2024-05-31
Project 91 | 1000305 | Project | Line of Business 7 | Project Manager 25 | Sub-Portfolio 8 | Sponsor 18 |  | Hybrid | Yes | Capital | Prepare for Closure | Gate 2 | 7. Closure | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2020-10-01 | 2024-04-10 | 900 | 2023-04-03 | 2024-04-30 | 1098 | 2020-10-01 | 2025-01-31 | 2024-01-08 | 2025-01-31 | 2020-10-01 |  | 2025-06-30 | 17 | 15 | 15 |  | 6 | [6 empty] | 3 | No Changes | Minor Changes | Major Changes |  | 2
Project 92 | 1001328 | Project | Line of Business 24 | Project Manager 25 | Sub-Portfolio 8 | Sponsor 18 |  | Agile | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Green | Amber | Green | Green |  | Green | Green | 2024-03-13 | 2025-11-03 | 407 | 2024-04-02 | 2025-03-31 | 407 | 2024-03-13 | 2025-11-03 | 2024-03-25 | 2025-11-03 | 2024-03-13 |  | 2025-06-02 | 17 | 94 | 72 | 22 | 75 | 2 | 3 | 20 | 1 | 1 | 2 | 6 | No Changes | No Changes | Minor Changes | 2 | 3 | 2024-08-28
Project 93 | 1001866 | Light Project | Line of Business 12 | Project Manager 3 | Sub-Portfolio 4 | Sponsor 16 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-02-27 | 2025-06-30 | 84 | 2025-02-27 | 2025-06-30 | 2025-02-27 | 2025-06-30 |  |  |  | 0
Project 96 | 1001276 | Project | Line of Business 12 | Project Manager 20 | Sub-Portfolio 4 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-03-11 | 2024-06-28 | 179 | 2024-10-01 | 2025-06-30 | 2024-10-01 | 2025-06-30 |  |  |  | 0
Project 95 | 1001647 | Project | Line of Business 12 | Project Manager 27 | Sub-Portfolio 4 | Sponsor 19 | Medium | Waterfall | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2025-01-06 | 2025-06-30 | 367.6 | 2024-10-08 | 2026-04-15 | 2024-10-08 | 2026-04-15 |  |  |  | 0 | [11 empty] | No Changes | No Changes | No Changes |  |  | 2025-02-26
Project 97 | 1001274 | Project | Line of Business 12 | Project Manager 23 | Sub-Portfolio 4 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-03-11 | 2024-06-28 | [8 empty] | 0
Project 98 | 1001363 | Project | Line of Business 12 | Project Manager 39 | Sub-Portfolio 4 | Sponsor 19 |  | Agile | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 06 Dec 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-03-26 | 2025-06-30 | 309 | 2024-07-01 | 2025-06-30 | 309 | 2024-03-26 | 2025-06-30 | 2024-07-01 | 2025-06-30 | 2024-03-26 |  | 2025-06-02 | 42 | 50 | 22 | 28 | 29 |  | 9 | 28 |  |  | 2 | 2 | No Changes | No Changes | No Changes |  |  | 2024-08-29
Project 100 | 1001483 | Minor Work | Line of Business 12 | Project Manager 19 | Sub-Portfolio 4 |  | Important |  |  | Capital | Requested |  |  | Weekly | [17 empty] | 2024-04-29 | 2024-08-30 | 88.9 | 2024-04-29 | 2024-08-30 | 2024-04-29 | 2024-08-30 |  |  |  | 0
Project 99 | 1001273 | Minor Work | Line of Business 12 | Project Manager 23 | Sub-Portfolio 4 |  | Medium |  |  |  | Requested |  |  | Monthly | [17 empty] | 2024-03-11 | 2024-06-28 | [8 empty] | 0
Project 101 | 1000309 | Project | Line of Business 12 | Project Manager 3 | Sub-Portfolio 4 | Sponsor 19 |  | Waterfall | No | Capital | Completed | Gate 3 | 7. Closure | Weekly |  |  |  | 10 May 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2022-08-01 | 2024-11-06 | 570 |  |  | 570 | 2022-08-01 | 2024-11-06 |  |  | 2022-08-01 | 2024-11-06 |  | 100 | 17 | 17 |  | 17 | [6 empty] | 4 | No Changes | No Changes | No Changes |  | 1 |  |  |  | 2025-02-26
Project 102 | 1001863 | Light Project | Line of Business 12 | Project Manager 3 | Sub-Portfolio 4 | Sponsor 26 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-02-27 | 2025-06-30 | 84 | 2025-02-27 | 2025-06-30 | 2025-02-27 | 2025-06-30 |  |  |  | 0
Project 103 | 1001872 | Project | Line of Business 12 |  | Sub-Portfolio 4 | Sponsor 8 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-03-03 | 2025-06-30 | 82 | 2025-03-03 | 2025-06-30 | 2025-03-03 | 2025-06-30 |  |  |  | 0
Project 104 | 1001275 | Project | Line of Business 12 | Project Manager 23 | Sub-Portfolio 4 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-03-11 | 2024-06-28 | [8 empty] | 0
Project 105 | 1001823 | Minor Work | Line of Business 12 | Project Manager 3 | Sub-Portfolio 3 |  | High |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-12-16 | 2025-06-30 | 126 | 2024-12-16 | 2025-06-30 | 2024-12-16 | 2025-06-30 |  |  |  | 0
Project 106 | 1000292 | Project | Line of Business 12 | Project Manager 3 | Sub-Portfolio 4 | Sponsor 19 |  | Waterfall | No | Capital | Prepare for Closure | Gate 2 | 7. Closure | Weekly |  | Aug-2024 | 06 Jul 24 - 19 Jul 24 | 11 Oct 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2023-07-03 | 2024-04-26 | 199 | 2023-11-06 | 2024-08-15 | 390 | 2023-07-03 | 2025-02-05 | 2023-10-16 | 2025-02-05 | 2023-07-03 |  | 2024-03-26 | 13 | 10 | 10 |  | 10 | [6 empty] | 5 | Moderate Changes | Major Changes | Major Changes | 1 | 1 |  |  |  | 2024-10-29
Project 107 | 1001271 | Minor Work | Line of Business 12 | Project Manager 23 | Sub-Portfolio 4 |  | High |  |  |  | Requested |  |  | Monthly | [17 empty] | 2024-03-11 | 2024-06-28 | [8 empty] | 0
Project 108 | 1001364 | Project | Line of Business 12 | Project Manager 3 | Sub-Portfolio 4 | Sponsor 19 |  |  | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Mar-2025 |  | 07 Mar 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-07-01 | 2025-07-31 | 267 | 2024-07-01 | 2025-06-30 | 374 | 2024-07-01 | 2026-01-14 | 2024-07-01 | 2026-01-14 | 2024-09-24 |  | 2025-06-02 | 1 | 20 | 9 | 11 | 14 | 6 | 6 | 5 |  |  | 6 | 6 | [5 empty] | 2024-09-24 | 2024-12-30 | 2025-05-30 | 2025-08-30
Project 109 | 1000303 | Project | Line of Business 12 | Project Manager 18 | Sub-Portfolio 4 | Sponsor 3 |  | Waterfall | No | Capital | Open/Active | Gate 3 | 7. Closure | Weekly |  |  |  | 01 Dec 23 | Green | Green | Green | Green | Green | Green | Green |  | Amber | Green | 2022-10-04 | 2025-10-01 | 744 |  |  | 744 | 2022-10-04 | 2025-10-01 |  |  | 2022-10-04 | 2025-10-01 |  | 100 | 19 | 19 |  | 19
Project 110 | 1001608 | Minor Work | Line of Business 12 | Project Manager 5 | Sub-Portfolio 4 |  | High |  | No | Capex & Opex | Open/Active |  | 6. Implement | Weekly |  |  |  | 28 Feb 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2024-09-16 | 2025-02-28 | 178.9 | 2024-10-01 | 2025-06-30 | 2024-10-01 | 2025-06-30 |  |  | 2025-06-27 | 0 | 14 |  | 14
Project 111 | 1001825 | Project |  | Project Manager 18 | Sub-Portfolio 4 | Sponsor 28 |  |  |  |  | Requested |  | 2. Concept | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2024-12-16 | 2025-06-30 | 216 | 2024-09-19 | 2025-08-08 | 2024-09-19 | 2025-08-08 |  |  |  | 0
Project 112 | 1001804 | Minor Work |  | Project Manager 35 | Sub-Portfolio 7 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly | [17 empty] | 2024-11-15 | 2025-06-30 | [8 empty] | 0
Project 113 | 1001784 | Application Support |  | Project Manager 13 | Sub-Portfolio 1 |  | High |  |  | Opex | Requested |  | 6. Implement | Monthly | [17 empty] | 2024-07-01 | 2025-06-30 | 311 | 2024-07-01 | 2025-09-30 | 2024-07-01 | 2025-09-30 |  |  |  | 0
Project 114 | 1001785 | Application Support |  | Project Manager 9 | Sub-Portfolio 2 |  | High |  |  | Opex | Requested |  |  | Monthly | [17 empty] | 2024-07-01 | 2025-06-30 | 245 | 2024-07-01 | 2025-06-30 | 2024-07-01 | 2025-06-30 |  |  |  | 0
Project 115 | 1001786 | Application Support |  |  | Sub-Portfolio 4 |  | High |  |  | Opex | Requested |  | 6. Implement | Monthly | [17 empty] | 2024-07-01 | 2025-06-30 | 245 | 2024-07-01 | 2025-06-30 | 2024-07-01 | 2025-06-30 |  |  |  | 0
Project 116 | 1001788 | Application Support |  |  | Sub-Portfolio 5 |  | High |  |  | Opex | Requested |  | 6. Implement | Monthly | [17 empty] | 2024-07-01 | 2025-06-30 | 245 | 2024-07-01 | 2025-06-30 | 2024-07-01 | 2025-06-30 |  |  |  | 0
Project 117 | 1001789 | Application Support |  |  | Sub-Portfolio 6 |  | High |  |  | Opex | Requested |  | 6. Implement | Monthly | [17 empty] | 2024-07-01 | 2025-06-30 | 245 | 2024-07-01 | 2025-06-30 | 2024-07-01 | 2025-06-30 |  |  |  | 0
Project 118 | 1001787 | Application Support |  |  | Sub-Portfolio 7 |  | High |  |  | Opex | Requested |  | 6. Implement | Monthly | [17 empty] | 2024-07-01 | 2025-06-30 | 245 | 2024-07-01 | 2025-06-30 | 2024-07-01 | 2025-06-30 |  |  |  | 0
Project 119 | 1001790 | Application Support |  |  | Sub-Portfolio 8 |  | High |  |  | Opex | Requested |  | 6. Implement | Monthly | [17 empty] | 2024-07-01 | 2025-06-30 | 245 | 2024-07-01 | 2025-06-30 | 2024-07-01 | 2025-06-30 |  |  |  | 0
Project 120 | 1000298 | Project | Line of Business 12 | Project Manager 38 | Sub-Portfolio 4 | Sponsor 19 |  | Waterfall | No | Capital | Open/Active | Gate 3 | 6. Implement | Weekly |  |  |  | 07 Mar 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2022-08-16 | 2025-06-30 | 712 | 2023-07-03 | 2025-06-30 | 712 | 2022-08-16 | 2025-06-30 | 2022-11-24 | 2025-06-30 | 2022-08-16 |  | 2025-06-27 | 18 | 18 | 11 | 7 | 12 |  | 1 | 7 |  |  | 1 | 4 | No Changes | No Changes | No Changes |  | 1
Project 121 | 1000301 | Project | Line of Business 16 | Project Manager 17 | Sub-Portfolio 7 | Sponsor 25 |  | Waterfall | No | Opex | Open/Active | Gate 1 | 6. Implement | Monthly |  | Feb-2025 |  |  | Red | Green | Amber | Red | Green | Green | Green |  | Red | Red | 2021-03-18 | 2024-12-20 | 959 |  |  | 1080 | 2021-03-18 | 2025-06-30 | 2021-03-18 | 2025-06-30 | 2021-03-18 |  | 2025-06-02 | 42 | 73 | 63 | 10 | 72 | 10 | 10 |  |  |  | 1 | 1 | No Changes | No Changes | Minor Changes | 1 | 4
Project 122 | 1000293 | Project | Line of Business 7 | Project Manager 18 | Sub-Portfolio 4 | Sponsor 32 |  | Waterfall | No | Capital | Open/Active | End | 6. Implement | Fortnightly |  |  | 19 Feb 24 - 01 Mar 24 | 12 Jan 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2022-08-16 | 2024-02-29 | 385 |  |  | 467 | 2022-08-16 | 2024-06-28 | 2024-02-12 | 2024-06-28 | 2022-08-16 |  | 2024-03-15 | 80 | 11 | 11 |  | 11 | [6 empty] | 5 |  |  |  |  | 1
Project 123 | 1000314 | Project | Line of Business 7 | Project Manager 33 | Sub-Portfolio 7 | Sponsor 14 |  | Hybrid | Yes | Capital | Open/Active | Gate 1 | 6. Implement | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Green | Amber | Green | Green |  | Amber | Green | 2023-03-22 | 2025-08-11 | 588 | 2023-03-22 | 2025-04-10 | 588 | 2023-03-22 | 2025-08-11 | 2023-09-11 | 2025-08-11 | 2023-03-22 |  | 2025-06-30 | 22 | 85 | 55 | 30 | 58 |  | 3 | 30 |  |  |  | 1 | Moderate Changes | Moderate Changes | Moderate Changes
Project 124 | 1001420 | Light Project | Line of Business 7 | Project Manager 18 | Sub-Portfolio 4 | Sponsor 48 | Medium |  | No | Capital | Requested |  | 2. Concept | Weekly | [17 empty] | 2024-03-04 | 2024-08-30 | 140.9 | 2024-04-15 | 2024-10-31 | 2024-04-15 | 2024-10-31 |  |  |  | 0
Project 125 | 1000962 | Minor Work | Line of Business 15 | Project Manager 27 | Sub-Portfolio 7 | Sponsor 29 |  | Hybrid |  |  | Prepare for Closure |  | 2. Concept | Monthly |  | Mar-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2023-12-12 | 2024-06-28 | 161.9 | 2024-01-11 | 2024-08-30 | 2024-01-11 | 2024-08-30 | 2024-03-14 |  |  | 36 | [11 empty] | No Changes | No Changes | No Changes
Project 126 | 1000924 | Project | Line of Business 7 | Project Manager 18 | Sub-Portfolio 4 |  |  |  | No | Opex | Requested |  | 2. Concept | Weekly |  |  |  | 01 Dec 23 | Green | Green | Green | Green | Green | Green | Green |  | Red | Green |  |  |  | 2023-09-01 | 2024-04-30 | 158 | 2023-09-01 | 2024-04-30 | 2023-09-01 | 2024-04-30 |  |  |  | 0
Project 127 | 1001829 | Project |  | Project Manager 35 | Sub-Portfolio 7 | Sponsor 40 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-01-28 | 2025-06-30 | 106 | 2025-01-28 | 2025-06-30 | 2025-01-28 | 2025-06-30 |  |  |  | 0
Project 128 | 1000315 | Project | Line of Business 7 | Project Manager 35 | Sub-Portfolio 7 | Sponsor 24 |  | Waterfall |  |  | Open/Active |  | 2. Concept | Monthly |  | Oct-2023 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | [5 empty] | 1593 | 2021-04-19 | 2027-08-27 | 2023-10-03 | 2027-08-27 | 2021-04-19 |  | 2027-06-21 | 10 | 4 | 4
Project 129 | 1000990 | Project | Line of Business 17 | Project Manager 12 | Sub-Portfolio 8 | Sponsor 18 |  | Waterfall | No | Capex & Opex | Completed | Gate 3 | 7. Closure | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2023-12-18 | 2024-05-15 | 93.5 | 2023-12-19 | 2024-03-28 | 93.5 | 2023-12-18 | 2024-05-15 |  |  | 2023-12-18 | 2024-05-15 |  | 100 | [10 empty] | 1 |  |  |  |  | 2 |  |  |  | 2024-09-25
Project 130 | 1000841 | Project | Line of Business 18 | Project Manager 38 | Sub-Portfolio 7 |  |  |  | No | Opex | On Hold | Gate 0 | 3. Evaluate | Monthly |  | Feb-2024 |  | 26 Jan 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2024-01-15 | 2024-06-28 | 115 | 2024-01-15 | 2024-06-28 | 2024-01-15 | 2024-06-28 |  |  |  | 0 | [10 empty] | 2 |  |  |  |  | 1
Project 131 | 1001375 | Project | Line of Business 8 | Project Manager 25 | Sub-Portfolio 8 |  |  |  |  | Capital | Requested |  | 2. Concept | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2024-03-01 | 2024-06-28 | 93.8 | 2024-03-01 | 2024-07-16 | 2024-03-01 | 2024-07-16 |  |  |  | 0 | [9 empty] | 1 | 2 |  |  |  |  | 1
Project 132 | 1000296 | Project | Line of Business 4 | Project Manager 8 | Sub-Portfolio 7 | Sponsor 21 |  | Hybrid | Yes | Capex & Opex | Open/Active | Gate 1 | 4. Analyse & Design | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Amber | Green | Green | Green |  | Amber | Green | 2019-07-01 | 2028-06-02 | 2262.5 | 2021-08-23 | 2026-12-24 | 2262.5 | 2019-07-01 | 2028-06-02 | 2019-10-18 | 2028-06-02 | 2019-07-01 |  | 2030-06-26 | 17 | 158 | 61 | 97 | 62 |  | 1 | 97 |  | 1 | 2 | 5 | Major Changes | Major Changes | Major Changes |  | 1 |  | 2025-02-26
Project 133 | 1001857 | Project |  |  | Sub-Portfolio 7 | Sponsor 46 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-02-17 | 2025-06-30 | [8 empty] | 0
Project 134 | 1001269 | Project | Line of Business 2 | Project Manager 35 | Sub-Portfolio 7 | Sponsor 14 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2024-03-08 | 2024-07-31 | 86 | 2024-03-25 | 2024-07-26 | 2024-03-25 | 2024-07-26 |  |  |  | 0
Project 135 | 1001871 | Project |  |  | Sub-Portfolio 7 | Sponsor 45 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-03-03 | 2025-06-30 | 82 | 2025-03-03 | 2025-06-30 | 2025-03-03 | 2025-06-30 |  |  |  | 0
Project 136 | 1001643 | Minor Work |  | Project Manager 27 | Sub-Portfolio 7 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Monthly | [17 empty] | 2024-09-30 | 2025-03-31 | 160 | 2024-09-30 | 2025-05-30 | 2024-09-30 | 2025-05-30 |  |  |  | 0
Project 137 | 1000869 | Project |  | Project Manager 17 | Sub-Portfolio 7 | Sponsor 50 |  | Hybrid | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2021-07-01 | 2025-08-28 | 1047 | 2023-11-15 | 2027-06-30 | 1248 | 2021-07-01 | 2026-06-30 | 2022-11-14 | 2026-06-30 | 2021-07-01 |  | 2025-06-27 | 14 | 69 | 16 | 53 | 35 | 6 | 19 | 37 |  |  | 2 | 3 | Minor Changes | Minor Changes | Minor Changes | 6 | 6 | 2023-11-16
Project 138 | 1000838 | Project | Line of Business 14 |  | Sub-Portfolio 7 |  |  |  | No | Capital | On Hold |  | 2. Concept | Monthly | [17 empty] | 2024-07-01 | 2026-12-17 | 365 | 2025-07-01 | 2026-12-17 | 2025-07-01 | 2026-12-17 |  |  |  | 0
Project 139 | 1001351 | Project | Line of Business 19 | Project Manager 29 | Sub-Portfolio 8 | Sponsor 10 |  | Hybrid | No | Capital | Open/Active | Gate 1 | 6. Implement | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Amber | Green | Green | Green |  | Green | Green | 2024-08-01 | 2025-06-30 | 221 | 2024-07-01 | 2024-12-20 | 221 | 2024-08-01 | 2025-06-30 | 2024-08-26 | 2025-06-30 | 2024-08-01 |  | 2025-06-02 | 14 | 68 | 50 | 18 | 54 | 4 | 4 | 14 |  |  | 5 | 7 | No Changes | Minor Changes | Minor Changes |  | 1 | 2024-08-21 | 2024-12-19
Project 140 | 1000295 | Minor Work | Line of Business 7 | Project Manager 39 | Sub-Portfolio 4 | Sponsor 2 |  | Waterfall | No | Capital | Requested | Gate 1 | 6. Implement | Weekly |  |  |  | 06 Dec 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2022-08-29 | 2024-12-20 | 582 |  |  | 703 | 2022-08-29 | 2025-06-30 | 2024-05-01 | 2025-06-30 | 2022-08-29 |  | 2025-06-27 | 99 | 34 | 31 | 3 | 34 | 3 | 3 |  |  |  | 1 | 22 | No Changes | Minor Changes | No Changes |  | 3
Project 141 | 1001347 | Project | Line of Business 7 | Project Manager 16 | Sub-Portfolio 8 | Sponsor 18 |  | Agile | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 28 Feb 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-09-02 | 2025-06-25 | 196 | 2024-07-01 | 2026-06-30 | 196 | 2024-09-02 | 2025-06-25 | 2025-01-24 | 2025-06-25 | 2024-09-02 |  | 2026-06-30 | 9 | 30 | 6 | 24 | 30 | 4 | 24 | 20 |  |  | 1 | 3 | Moderate Changes | Major Changes | Major Changes |  |  | 2024-09-25
Project 142 | 1001350 | Project | Line of Business 13 | Project Manager 25 | Sub-Portfolio 8 | Sponsor 18 |  | Agile | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-07-01 | 2025-09-08 | 295 | 2024-07-01 | 2025-06-30 | 197 | 2024-07-01 | 2025-04-17 | 2024-07-01 | 2025-04-17 | 2024-09-06 |  | 2025-06-02 | 1 | 49 | 44 | 5 | 50 | 5 | 8 |  |  | 1 |  | 10 | No Changes | No Changes | Minor Changes |  | 3 | 2024-08-28
Project 143 | 1001355 | Project |  | Project Manager 12 | Sub-Portfolio 8 |  |  | Hybrid | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 28 Feb 25 | Amber | Green | Amber | Amber | Amber | Green | Green |  | Green | Red | 2024-07-01 | 2025-06-30 | 244.9 | 2024-07-01 | 2025-06-30 | 332.9 | 2024-07-01 | 2025-10-31 | 2024-07-01 | 2025-10-31 | 2024-08-30 |  | 2025-06-02 | 0 | 41 | 20 | 21 | 29 | 4 | 9 | 17 |  |  | 3 | 3 | Moderate Changes | Major Changes | Major Changes | 1 | 1
Project 144 | 1001440 | Project | Line of Business 24 | Project Manager 13 | Sub-Portfolio 8 |  |  | Agile | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Feb-2025 |  |  | Red | Red | Red | Amber | Amber | Green | Green |  | Amber | Red | 2024-05-10 | 2026-06-04 | 506 | 2024-05-01 | 2025-06-30 | 506 | 2024-05-10 | 2026-06-04 | 2024-07-01 | 2026-06-04 | 2024-05-10 |  | 2025-06-02 | 6 | 52 | 18 | 34 | 42 | 2 | 24 | 32 |  |  | 2 | 2 | No Changes | Moderate Changes | No Changes | 2 | 2
Project 145 | 1000306 | Light Project | Line of Business 7 | Project Manager 26 | Sub-Portfolio 5 | Sponsor 43 |  | Hybrid | No | Opex | Completed | Gate 3 | 7. Closure | Monthly |  | Jun-2024 |  |  | Green | Green | Green |  | Green | Green |  |  | Green |  | 2018-01-01 | 2024-07-18 | 1687 | 2023-07-03 | 2024-06-28 | 1677 | 2018-01-12 | 2024-07-18 |  |  | 2018-01-12 | 2024-07-18 |  | 100 | 7 | 7 |  | 7 | [7 empty] | No Changes | No Changes | No Changes | [5 empty] | 2024-07-12
Project 146 | 1001138 | Application Support |  |  | Sub-Portfolio 5 |  | High |  |  |  | Requested |  |  | Weekly | [17 empty] | 2024-02-01 | 2024-06-28 | 115 | 2024-01-15 | 2024-06-28 | 2024-01-15 | 2024-06-28 |  |  |  | 0
Project 147 | 1001282 | Project |  | Project Manager 14 | Sub-Portfolio 7 | Sponsor 7 |  | Agile | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Feb-2025 |  |  | Amber | Green | Amber | Amber | Amber | Green | Green |  | Amber | Amber | 2024-04-24 | 2026-02-16 | 440.9 | 2024-03-04 | 2025-06-30 | 440.9 | 2024-04-24 | 2026-02-16 | 2024-09-02 | 2026-02-16 | 2024-04-24 |  | 2025-06-02 | 22 | 59 | 40 | 19 | 48 | 8 | 8 | 11 |  |  | 4 | 10 | Moderate Changes | Moderate Changes | Moderate Changes | 6 | 8 | 2024-03-28
Project 149 | 1001171 | Minor Work | Line of Business 6 | Project Manager 18 | Sub-Portfolio 4 | Sponsor 38 | Important |  | No | Capital | Requested |  | 2. Concept | Weekly | [17 empty] | 2024-02-26 | 2024-06-28 | 85.9 | 2024-02-26 | 2024-06-28 | 2024-02-26 | 2024-06-28 |  |  |  | 0
Project 150 | 1000921 | Project | Line of Business 7 | Project Manager 18 | Sub-Portfolio 4 |  |  |  | No | Capex & Opex | Cancelled |  | 2. Concept | Weekly |  |  |  | 01 Dec 23 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 2023-08-01 | 2024-06-28 | 223 | 2023-08-01 | 2024-06-28 |  |  | 2023-08-01 | 2024-06-28 |  | 100
Project 151 | 1000310 | Project | Line of Business 7 | Project Manager 6 | Sub-Portfolio 8 | Sponsor 36 |  | Hybrid | No | Capex & Opex | Open/Active | Gate 1 | 5. Build & Test | Monthly |  | Feb-2025 |  | 14 Jun 24 | Green | Green | Green | Green | Green | Green | Green |  | Amber | Amber | 2023-07-03 | 2029-12-21 | 1619 | 2023-07-03 | 2027-06-30 | 1619 | 2023-07-03 | 2029-12-21 | 2024-02-01 | 2029-12-21 | 2023-07-03 |  | 2026-05-08 | 21 | 203 | 95 | 108 | 145 | 2 | 51 | 106 |  |  | 7 | 10 | Moderate Changes | Major Changes | Moderate Changes | 3 | 5
Project 152 | 1000313 | Project | Line of Business 7 | Project Manager 32 | Sub-Portfolio 1 | Sponsor 13 |  | Waterfall | No | Opex | Prepare for Closure | Gate 2 | 7. Closure | Monthly | [14 empty] | 2023-08-01 | 2024-05-30 | 203 |  |  | 203 | 2023-08-01 | 2024-05-30 | 2023-08-01 | 2024-05-30 | 2023-08-01 |  |  | 10 | 3 | 3 |  | 3
Project 153 | 1001803 | Minor Work |  | Project Manager 35 | Sub-Portfolio 7 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly | [17 empty] | 2024-11-15 | 2025-06-30 | [8 empty] | 0
Project 154 | 1001349 | Project | Line of Business 12 | Project Manager 27 | Sub-Portfolio 4 | Sponsor 19 |  | Agile | No | Capex & Opex | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 28 Feb 25 | Green | Green | Green | Amber | Green | Green | Green |  | Amber | Green | 2024-03-26 | 2025-08-01 | 332 | 2024-07-01 | 2025-12-24 | 332 | 2024-03-26 | 2025-08-01 | 2024-07-01 | 2025-08-01 | 2024-03-26 |  | 2025-06-27 | 16 | 53 | 19 | 34 | 25 | 4 | 6 | 30 |  |  | 3 | 4 | Moderate Changes | Moderate Changes | Moderate Changes |  |  | 2024-08-29
Project 155 | 1000312 | Project | Line of Business 3 | Project Manager 10 | Sub-Portfolio 7 | Sponsor 17 |  | Agile | Yes | Capital | Completed | Gate 3 | 7. Closure | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Amber | Green | Green | Amber |  | Amber | Green | 2021-07-12 | 2024-11-25 | 858 | 2024-07-01 | 2025-06-30 | 858 | 2021-07-12 | 2024-11-25 |  |  | 2021-07-12 | 2024-11-25 |  | 100 | 27 | 27 |  | 27 | [5 empty] | 1 | 11 |  |  |  |  | 4 |  |  | 2024-08-28 | 2024-11-28
Project 156 | 1001869 | Minor Work |  |  | Sub-Portfolio 3 | [5 empty] | Requested |  | 2. Concept | Weekly | [17 empty] | 2025-03-03 | 2025-03-03 | [8 empty] | 0
Project 157 | 1000987 | Project | Line of Business 22 | Project Manager 29 | Sub-Portfolio 7 | Sponsor 51 |  | Hybrid | No | Capex & Opex | Open/Active | Gate 1 | 4. Analyse & Design | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Amber | Green | Green | Green |  | Green | Green | 2024-04-19 | 2027-02-26 | 698 | 2023-12-18 | 2025-12-24 | 698 | 2024-04-19 | 2027-02-26 | 2024-07-01 | 2027-02-26 | 2024-04-19 |  | 2025-06-02 | 34 | 69 | 35 | 34 | 49 | 12 | 14 | 22 |  |  | 2 | 7 | Minor Changes | Minor Changes | Minor Changes |  | 2 | 2024-08-06 | 2024-08-12
Project 158 | 1001774 | Project |  | Project Manager 4 | Sub-Portfolio 4 | Sponsor 19 |  |  |  |  | Requested |  | 2. Concept | Monthly |  | Jan-2025 |  | 21 Feb 25 | Green | Green | Green | Amber | Green | Green | Green |  | Green | Green |  |  |  | 2024-11-01 | 2025-06-30 | 192 | 2024-11-01 | 2025-08-18 | 2024-12-02 | 2025-08-18 | 2024-11-01 |  | 2025-04-08 | 38 | 6 | 1 | 5
Project 159 | 1001777 | Minor Work |  | Project Manager 14 | Sub-Portfolio 4 | Sponsor 19 | Medium |  |  |  | Requested |  | 2. Concept | Monthly |  | Feb-2025 |  | 21 Feb 25 | Green | Green | Green | Amber | Green | Green | Green |  | Amber | Green | 2024-11-01 | 2025-12-19 | 280 | 2024-11-01 | 2025-06-30 | 280 | 2024-11-01 | 2025-12-19 | 2024-11-01 | 2025-12-19 | 2024-11-01 |  |  | 10 | 8 |  | 8 |  |  |  | 8
Project 160 | 1001775 | Light Project |  | Project Manager 14 | Sub-Portfolio 4 | Sponsor 19 |  |  | No | Capital | Requested |  | 2. Concept | Monthly |  | Feb-2025 |  | 21 Feb 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-11-01 | 2025-06-30 | 157 | 2024-11-01 | 2025-06-30 | 157 | 2024-11-01 | 2025-06-30 | 2024-11-01 | 2025-06-30 |  |  | 2025-06-02 | 0 | 8 |  | 8
Project 161 | 1001776 | Light Project |  | Project Manager 14 | Sub-Portfolio 4 | Sponsor 19 |  |  | No | Capital | Requested |  | 2. Concept | Monthly |  | Feb-2025 |  | 21 Feb 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-11-01 | 2026-06-30 | 401 | 2024-11-01 | 2025-06-30 | 279 | 2024-11-01 | 2025-12-19 | 2024-11-01 | 2025-12-19 |  |  | 2025-06-02 | 0 | 12 |  | 12
Project 162 | 1001428 | Minor Work |  | Project Manager 13 | Sub-Portfolio 7 |  | High |  |  |  | Requested |  |  | Monthly | [17 empty] | 2024-04-17 | 2024-06-28 | 103 | 2024-02-01 | 2024-06-28 | 2024-02-01 | 2024-06-28 |  |  |  | 0
Project 163 | 1000304 | Project | Line of Business 7 | Project Manager 22 | Sub-Portfolio 8 | Sponsor 18 |  | Hybrid | Yes | Capital | Prepare for Closure | Gate 2 | 7. Closure | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2023-02-13 | 2025-03-31 | 523 | 2023-09-01 | 2024-12-20 | 523 | 2023-02-13 | 2025-03-31 | 2023-07-03 | 2025-03-31 | 2023-02-13 |  |  | 39 | 75 | 71 | 4 | 71 |  |  | 4 |  |  | 2 | 6 | Moderate Changes | Minor Changes | Major Changes | 1 | 6 |  |  | 2025-03-06
Project 164 | 1000316 | Project | Line of Business 17 | Project Manager 38 | Sub-Portfolio 7 | Sponsor 4 |  | Agile | No | Capital | Completed | Gate 3 | 7. Closure | Monthly |  | May-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2021-06-30 | 2024-05-31 | 742 | 2022-02-01 | 2024-05-31 | 742 | 2021-06-30 | 2024-05-31 |  |  | 2021-06-30 | 2024-05-31 |  | 100 | 19 | 19 |  | 19 | [6 empty] | 2 | Moderate Changes | No Changes | No Changes |  | 1 |  |  |  | 2024-06-30
Project 165 | 1000307 | Project | Line of Business 3 | Project Manager 34 | Sub-Portfolio 7 | Sponsor 17 |  | Waterfall | Yes | Capex & Opex | Open/Active | Gate 1 | 5. Build & Test | Monthly |  | Feb-2025 |  |  | Amber | Green | Amber | Amber | Green | Green | Green |  | Amber | Amber | 2019-06-04 | 2029-12-21 | 2677 |  |  | 2853.9 | 2018-09-28 | 2035-02-21 | 2018-09-28 | 2035-02-21 | 2021-06-14 |  | 2035-01-01 | 11 | 85 | 56 | 29 | 55 | 15 | 1 | 7 |  |  | 25 | 44 | Major Changes | Major Changes | Major Changes | 2 | 6
Project 166 | 1001399 | Project | Line of Business 7 | Project Manager 14 | Sub-Portfolio 4 |  | Important | Agile | No | Capital | Prepare for Closure | Gate 2 | 7. Closure | Weekly |  |  |  | 31 Jan 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-03-28 | 2025-02-03 | 205.1 | 2024-04-05 | 2025-06-30 | 205.1 | 2024-03-28 | 2025-02-03 | 2024-07-01 | 2025-01-31 | 2024-03-28 |  | 2025-06-02 | 100 | 53 | 53 |  | 53 | [6 empty] | 2 | Minor Changes | No Changes | Minor Changes |  |  | 2024-03-28 | 2025-02-03 | 2024-11-29 | 2025-02-28
Project 167 | 1001358 | Project |  | Project Manager 30 | Sub-Portfolio 7 |  |  | Hybrid | No | Capex & Opex | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 07 Feb 25 | Red | Green | Red | Red | Amber | Green | Green |  | Green | Green | 2024-07-31 | 2025-09-22 | 281.9 | 2024-07-01 | 2025-06-30 | 340.9 | 2024-07-31 | 2025-12-15 | 2024-12-13 | 2025-12-15 | 2024-07-31 |  | 2025-07-01 | 15 | 72 | 30 | 42 | 31 | 24 | 4 |  |  |  | 5 | 5 | Moderate Changes | Minor Changes | Minor Changes |  |  | 2024-08-29 | 2025-02-24 | 2025-08-31 | 2025-09-30
Project 168 | 1001239 | Minor Work |  | Project Manager 13 | Sub-Portfolio 3 |  | Low | Waterfall | No | Capital | Completed | Gate 3 | 7. Closure | Weekly | [14 empty] | 2024-04-02 | 2024-07-29 | 83 | 2024-03-07 | 2024-06-28 | 83 | 2024-04-02 | 2024-07-29 |  |  | 2024-04-02 | 2024-07-29 |  | 100 | 9 | 9 |  | 9 | [7 empty] | No Changes | No Changes | No Changes | 1 | 1 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30
Project 169 | 1001618 | Minor Work |  | Project Manager 36 | Sub-Portfolio 4 | Sponsor 11 | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly |  | Jan-2025 |  | 07 Mar 25 | Green | Green | Green | Amber | Green | Green | Green |  | Green | Green |  |  |  | 2024-09-11 | 2025-05-09 | 151 | 2024-09-11 | 2025-04-30 | 2024-09-11 | 2025-04-30 | 2024-09-30 |  | 2025-04-08 | 15 | 12 | 8 | 4 | [6 empty] | 2 | 3
Project 170 | 1001755 | Project |  | Project Manager 3 | Sub-Portfolio 4 | Sponsor 8 |  |  | No | Capex & Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 2025-02-17 | 2025-06-30 | 91.9 | 2025-02-17 | 2025-06-30 | 2025-02-17 | 2025-06-30 |  |  |  | 0
Project 171 | 1001805 | Minor Work |  | Project Manager 35 | Sub-Portfolio 7 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly | [17 empty] | 2024-11-15 | 2025-06-30 | [8 empty] | 0
Project 172 | 1001359 | Project |  | Project Manager 21 | Sub-Portfolio 8 | Sponsor 18 |  | Waterfall | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 28 Feb 25 | Green | Green | Amber | Green | Green | Green | Green |  | Green | Green | 2024-03-26 | 2025-06-30 | 310 | 2024-07-01 | 2025-06-30 | 397 | 2024-03-26 | 2025-10-31 | 2025-01-06 | 2025-10-31 | 2024-03-26 |  | 2025-06-02 | 47 | 11 | 5 | 6 | 5 | [5 empty] | 8 | 8 | No Changes | Minor Changes | Minor Changes |  |  | 2024-03-26