## Chart
Milestone Status Summary
Portfolio: Portfolio_GS IT All Projects

## Detail Table
Project Status | Schedule Variance | Project Description | Milestone Description | Milestone Type | Milestone Indentifier | Project Status | Stage | Work Notes: | Actual/Schedule Finish | Baseline Date | Variance (d) | Variance (%)
Requested | 0% | Project 132 | Release 1.1 Go-Live | Deliverable | Go-Live | Requested | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0%
Requested | 0% | Project 132 | Release 1.2 Go-Live | Deliverable | Go-Live | Requested | 3. Evaluate | Delay reason shown here | 2026-04-01 17:00 | 2026-04-01 17:00 | 0 | 0%
Requested | 0% | Project 132 | Release 1.3 Go-Live | Deliverable | Go-Live | Requested | 3. Evaluate | Delay reason shown here | 2026-09-04 17:00 | 2026-09-04 17:00 | 0 | 0%
Requested | 0% | Project 143 | 4.09 Test Plan Sign Off Phase 2 | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Requested | 0% | Project 143 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Requested | 3. Evaluate | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
Requested | -25% to -10% | Project 59 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -15.67%
Requested | -25% to -10% | Project 59 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -15.67%
Requested | N/A | Project 22 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Requested | 2. Concept | Delay reason shown here | 2025-12-12 17:00
Requested | N/A | Project 22 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Requested | 2. Concept | Delay reason shown here | 2025-12-15 17:00
Requested | N/A | Project 22 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Requested | 2. Concept | Delay reason shown here | 2025-12-17 17:00
Requested | N/A | Project 22 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Requested | 2. Concept | Delay reason shown here | 2025-12-22 17:00
Requested | -10% to -5% | Project 154 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Requested | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-03-17 08:00 | -32 | -9.639%
Requested | -25% to -10% | Project 140 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Requested | 6. Implement | Delay reason shown here | 2025-05-01 17:00 | 2024-12-20 17:00 | -80 | -11.38%
Requested | -25% to -10% | Project 140 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Requested | 6. Implement | Delay reason shown here | 2025-05-01 17:00 | 2024-12-20 17:00 | -80 | -11.38%
Requested | -25% to -10% | Project 140 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Requested | 6. Implement | Delay reason shown here | 2025-05-01 17:00 | 2024-12-20 17:00 | -80 | -11.38%
Requested | 0% | Project 83 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Requested | 3. Evaluate | Delay reason shown here | 2026-04-30 17:00 | 2026-04-30 17:00 | 0 | 0%
Requested | 0% | Project 83 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Requested | 3. Evaluate | Delay reason shown here | 2026-04-30 17:00 | 2026-04-30 17:00 | 0 | 0%
Requested | 0% | Project 83 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Requested | 3. Evaluate | Delay reason shown here | 2026-04-30 17:00 | 2026-04-30 17:00 | 0 | 0%
Requested | 0% | Project 83 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Requested | 3. Evaluate | Delay reason shown here | 2026-04-30 17:00 | 2026-04-30 17:00 | 0 | 0%
Requested | 0% | Project 83 | System Architect Replacement | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-10-31 08:00 | 2025-10-31 08:00 | 0 | 0%
Requested | 0% | Project 83 | Microfocus to TOSCA migration for Automation suite | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-09-02 08:00 | 2025-09-02 08:00 | 0 | 0%
Requested | 0% | Project 83 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-20 17:00 | 2026-03-20 17:00 | 0 | 0%
Requested | 0% | Project 83 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-20 17:00 | 2026-03-20 17:00 | 0 | 0%
Requested | 0% | Project 83 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-20 17:00 | 2026-03-20 17:00 | 0 | 0%
Requested | 0% | Project 83 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-20 17:00 | 2026-03-20 17:00 | 0 | 0%
Requested | 0% | Project 83 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-20 17:00 | 2026-03-20 17:00 | 0 | 0%
Requested | 0% | Project 83 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-20 17:00 | 2026-03-20 17:00 | 0 | 0%
Requested | 0% | Project 83 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-20 17:00 | 2026-03-20 17:00 | 0 | 0%
Requested | 0% | Project 83 | GO LIVE | Deliverable | Go-Live | Requested | 3. Evaluate | Delay reason shown here | 2026-03-23 17:00 | 2026-03-23 17:00 | 0 | 0%
Requested | 0% | Project 83 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-31 17:00 | 2026-03-31 17:00 | 0 | 0%
Requested | 0% | Project 83 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-06 17:00 | 2026-03-06 17:00 | 0 | 0%
Requested | 0% | Project 83 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0%
Requested | 0% | Project 83 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-06 17:00 | 2026-03-06 17:00 | 0 | 0%
Requested | 0% | Project 83 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-06 17:00 | 2026-03-06 17:00 | 0 | 0%
Requested | 0% | Project 83 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-06 17:00 | 2026-03-06 17:00 | 0 | 0%
Requested | 0% | Project 83 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-06 17:00 | 2026-03-06 17:00 | 0 | 0%
Requested | 0% | Project 83 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-06 17:00 | 2026-03-06 17:00 | 0 | 0%
Requested | 0% | Project 83 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-20 17:00 | 2026-03-20 17:00 | 0 | 0%
Requested | 0% | Project 83 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-06 17:00 | 2026-03-06 17:00 | 0 | 0%
Requested | 0% | Project 83 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Requested | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-06-06 17:00 | 2025-06-06 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-06-06 17:00 | 2025-06-06 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-09-12 17:00 | 2025-09-12 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-09-12 17:00 | 2025-09-12 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-06-13 17:00 | 2025-06-13 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-09-12 17:00 | 2025-09-12 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-09-12 17:00 | 2025-09-12 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-09-12 17:00 | 2025-09-12 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-09-12 17:00 | 2025-09-12 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-09-12 17:00 | 2025-09-12 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Requested | 0% | Project 83 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-09-12 17:00 | 2025-09-12 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Requested | 0% | Project 83 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Requested | 0% | Project 132 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2027-01-11 17:00 | 2027-01-11 17:00 | 0 | 0%
Requested | N/A | Project 87 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-07-07 08:00
Requested | N/A | Project 87 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-07-07 08:00
Requested | N/A | Project 87 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-15 17:00
Requested | N/A | Project 87 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-22 17:00
Requested | N/A | Project 87 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-08-29 08:00
Requested | N/A | Project 87 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-07-21 08:00
Requested | N/A | Project 87 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-07-21 08:00
Requested | N/A | Project 87 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Requested | 2. Concept | Delay reason shown here | 2026-06-05 17:00
Requested | N/A | Project 87 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Requested | 2. Concept | Delay reason shown here | 2026-06-12 17:00
Requested | N/A | Project 87 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Requested | 2. Concept | Delay reason shown here | 2026-06-19 17:00
Requested | N/A | Project 87 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Requested | 2. Concept | Delay reason shown here | 2026-06-30 17:00
Requested | N/A | Project 120 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Requested | 6. Implement | Delay reason shown here | 2025-05-30 17:00
Requested | N/A | Project 158 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-06-26 08:00
Requested | N/A | Project 158 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-06-26 08:00
Requested | N/A | Project 158 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-06-26 08:00
Requested | N/A | Project 158 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-06-26 08:00
Requested | N/A | Project 158 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-06-26 08:00
Requested | N/A | Project 160 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-04-30 17:00
Requested | N/A | Project 160 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-04-30 17:00
Requested | N/A | Project 160 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here
Requested | N/A | Project 160 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00
Requested | N/A | Project 160 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00
Requested | N/A | Project 160 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00
Requested | N/A | Project 161 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-04-30 17:00
Requested | N/A | Project 161 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-04-30 17:00
Requested | N/A | Project 161 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-04-30 17:00
Requested | N/A | Project 161 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00
Requested | N/A | Project 161 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00
Requested | N/A | Project 161 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00
Requested | N/A | Project 161 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00
Requested | N/A | Project 161 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00
Requested | N/A | Project 161 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00
Requested | N/A | Project 161 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00
Requested | -10% to -5% | Project 159 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-04-30 17:00 | 2025-03-31 17:00 | -19 | -6.714%
Requested | -10% to -5% | Project 159 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-04-30 17:00 | 2025-03-31 17:00 | -19 | -6.714%
Requested | -10% to -5% | Project 159 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00 | 2025-04-17 17:00 | -28 | -9.894%
Requested | -25% to -10% | Project 159 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00 | 2025-04-14 17:00 | -31 | -10.95%
Requested | -25% to -10% | Project 159 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00 | 2025-04-14 17:00 | -31 | -10.95%
Requested | -10% to -5% | Project 159 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00 | 2025-04-17 17:00 | -28 | -9.894%
Requested | -10% to -5% | Project 159 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-05-30 17:00 | 2025-04-30 17:00 | -22 | -7.774%
Requested | -10% to -5% | Project 144 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Requested | 3. Evaluate | Delay reason shown here | 2025-05-12 17:00 | 2025-02-28 17:00 | -48 | -9.486%
Requested | N/A | Project 170 | Closure Phase | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-07-04 08:00
Requested | N/A | Project 170 | Documentation Deliverables (SAD,BRD,Test Plan) | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-05-16 08:00
Requested | N/A | Project 170 | Analysis and Design Phase Completed | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-05-16 08:00
Requested | N/A | Project 170 | Procurement phase completed | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-04-24 08:00
Requested | N/A | Project 170 | Build and test completed | Deliverable | Unassigned | Requested | 2. Concept | Delay reason shown here | 2025-06-02 08:00
Requested | N/A | Project 94 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-06-30 17:00
Requested | N/A | Project 94 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-06-30 17:00
Requested | N/A | Project 94 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-06-30 17:00
Requested | N/A | Project 94 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-06-30 17:00
Requested | N/A | Project 94 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Requested | 2. Concept | Delay reason shown here | 2025-06-30 17:00
Requested | 0% | Project 83 | Performance Test suite Migration | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-08-28 17:00 | 2025-08-28 17:00 | 0 | 0%
Requested | 0% | Project 83 | SIT Start | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-08-01 17:00 | 2025-08-01 17:00 | 0 | 0%
Requested | 0% | Project 83 | SIT End | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2025-12-19 17:00 | 2025-12-19 17:00 | 0 | 0%
Requested | 0% | Project 83 | UAT End | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-03-06 17:00 | 2026-03-06 17:00 | 0 | 0%
Requested | 0% | Project 83 | UAT Start | Deliverable | Unassigned | Requested | 3. Evaluate | Delay reason shown here | 2026-01-12 17:00 | 2026-01-12 17:00 | 0 | 0%
Open/Active | <-25% | Project 46 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-12-24 17:00 | 2024-03-01 17:00 | -452 | -26.39%
Open/Active | -5% to 0% | Project 151 | CIS Applications Migration Build & Test Complete | Governance | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-01 17:00 | 2025-03-31 17:00 | -20 | -1.235%
Open/Active | 0% | Project 151 | CIS Applications Mig'n Implementation & GO LIVE | Governance | Go-Live | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-19 17:00 | 2025-05-19 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | PROJECT CLOSED (GATE 3): Stage 1 | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2027-03-05 17:00 | 2027-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Implement Archiving Solution | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-12-24 08:00 | 2026-12-24 08:00 | 0 | 0%
Open/Active | 0% | Project 165 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 5. Build & Test | Delay reason shown here | 2026-08-31 17:00 | 2026-08-31 17:00 | 0 | 0%
Open/Active | 0% | Project 123 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-07-01 17:00 | 2025-07-01 17:00 | 0 | 0%
Open/Active | 0% | Project 123 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-07-02 17:00 | 2025-07-02 17:00 | 0 | 0%
Open/Active | 0% | Project 123 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-07-02 17:00 | 2025-07-02 17:00 | 0 | 0%
Open/Active | -5% to 0% | Project 123 | ANALYSIS & DESIGN PHASE 3 COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-27 17:00 | 2025-05-19 17:00 | -6 | -1.02%
Open/Active | 0% | Project 123 | BUILD & TEST PHASE 3 COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-18 17:00 | 2025-06-18 17:00 | 0 | 0%
Open/Active | 0% | Project 123 | IMPLEMENT PHASE 3 COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-01 17:00 | 2025-07-01 17:00 | 0 | 0%
Open/Active | 0% | Project 121 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 | 0%
Open/Active | 0% | Project 121 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 | 0%
Open/Active | 0% | Project 121 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
Open/Active | 0% | Project 121 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
Open/Active | N/A | Project 46 | GR5.07 Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-09-01 17:00
Open/Active | N/A | Project 46 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-09-01 17:00
Open/Active | N/A | Project 46 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-09-19 17:00
Open/Active | N/A | Project 46 | 5.03 Release Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-09-12 17:00
Open/Active | N/A | Project 46 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-09-19 17:00
Open/Active | N/A | Project 46 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-09-01 17:00
Open/Active | N/A | Project 46 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-09-22 17:00
Open/Active | N/A | Project 46 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-09-30 08:00
Open/Active | N/A | Project 46 | GR6.07 Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-10-01 17:00
Open/Active | N/A | Project 46 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-11-03 17:00
Open/Active | N/A | Project 46 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-11-14 17:00
Open/Active | N/A | Project 46 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-12-01 17:00
Open/Active | N/A | Project 46 | HYB6.04 Release Retrospective Complete | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-11-03 17:00
Open/Active | N/A | Project 46 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-11-28 17:00
Open/Active | N/A | Project 46 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-12-05 17:00
Open/Active | N/A | Project 46 | BUSINESS GO LIVE (R4 Dates to be Built in) | Deliverable | Go-Live | Open/Active | 6. Implement | Delay reason shown here | 2025-12-24 08:00
Open/Active | N/A | Project 46 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-12-24 08:00
Open/Active | N/A | Project 46 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-12-24 08:00
Open/Active | N/A | Project 46 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-12-24 08:00
Open/Active | N/A | Project 46 | 7.03 Closure Checklist & Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-12-24 08:00
Open/Active | 0% | Project 132 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2027-02-10 17:00 | 2027-02-10 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2027-01-13 17:00 | 2027-01-13 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2027-03-03 17:00 | 2027-03-03 17:00 | 0 | 0%
Open/Active | -5% to 0% | Project 132 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-15 17:00 | 2025-02-26 17:00 | -53 | -1.994%
Open/Active | 0% | Project 137 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | Delay reason shown here | 2027-02-05 17:00 | 2027-02-05 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | Delay reason shown here | 2027-02-12 17:00 | 2027-02-12 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | Delay reason shown here | 2027-02-19 17:00 | 2027-02-19 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 4. Analyse & Design | Delay reason shown here | 2027-02-26 17:00 | 2027-02-26 17:00 | 0 | 0%
Open/Active | -25% to -10% | Project 157 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-07-31 17:00 | 2025-02-14 17:00 | -115 | -16.48%
Open/Active | <-25% | Project 157 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-10-31 17:00 | 2025-02-21 17:00 | -175 | -25.07%
Open/Active | <-25% | Project 157 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-28 17:00 | 2025-02-13 17:00 | -201 | -28.8%
Open/Active | <-25% | Project 157 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-14 17:00 | 2025-02-14 17:00 | -190 | -27.22%
Open/Active | -10% to -5% | Project 157 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-09 17:00 | 2025-02-28 17:00 | -47 | -6.734%
Open/Active | 0% | Project 157 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-10-13 17:00 | 2025-10-13 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-03 17:00 | 2025-11-03 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-21 17:00 | 2025-11-21 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-10-13 17:00 | 2025-10-13 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-10-01 17:00 | 2025-10-01 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-03 17:00 | 2025-11-03 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-14 17:00 | 2025-11-14 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-12 17:00 | 2025-11-12 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-28 17:00 | 2025-11-28 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | GO LIVE | Deliverable | Go-Live | Open/Active | 4. Analyse & Design | Delay reason shown here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0%
Open/Active | 0% | Project 157 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0%
Open/Active | 0% | Project 165 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 5. Build & Test | Delay reason shown here | 2026-08-14 17:00 | 2026-08-14 17:00 | 0 | 0%
Open/Active | 0% | Project 165 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 5. Build & Test | Delay reason shown here | 2026-08-21 17:00 | 2026-08-21 17:00 | 0 | 0%
Open/Active | 0% | Project 165 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 5. Build & Test | Delay reason shown here | 2026-08-28 17:00 | 2026-08-28 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 5. Build & Test | Delay reason shown here | 2027-06-18 17:00 | 2027-06-18 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 5. Build & Test | Delay reason shown here | 2027-06-11 17:00 | 2027-06-11 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 5. Build & Test | Delay reason shown here | 2027-06-25 17:00 | 2027-06-25 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 5. Build & Test | Delay reason shown here | 2027-06-30 17:00 | 2027-06-30 17:00 | 0 | 0%
Open/Active | -25% to -10% | Project 108 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-16 17:00 | 2025-01-31 08:00 | -73 | -23.4%
Open/Active | <-25% | Project 108 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-02-14 08:00 | -93 | -29.81%
Open/Active | <-25% | Project 108 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-01-31 08:00 | -83 | -26.6%
Open/Active | <-25% | Project 108 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-02-14 08:00 | -93 | -29.81%
Open/Active | -5% to 0% | Project 108 | MARITIME S/W OP INCIDENT MGT VENDOR SELECTED | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-11 17:00 | 2025-07-11 08:00 | -1 | -0.3205%
Open/Active | 0% | Project 144 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-20 17:00 | 2025-06-20 17:00 | 0 | 0%
Open/Active | 0% | Project 144 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | -10% to -5% | Project 144 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-09 17:00 | 2025-02-28 17:00 | -47 | -9.289%
Open/Active | -5% to 0% | Project 59 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-23 17:00 | 2025-06-06 17:00 | -10 | -3.731%
Open/Active | -5% to 0% | Project 59 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-23 17:00 | 2025-06-20 17:00 | -1 | -0.3731%
Open/Active | 0% | Project 59 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-27 17:00 | 2025-06-27 17:00 | 0 | 0%
Open/Active | 0% | Project 59 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 3.14 Project Management Plan Sign Off (use SoW) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 3.00 EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 7.00 PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 147 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-15 08:00 | 2025-07-15 08:00 | 0 | 0%
Open/Active | 0% | Project 147 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-15 08:00 | 2025-07-15 08:00 | 0 | 0%
Open/Active | 0% | Project 147 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-16 08:00 | 2025-07-16 08:00 | 0 | 0%
Open/Active | 0% | Project 147 | 7.00 PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-16 08:00 | 2025-07-16 08:00 | 0 | 0%
Open/Active | -25% to -10% | Project 147 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2024-12-20 17:00 | -101 | -22.91%
Open/Active | -25% to -10% | Project 147 | 3.00 EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2024-12-20 17:00 | -101 | -22.91%
Open/Active | -5% to 0% | Project 143 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-15 17:00 | 2025-04-30 17:00 | -11 | -3.819%
Open/Active | -10% to -5% | Project 143 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-30 17:00 | -22 | -7.639%
Open/Active | -10% to -5% | Project 143 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-30 17:00 | -22 | -7.639%
Open/Active | 0% | Project 143 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-08 17:00 | 2025-10-08 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-08 17:00 | 2025-10-08 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-10 17:00 | 2025-10-10 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-08 17:00 | 2025-10-08 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-10 17:00 | 2025-10-10 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | TRANCHE 3 GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-08 17:00 | 2025-10-08 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-17 17:00 | 2025-10-17 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
Open/Active | -25% to -10% | Project 34 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-01 17:00 | 2024-12-20 17:00 | -80 | -24.77%
Open/Active | -10% to -5% | Project 34 | 4.01 Sol'n Architecture Design (SAD) Sign Off LLID | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-05 17:00 | 2025-04-04 17:00 | -18 | -5.573%
Open/Active | -10% to -5% | Project 34 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-05 17:00 | 2025-04-04 17:00 | -18 | -5.573%
Open/Active | -10% to -5% | Project 34 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-16 17:00 | 2025-04-04 17:00 | -27 | -8.359%
Open/Active | 0% | Project 34 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-08 17:00 | 2025-08-08 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-15 17:00 | 2025-08-15 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-08 17:00 | 2025-08-08 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-28 17:00 | 2025-07-28 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-14 17:00 | 2025-08-14 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | GO LIVE Production | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-15 17:00 | 2025-08-15 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-18 17:00 | 2025-08-18 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0%
Open/Active | -25% to -10% | Project 59 | 4.11 Security Risk Assessment (SRA) Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -15.67%
Open/Active | -25% to -10% | Project 59 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-02-25 17:00 | -45 | -16.79%
Open/Active | -25% to -10% | Project 59 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -15.67%
Open/Active | -5% to 0% | Project 59 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-16 17:00 | 2025-04-29 17:00 | -13 | -4.851%
Open/Active | -5% to 0% | Project 59 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-09 17:00 | 2025-04-17 17:00 | -13 | -4.851%
Open/Active | -5% to 0% | Project 59 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-09 17:00 | 2025-04-17 17:00 | -13 | -4.851%
Open/Active | -5% to 0% | Project 59 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-09 17:00 | 2025-04-28 17:00 | -9 | -3.358%
Open/Active | -10% to -5% | Project 59 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-29 17:00 | -23 | -8.582%
Open/Active | -10% to -5% | Project 59 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-30 17:00 | -22 | -8.209%
Open/Active | -10% to -5% | Project 59 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-13 17:00 | 2025-05-12 17:00 | -23 | -8.582%
Open/Active | -10% to -5% | Project 59 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-13 17:00 | 2025-05-09 17:00 | -24 | -8.955%
Open/Active | -10% to -5% | Project 59 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-13 17:00 | 2025-05-16 17:00 | -19 | -7.09%
Open/Active | -10% to -5% | Project 59 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-06 17:00 | 2025-05-05 17:00 | -24 | -8.955%
Open/Active | -10% to -5% | Project 59 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-13 17:00 | 2025-05-20 17:00 | -17 | -6.343%
Open/Active | -10% to -5% | Project 59 | GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-20 17:00 | 2025-05-21 17:00 | -21 | -7.836%
Open/Active | -10% to -5% | Project 59 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-20 17:00 | 2025-05-30 17:00 | -14 | -5.224%
Open/Active | <-25% | Project 167 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-01 08:00 | 2024-11-22 17:00 | -99 | -29.04%
Open/Active | -10% to -5% | Project 167 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-24 17:00 | -25 | -7.334%
Open/Active | -10% to -5% | Project 167 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-30 17:00 | -22 | -6.454%
Open/Active | -10% to -5% | Project 167 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-17 17:00 | -28 | -8.214%
Open/Active | -10% to -5% | Project 167 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-17 17:00 | -28 | -8.214%
Open/Active | -10% to -5% | Project 167 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-11 17:00 | -32 | -9.388%
Open/Active | -25% to -10% | Project 167 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-03-14 17:00 | -52 | -15.25%
Open/Active | -10% to -5% | Project 167 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-29 17:00 | -23 | -6.747%
Open/Active | -10% to -5% | Project 167 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-28 17:00 | -24 | -7.041%
Open/Active | -10% to -5% | Project 167 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-29 17:00 | -23 | -6.747%
Open/Active | -10% to -5% | Project 167 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-30 17:00 | -22 | -6.454%
Open/Active | -25% to -10% | Project 167 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 17:00 | 2025-03-28 17:00 | -85 | -24.94%
Open/Active | -25% to -10% | Project 167 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 17:00 | 2025-03-28 17:00 | -85 | -24.94%
Open/Active | -25% to -10% | Project 167 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 17:00 | 2025-04-23 17:00 | -69 | -20.24%
Open/Active | -25% to -10% | Project 167 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-05-09 17:00 | -79 | -23.18%
Open/Active | -25% to -10% | Project 167 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-05-23 17:00 | -69 | -20.24%
Open/Active | -25% to -10% | Project 167 | GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-05-30 17:00 | -64 | -18.78%
Open/Active | -25% to -10% | Project 167 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-06-06 17:00 | -59 | -17.31%
Open/Active | -25% to -10% | Project 167 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-06-13 17:00 | -77 | -22.59%
Open/Active | -25% to -10% | Project 167 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-06-25 17:00 | -69 | -20.24%
Open/Active | -25% to -10% | Project 167 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-06-30 08:00 | -67 | -19.66%
Open/Active | -5% to 0% | Project 142 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-05-01 17:00 | 2025-04-17 17:00 | -7 | -4.545%
Open/Active | -5% to 0% | Project 142 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-05-01 17:00 | 2025-04-17 17:00 | -7 | -4.545%
Open/Active | -5% to 0% | Project 142 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-05-01 17:00 | 2025-04-17 17:00 | -7 | -4.545%
Open/Active | -25% to -10% | Project 108 | RFP DOCUMENTATION COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-04-04 08:00 | -38 | -12.18%
Open/Active | -10% to -5% | Project 108 | CLOSED RFP LAUNCHED (w/ 10 Selected Vendors) | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-13 17:00 | 2025-05-02 08:00 | -30 | -9.615%
Open/Active | -5% to 0% | Project 108 | PROPOSAL REVIEW COMPLETE | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-13 17:00 | 2025-06-13 08:00 | -1 | -0.3205%
Open/Active | 0% | Project 92 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | GO LIVE Oracle Solaris: DOCUMENTUM | Deliverable | Go-Live | Open/Active | 6. Implement | Delay reason shown here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | GO LIVE Oracle Solaris: RailTable Suite of Apps | Deliverable | Go-Live | Open/Active | 6. Implement | Delay reason shown here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | DEP OUT - GO LIVE Oracle Solaris: TPS | Deliverable | Go-Live | Open/Active | 6. Implement | Delay reason shown here | 2025-06-02 17:00 | 2025-06-02 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | BUILD & TEST PHASE COMPLETE (DOCUMENTUM) | Governance | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | 5.00 ICT Release Board Approval (CAB) for TPS | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-20 17:00 | 2025-06-20 17:00 | 0 | 0%
Open/Active | 0% | Project 139 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-02 17:00 | 2025-05-02 17:00 | 0 | 0%
Open/Active | 0% | Project 139 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-02 17:00 | 2025-05-02 17:00 | 0 | 0%
Open/Active | 0% | Project 139 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-02 17:00 | 2025-05-02 17:00 | 0 | 0%
Open/Active | 0% | Project 139 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-02 17:00 | 2025-05-02 17:00 | 0 | 0%
Open/Active | 0% | Project 139 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-23 17:00 | 2025-05-23 17:00 | 0 | 0%
Open/Active | 0% to 5% | Project 139 | SQUIZ - SMS GO LIVE | Deliverable | Go-Live | Open/Active | 6. Implement | Delay reason shown here | 2025-05-16 17:00 | 2025-05-30 17:00 | 10 | 4.525%
Open/Active | 0% | Project 139 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 139 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-06-06 17:00 | 2025-06-06 17:00 | 0 | 0%
Open/Active | 0% | Project 139 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-06-13 17:00 | 2025-06-13 17:00 | 0 | 0%
Open/Active | 0% | Project 139 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-06-20 17:00 | 2025-06-20 17:00 | 0 | 0%
Open/Active | 0% | Project 139 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-06-20 17:00 | 2025-06-20 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.01 Sol'n Architecture Design (SAD) Sign Off 1.3 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-01-13 17:00 | 2026-01-13 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-01-13 17:00 | 2026-01-13 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-01-13 17:00 | 2026-01-13 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.09 Test Plan Sign Off 1.3 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | -10% to -5% | Project 147 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-01 17:00 | 2025-02-28 17:00 | -41 | -9.3%
Open/Active | -10% to -5% | Project 147 | 4.00 ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-01 17:00 | 2025-02-28 17:00 | -41 | -9.3%
Open/Active | 0% | Project 147 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 147 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-14 08:00 | 2025-05-14 08:00 | 0 | 0%
Open/Active | 0% | Project 147 | 5.00 BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-16 08:00 | 2025-05-16 08:00 | 0 | 0%
Open/Active | 0% | Project 147 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-14 08:00 | 2025-05-14 08:00 | 0 | 0%
Open/Active | 0% | Project 147 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-16 08:00 | 2025-05-16 08:00 | 0 | 0%
Open/Active | -5% to 0% | Project 147 | 6.00 GO LIVE PHASE 1 | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-20 17:00 | 2025-05-27 08:00 | -18 | -4.083%
Open/Active | -5% to 0% | Project 147 | 6.00 IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-23 17:00 | 2025-05-28 17:00 | -17 | -3.856%
Open/Active | 0% | Project 144 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-05-02 17:00 | 0 | 0%
Open/Active | 0% | Project 144 | GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-06 17:00 | 2025-05-06 17:00 | 0 | 0%
Open/Active | 0% | Project 144 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-07 17:00 | 2025-05-07 17:00 | 0 | 0%
Open/Active | -5% to 0% | Project 165 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-08-01 17:00 | 2025-04-02 08:00 | -84 | -3.912%
Open/Active | -5% to 0% | Project 165 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-08-12 17:00 | 2025-04-11 08:00 | -84 | -3.912%
Open/Active | -5% to 0% | Project 165 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-08-29 17:00 | 2025-08-15 08:00 | -11 | -0.5123%
Open/Active | -5% to 0% | Project 165 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-10-31 17:00 | 2025-08-01 08:00 | -65 | -3.027%
Open/Active | -5% to 0% | Project 165 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-10-13 17:00 | 2025-08-08 08:00 | -46 | -2.143%
Open/Active | -5% to 0% | Project 165 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-10-31 17:00 | 2025-08-15 08:00 | -55 | -2.562%
Open/Active | -5% to 0% | Project 165 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-10-31 17:00 | 2025-08-22 08:00 | -50 | -2.329%
Open/Active | -5% to 0% | Project 165 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-10-31 17:00 | 2025-08-29 17:00 | -44 | -2.049%
Open/Active | -5% to 0% | Project 165 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-08-25 17:00 | 2025-08-25 08:00 | -1 | -0.04658%
Open/Active | -5% to 0% | Project 165 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-08-27 17:00 | 2025-08-27 08:00 | -1 | -0.04658%
Open/Active | -5% to 0% | Project 165 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-09-12 17:00 | 2025-09-12 08:00 | -1 | -0.04658%
Open/Active | -5% to 0% | Project 165 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-09-19 17:00 | 2025-09-19 08:00 | -1 | -0.04658%
Open/Active | -5% to 0% | Project 165 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-09-24 17:00 | 2025-09-24 08:00 | -1 | -0.04658%
Open/Active | -5% to 0% | Project 165 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-09-25 17:00 | 2025-09-25 08:00 | -1 | -0.04658%
Open/Active | -5% to 0% | Project 165 | GO LIVE TCOPS PHASE 1 | Deliverable | Go-Live | Open/Active | 5. Build & Test | Delay reason shown here | 2025-11-14 17:00 | 2025-09-29 08:00 | -34 | -1.584%
Open/Active | -5% to 0% | Project 165 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-11-17 17:00 | 2025-09-30 08:00 | -34 | -1.584%
Open/Active | -25% to -10% | Project 154 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -12.65%
Open/Active | -10% to -5% | Project 154 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-03-31 08:00 | -22 | -6.627%
Open/Active | -10% to -5% | Project 154 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-03-31 08:00 | -22 | -6.627%
Open/Active | -25% to -10% | Project 154 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-02-21 17:00 | -47 | -14.16%
Open/Active | -5% to 0% | Project 154 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -3.313%
Open/Active | -5% to 0% | Project 154 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-04-22 08:00 | -8 | -2.41%
Open/Active | -5% to 0% | Project 154 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-04-14 08:00 | -12 | -3.614%
Open/Active | -10% to -5% | Project 154 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-03-28 08:00 | -23 | -6.928%
Open/Active | -25% to -10% | Project 154 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -12.65%
Open/Active | -25% to -10% | Project 154 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -12.65%
Open/Active | -10% to -5% | Project 154 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-03-17 08:00 | -32 | -9.639%
Open/Active | -10% to -5% | Project 154 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-03-31 08:00 | -22 | -6.627%
Open/Active | -10% to -5% | Project 154 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-03-17 08:00 | -32 | -9.639%
Open/Active | -5% to 0% | Project 154 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-04-30 17:00 | -2 | -0.6024%
Open/Active | 0% | Project 154 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-13 08:00 | 2025-06-13 08:00 | 0 | 0%
Open/Active | -5% to 0% | Project 154 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -3.313%
Open/Active | 0% | Project 154 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-13 08:00 | 2025-06-13 08:00 | 0 | 0%
Open/Active | -5% to 0% | Project 154 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -3.313%
Open/Active | 0% | Project 154 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-02 17:00 | 2025-06-02 17:00 | 0 | 0%
Open/Active | 0% | Project 154 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-13 17:00 | 2025-06-13 17:00 | 0 | 0%
Open/Active | -5% to 0% | Project 154 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-04-30 17:00 | -2 | -0.6024%
Open/Active | -5% to 0% | Project 154 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -3.313%
Open/Active | -5% to 0% | Project 154 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -3.313%
Open/Active | 0% | Project 154 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-13 08:00 | 2025-06-13 08:00 | 0 | 0%
Open/Active | 0% | Project 154 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-12 17:00 | 2025-05-12 17:00 | 0 | 0%
Open/Active | 0% | Project 154 | GO LIVE: First 8-10 Vessels/Vehicles Ready | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-17 08:00 | 2025-06-17 08:00 | 0 | 0%
Open/Active | 0% | Project 154 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-18 08:00 | 2025-06-18 08:00 | 0 | 0%
Open/Active | 0% | Project 154 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 08:00 | 2025-06-30 08:00 | 0 | 0%
Open/Active | 0% | Project 154 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-01 08:00 | 2025-08-01 08:00 | 0 | 0%
Open/Active | 0% | Project 154 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-01 08:00 | 2025-08-01 08:00 | 0 | 0%
Open/Active | -5% to 0% | Project 154 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -3.313%
Open/Active | -5% to 0% | Project 154 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -3.313%
Open/Active | 0% | Project 98 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-06 17:00 | 2025-06-06 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 5.00 BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-06 17:00 | 2025-06-06 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 98 | 6.00 IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 123 | GO LIVE - OT-IT Ph3 | Deliverable | Go-Live | Open/Active | 6. Implement | Delay reason shown here | 2025-06-25 17:00 | 2025-06-25 17:00 | 0 | 0%
Open/Active | 0% | Project 123 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-18 17:00 | 2025-06-18 17:00 | 0 | 0%
Open/Active | -5% to 0% | Project 123 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-27 17:00 | 2025-04-17 17:00 | -25 | -4.252%
Open/Active | -5% to 0% | Project 151 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-01 17:00 | 2025-03-31 17:00 | -20 | -1.235%
Open/Active | -5% to 0% | Project 151 | 5.00 Service Continuity Runbook Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-01 17:00 | 2025-03-31 17:00 | -20 | -1.235%
Open/Active | 0% | Project 151 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | 6.02 Implementation Plan Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | 6.00 Application Handover Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | 5.00 Service Continuity Runbook Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-30 08:00 | 2025-05-30 08:00 | 0 | 0%
Open/Active | 0% | Project 151 | 6.02 Implementation Plan Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-30 08:00 | 2025-05-30 08:00 | 0 | 0%
Open/Active | 0% | Project 151 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-12 17:00 | 2025-06-12 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | 6.00 Application Handover Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-13 17:00 | 2025-06-13 17:00 | 0 | 0%
Open/Active | 0% | Project 137 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 137 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 137 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 137 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 5.01 Test Cases Sign Off 1.3 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | 5.02 Test Summary Report/Cert Sign Off 1.3 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0%
Open/Active | 0% | Project 83 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 83 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 83 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 83 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 83 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-06 17:00 | 2025-06-06 17:00 | 0 | 0%
Open/Active | 0% | Project 83 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 83 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 83 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 83 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | <-25% | Project 59 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-01 17:00 | 2024-12-04 17:00 | -92 | -34.33%
Open/Active | <-25% | Project 59 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-01 17:00 | 2024-12-04 17:00 | -92 | -34.33%
Open/Active | 0% to 5% | Project 123 | OT-IT PH3 End of Build | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-23 17:00 | 2025-06-04 17:00 | 8 | 1.361%
Open/Active | -5% to 0% | Project 151 | 5.06 Release Requested - Blocksheets | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-02 17:00 | 2025-02-28 17:00 | -63 | -3.891%
Open/Active | -5% to 0% | Project 151 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-06 17:00 | 2025-02-28 17:00 | -67 | -4.138%
Open/Active | -5% to 0% | Project 151 | 6.02 Implementation Plan Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-02 17:00 | 2025-03-31 17:00 | -42 | -2.594%
Open/Active | -5% to 0% | Project 151 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-20 17:00 | 2025-03-31 17:00 | -55 | -3.397%
Open/Active | -5% to 0% | Project 151 | BlockSheets GO LIVE | Deliverable | Go-Live | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-30 17:00 | 2025-04-07 17:00 | -56 | -3.459%
Open/Active | -5% to 0% | Project 151 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-30 17:00 | 2025-03-31 17:00 | -41 | -2.532%
Open/Active | -5% to 0% | Project 151 | 5.06 Release Requested - SSTS | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-02 17:00 | 2025-04-17 17:00 | -29 | -1.791%
Open/Active | -5% to 0% | Project 151 | 5.00 Service Continuity Runbook Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-30 17:00 | 2025-03-31 17:00 | -41 | -2.532%
Open/Active | -5% to 0% | Project 151 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-02 17:00 | 2025-03-31 17:00 | -42 | -2.594%
Open/Active | -5% to 0% | Project 151 | SSTS BUILD & TEST PHASE COMPLETE | Governance | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-30 17:00 | 2025-03-31 17:00 | -41 | -2.532%
Open/Active | -5% to 0% | Project 151 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-02 17:00 | 2025-04-29 17:00 | -24 | -1.482%
Open/Active | -5% to 0% | Project 151 | 6.02 Implementation Plan Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-02 17:00 | 2025-04-29 17:00 | -24 | -1.482%
Open/Active | -5% to 0% | Project 151 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-02 17:00 | 2025-04-29 17:00 | -24 | -1.482%
Open/Active | -5% to 0% | Project 151 | 6.00 Application Handover Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-02 17:00 | 2025-04-29 17:00 | -24 | -1.482%
Open/Active | -5% to 0% | Project 151 | SSTS GO LIVE | Deliverable | Go-Live | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-30 17:00 | 2025-04-30 17:00 | -42 | -2.594%
Open/Active | N/A | Project 120 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-30 17:00
Open/Active | -5% to 0% | Project 120 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-06 17:00 | 2025-04-30 17:00 | -27 | -3.557%
Open/Active | -5% to 0% | Project 120 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-30 17:00 | 2025-05-30 17:00 | -20 | -2.635%
Open/Active | -5% to 0% | Project 120 | GO LIVE (NSW BOSN) | Deliverable | Go-Live | Open/Active | 6. Implement | Delay reason shown here | 2025-07-31 17:00 | 2025-06-16 17:00 | -33 | -4.348%
Open/Active | -10% to -5% | Project 120 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-09-03 17:00 | 2025-06-30 17:00 | -47 | -6.192%
Open/Active | -10% to -5% | Project 120 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-09-03 17:00 | 2025-06-30 17:00 | -47 | -6.192%
Open/Active | -10% to -5% | Project 120 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-09-03 17:00 | 2025-06-30 17:00 | -47 | -6.192%
Open/Active | <-25% | Project 141 | 3.06 HL Business Requirements Document Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-16 17:00 | 2025-01-31 17:00 | -72 | -36.36%
Open/Active | <-25% | Project 141 | 3.11 Prelim Sol'n Options Roadmap Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-16 17:00 | 2025-01-31 17:00 | -72 | -36.36%
Open/Active | <-25% | Project 141 | 3.21 Final Business Case Approved (Light Touch) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-12 17:00 | 2025-01-31 17:00 | -90 | -45.45%
Open/Active | <-25% | Project 141 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-19 17:00 | 2025-01-31 17:00 | -95 | -47.98%
Open/Active | -5% to 0% | Project 72 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-07 17:00 | 2025-04-30 17:00 | -5 | -2.033%
Open/Active | 0% | Project 72 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-16 08:00 | 2025-06-16 08:00 | 0 | 0%
Open/Active | 0% | Project 72 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-16 08:00 | 2025-06-16 08:00 | 0 | 0%
Open/Active | 0% | Project 72 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-16 08:00 | 2025-06-16 08:00 | 0 | 0%
Open/Active | 0% | Project 72 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-16 08:00 | 2025-06-16 08:00 | 0 | 0%
Open/Active | 0% | Project 72 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-04 17:00 | 2025-07-04 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | GO LIVE - LEGACY SHAREPOINT MIGRATION (GOV DC) | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
Open/Active | 0% | Project 72 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
Open/Active | N/A | Project 110 | GO LIVE | Deliverable | Go-Live | Open/Active | 6. Implement | Delay reason shown here | 2025-04-30 17:00
Open/Active | N/A | Project 110 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-04-30 17:00
Open/Active | N/A | Project 110 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-05-07 17:00
Open/Active | N/A | Project 110 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-05-09 17:00
Open/Active | N/A | Project 110 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-05-14 17:00
Open/Active | N/A | Project 110 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-05-16 17:00
Open/Active | 0% | Project 123 | 6.03 Go Live Readiness Complete | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-23 17:00 | 2025-06-23 17:00 | 0 | 0%
Open/Active | 0% | Project 123 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-25 17:00 | 2025-06-25 17:00 | 0 | 0%
Open/Active | 0% | Project 123 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-24 17:00 | 2025-06-24 17:00 | 0 | 0%
Open/Active | 0% | Project 123 | 6.05 Service Design & Definition Complete (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-20 17:00 | 2025-06-20 17:00 | 0 | 0%
Open/Active | 0% | Project 123 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-23 17:00 | 2025-06-23 17:00 | 0 | 0%
Open/Active | 0% to 5% | Project 123 | OT-IT PH3 End of SIT | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-30 17:00 | 2025-06-18 17:00 | 12 | 2.041%
Open/Active | 0% to 5% | Project 123 | OT-IT PH3 End of UAT | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-06-06 17:00 | 2025-06-18 17:00 | 7 | 1.19%
Open/Active | 0% | Project 123 | HDI>>SAA Req't (Ph1 Jun'25, Ph2 Sep'25) | External | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-27 17:00 | 2025-05-27 17:00 | 0 | 0%
Open/Active | N/A | Project 169 | UAT Signed Off | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-05-05 08:00
Open/Active | N/A | Project 169 | Deploy into GSIT Prod completion/final signoff | Deliverable | Go-Live | Open/Active | 6. Implement | Delay reason shown here | 2025-05-30 08:00
Open/Active | 0% | Project 108 | VENDOR CONTRACT SIGNED (PHASE 2 END) | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-31 08:00 | 2025-07-31 08:00 | 0 | 0%
Open/Active | 0% | Project 121 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
Open/Active | 0% | Project 154 | Training Documentation Ready | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-13 08:00 | 2025-06-13 08:00 | 0 | 0%
Open/Active | -25% to -10% | Project 46 | TMS R4 Go-live (TBC) | Deliverable | Go-Live | Open/Active | 6. Implement | Delay reason shown here | 2025-12-24 17:00 | 2025-01-01 17:00 | -247 | -14.42%
Open/Active | -10% to -5% | Project 46 | TMS R4 UAT Interface & Testing Support Complete | Deliverable | Yes | Open/Active | 6. Implement | Delay reason shown here | 2025-09-30 17:00 | 2025-03-17 17:00 | -137 | -7.998%
Open/Active | 0% | Project 121 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 | 0%
Open/Active | 0% | Project 123 | PROJECT CLOSED (GATE 3) Phase 2 | Governance | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-07-02 17:00 | 2025-07-02 17:00 | 0 | 0%
Open/Active | 0% | Project 121 | Business GO LIVE | Deliverable | Go-Live | Open/Active | 6. Implement | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 121 | Technical Deployment | Deliverable | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 121 | IMPLEMENT PHASE COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 121 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-05 17:00 | 2025-05-05 17:00 | 0 | 0%
Open/Active | 0% | Project 92 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Gate 3 Approval | Open/Active | 6. Implement | Delay reason shown here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0%
Open/Active | 0% | Project 151 | TRIMS (VIZIRAIL) GO LIVE (CONFIRMED FY26) | Deliverable | Go-Live | Open/Active | 5. Build & Test | Delay reason shown here | 2026-06-30 17:00 | 2026-06-30 17:00 | 0 | 0%
Open/Active | 10% to 25% | Project 151 | FMCS GO LIVE - Minor Release targeting 31/7 | Deliverable | Go-Live | Open/Active | 5. Build & Test | Delay reason shown here | 2025-07-31 17:00 | 2026-06-30 17:00 | 221 | 13.65%
Open/Active | -5% to 0% | Project 132 | TPS.Plan SIT environment readiness | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-19 17:00 | 2025-04-14 17:00 | -22 | -0.8277%
Open/Active | 0% | Project 132 | TPS.Plan PROD&DR environment readiness | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-26 17:00 | 2025-06-26 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | TPS.Plan DEV03 environment readiness | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-17 17:00 | 2025-07-17 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Integration PSAD endorse by GSIT PDA | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-12-09 17:00 | 2025-12-09 17:00 | 0 | 0%
Open/Active | -5% to 0% | Project 132 | Contract execution | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-23 17:00 | 2025-03-31 17:00 | -36 | -1.354%
Open/Active | -5% to 0% | Project 132 | SOW for TPS.Plan installation and configuration | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-16 17:00 | 2025-04-30 17:00 | -12 | -0.4515%
Open/Active | -5% to 0% | Project 132 | SOW Review & Sign-Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-23 17:00 | 2025-05-07 17:00 | -12 | -0.4515%
Open/Active | 0% | Project 132 | Define Application Managed Support Services (AMSS) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-04 17:00 | 2025-06-04 17:00 | 0 | 0%
Open/Active | -5% to 0% | Project 132 | Service Design Workshops & Define Support Model | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-04-04 17:00 | -57 | -2.144%
Open/Active | -5% to 0% | Project 132 | Document the Support Process | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00 | 2025-06-04 17:00 | -17 | -0.6396%
Open/Active | 0% | Project 132 | Business & IT Stakeholder Socialization | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-30 17:00 | 2025-07-30 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Service Design Sign-Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-13 17:00 | 2025-08-13 17:00 | 0 | 0%
Open/Active | -5% to 0% | Project 132 | Test Plan & Test Cases readiness | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-19 17:00 | 2025-04-11 17:00 | -23 | -0.8653%
Open/Active | 0% | Project 132 | SIT Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-01 17:00 | 2025-07-01 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | UAT Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-14 17:00 | 2025-08-14 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | NFR Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-14 17:00 | 2025-08-14 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | End of warranty support | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-17 17:00 | 2025-09-17 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Go-Live Business Approval | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-15 17:00 | 2025-08-15 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Decommission TPAC Rail Suite (RailNet & RailTable) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-11-12 17:00 | 2026-11-12 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Decommission other GSIT Managed Apps Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-11-12 17:00 | 2026-11-12 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | PSAD (R1.3 entire solution) endorse by GSIT PDA | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-11-03 17:00 | 2025-11-03 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Integration & Application SAD sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-12-15 17:00 | 2025-12-15 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Interface control document sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-12-22 17:00 | 2025-12-22 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Integration solution build | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-04-22 17:00 | 2026-04-22 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Application solution build | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-04-23 17:00 | 2026-04-23 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Report SAD sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-01-13 17:00 | 2026-01-13 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Report solution build | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-03 17:00 | 2026-03-03 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Test Plan & Test Cases Readiness | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | SIT Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-06-12 17:00 | 2026-06-12 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | UAT Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-07-24 17:00 | 2026-07-24 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Regression Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-08-14 17:00 | 2026-08-14 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | NFR Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Update BAU Documents & Sign-Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-04 17:00 | 2026-03-04 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Go-Live Business Approval | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-02 17:00 | 2026-09-02 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | End of warranty support | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-30 17:00 | 2026-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | SOE design | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-20 17:00 | 2025-08-20 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Installation and SOE package rollout | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-11-13 17:00 | 2025-11-13 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Monitor and hardware procurement | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-17 17:00 | 2025-09-17 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | PSAD (R1.2 entire solution) endorse by GSIT PDA | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-25 17:00 | 2025-06-25 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Integration & Application SAD sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-13 17:00 | 2025-08-13 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Interface control document sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-30 17:00 | 2025-07-30 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Integration solution build | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-20 17:00 | 2025-08-20 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Application solution build | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-03 17:00 | 2025-09-03 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Report SAD sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-04 17:00 | 2025-08-04 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Report solution build | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-15 17:00 | 2025-09-15 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Test Plan & Test Cases readiness | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-11-05 17:00 | 2025-11-05 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | SIT Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-12-09 17:00 | 2025-12-09 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | UAT Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-04 17:00 | 2026-03-04 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | NFR Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-26 17:00 | 2026-03-26 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Update BAU documents and sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-11-20 17:00 | 2025-11-20 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | Go-Live Business Approval | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-31 17:00 | 2026-03-31 17:00 | 0 | 0%
Open/Active | 0% | Project 132 | End of warranty support | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-04-30 17:00 | 2026-04-30 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | InfoArchive Build Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-23 17:00 | 2025-05-23 17:00 | 0 | 0%
Open/Active | 0% | Project 34 | Data Migration Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | TRANCHE 1 GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-27 17:00 | 2025-06-27 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | TRANCHE 2 GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-07 17:00 | 2025-08-07 17:00 | 0 | 0%
Open/Active | N/A | Project 132 | 5.02 Test Summary Report/Cert Sign Off (R1.1) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-15 17:00
Open/Active | N/A | Project 132 | 5.02 Test Summary Report/Cert Sign Off (R1.2) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-03-31 17:00
Open/Active | N/A | Project 132 | 4.01 Sol'n Architecture Design (SAD) Sign Off 1.3 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-15 17:00
Open/Active | N/A | Project 132 | 4.01 Sol'n Architecture Design (SAD) Sign Off 1.2 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-04 17:00
Open/Active | N/A | Project 132 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-15 17:00
Open/Active | 0% | Project 57 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-13 17:00 | 2025-06-13 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-17 17:00 | 2025-06-17 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | End of Sprint 3 | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-06 17:00 | 2025-05-06 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | End of Sprint 5 | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-03 17:00 | 2025-06-03 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | End of Sprint 4 | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-20 17:00 | 2025-05-20 17:00 | 0 | 0%
Open/Active | 0% | Project 137 | Procurement Decision: How to Engage Vendor | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 137 | Statement of Work Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | N/A | Project 139 | SQUIZ - SECURE LIBRARY GO LIVE | Deliverable | Go-Live | Open/Active | 6. Implement | Delay reason shown here | 2025-05-02 17:00
Open/Active | N/A | Project 44 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-30 17:00
Open/Active | N/A | Project 44 | 7.02 PIR Sign Off (done for Phase 2 Only) | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-30 17:00
Open/Active | N/A | Project 44 | 7.03 Closure Memo Sign Off for Phase 3 | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-30 17:00
Open/Active | N/A | Project 44 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-30 17:00
Open/Active | N/A | Project 44 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-18 17:00
Open/Active | N/A | Project 44 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-18 17:00
Open/Active | N/A | Project 44 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-18 17:00
Open/Active | N/A | Project 44 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-18 17:00
Open/Active | N/A | Project 44 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-18 17:00
Open/Active | N/A | Project 44 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-18 17:00
Open/Active | N/A | Project 44 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-18 17:00
Open/Active | N/A | Project 44 | GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-18 17:00
Open/Active | N/A | Project 44 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2026-09-18 17:00
Open/Active | 0% | Project 143 | End of Sprint 5 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-13 17:00 | 2025-05-13 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | End of Sprint 6 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-27 17:00 | 2025-05-27 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | End of Sprint 7 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-10 17:00 | 2025-06-10 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | End of Sprint 8 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-24 17:00 | 2025-06-24 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | End of Sprint 9 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-08 17:00 | 2025-07-08 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | End of Sprint 10 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-22 17:00 | 2025-07-22 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | End of Sprint 11 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-05 17:00 | 2025-08-05 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | End of Sprint 12 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-19 17:00 | 2025-08-19 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | End of Sprint 13 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-02 17:00 | 2025-09-02 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | End of Sprint 14 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-16 17:00 | 2025-09-16 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | End of Sprint 15 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | End of Sprint 16 | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0%
Open/Active | N/A | Project 144 | Task Assigner Development Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00
Open/Active | N/A | Project 144 | eSCD Development Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-31 17:00
Open/Active | N/A | Project 144 | Task Assigner UAT Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-12-24 17:00
Open/Active | N/A | Project 144 | TCSS Prod Deployment | Deliverable | Go-Live | Open/Active | 3. Evaluate | Delay reason shown here | 2026-01-30 17:00
Open/Active | N/A | Project 144 | MyRoster Development Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00
Open/Active | N/A | Project 144 | CAS Development Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-31 17:00
Open/Active | 0% | Project 172 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 6.01 Training Docs & App H'over Checklist Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | GO LIVE | Deliverable | Go-Live | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 172 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | Sprint Plan | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-06 17:00 | 2025-05-06 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | Sprint Review | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-06 17:00 | 2025-05-06 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-06 17:00 | 2025-05-06 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | Sprint Plan | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-20 17:00 | 2025-05-20 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | Sprint Review | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-20 17:00 | 2025-05-20 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-05-20 17:00 | 2025-05-20 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | Sprint Plan | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-03 17:00 | 2025-06-03 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | Sprint Review | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-03 17:00 | 2025-06-03 17:00 | 0 | 0%
Open/Active | 0% | Project 57 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-06-03 17:00 | 2025-06-03 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-13 17:00 | 2025-05-13 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-13 17:00 | 2025-05-13 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-13 17:00 | 2025-05-13 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-27 17:00 | 2025-05-27 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-27 17:00 | 2025-05-27 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-27 17:00 | 2025-05-27 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-10 17:00 | 2025-06-10 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-10 17:00 | 2025-06-10 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-10 17:00 | 2025-06-10 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-24 17:00 | 2025-06-24 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-24 17:00 | 2025-06-24 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-24 17:00 | 2025-06-24 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-08 17:00 | 2025-07-08 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-08 17:00 | 2025-07-08 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-08 17:00 | 2025-07-08 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-22 17:00 | 2025-07-22 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-22 17:00 | 2025-07-22 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-07-22 17:00 | 2025-07-22 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-05 17:00 | 2025-08-05 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-05 17:00 | 2025-08-05 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-05 17:00 | 2025-08-05 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-19 17:00 | 2025-08-19 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-19 17:00 | 2025-08-19 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-08-19 17:00 | 2025-08-19 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-02 17:00 | 2025-09-02 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-02 17:00 | 2025-09-02 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-02 17:00 | 2025-09-02 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-16 17:00 | 2025-09-16 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-16 17:00 | 2025-09-16 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-16 17:00 | 2025-09-16 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0%
Open/Active | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0%
Open/Active | N/A | Project 5 | Production Deployment Phase 1 | Deliverable | Go-Live | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-08-18 08:00
Open/Active | N/A | Project 5 | Production Deployment Phase 2 | Deliverable | Go-Live | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-10 08:00
Open/Active | 0% | Project 72 | Site Locking - Banners - Server Stop - Decomm End | Deliverable | Unassigned | Open/Active | 3. Evaluate | Delay reason shown here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0%
Open/Active | N/A | Project 154 | RFP Finalisation | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-05-02 17:00
Open/Active | N/A | Project 95 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 95 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | Delay reason shown here | 2025-06-30 17:00
Open/Active | N/A | Project 5 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-10-31 17:00
Open/Active | N/A | Project 5 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-14 17:00
Open/Active | N/A | Project 5 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-14 17:00
Open/Active | N/A | Project 5 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-14 17:00
Open/Active | N/A | Project 5 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-11-28 17:00
Open/Active | N/A | Project 5 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-10-24 17:00
Open/Active | N/A | Project 5 | 5.02 Test Summary Ph2 Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-10-31 17:00
Open/Active | N/A | Project 5 | 5.01 System Integration Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-07-11 17:00
Open/Active | N/A | Project 5 | 5.02 Test Summary Ph1 Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | Delay reason shown here | 2025-07-11 17:00
Open/Active | 0% | Project 151 | Ph1 - GovDC uplift Migration Implementation | Governance | Go-Live | Open/Active | 5. Build & Test | Delay reason shown here | 2025-06-16 08:00 | 2025-06-16 08:00 | 0 | 0%
Open/Active | 0% | Project 151 | Ph1 - GovDC Migration Build and Test Complete | Governance | Unassigned | Open/Active | 5. Build & Test | Delay reason shown here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0%
On Hold | 0% | Project 151 | TCSS Mig'n Scratch & Design Complete | Governance | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-12-18 17:00 | 2024-12-18 17:00 | 0 | 0%
On Hold | 0% | Project 84 | ICFMS DB migration plan as a subset of BC | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2023-12-21 17:00 | 2023-12-21 17:00 | 0
On Hold | 0% | Project 84 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | On Hold | 7. Closure | Delay reason shown here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0
On Hold | -25% to -10% | Project 90 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-01-30 17:00 | 2024-08-30 17:00 | -97 | -11.8%
On Hold | -25% to -10% | Project 90 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-01-30 17:00 | 2024-08-30 17:00 | -97 | -11.8%
On Hold | -25% to -10% | Project 90 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-01-30 17:00 | 2024-08-30 17:00 | -97 | -11.8%
On Hold | -25% to -10% | Project 90 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-01-30 17:00 | 2024-08-30 17:00 | -97 | -11.8%
On Hold | -25% to -10% | Project 90 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -10% to -5% | Project 90 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-27 17:00 | 2024-10-21 17:00 | -82 | -9.976%
On Hold | -25% to -10% | Project 90 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -25% to -10% | Project 90 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-19 17:00 | 2024-09-27 17:00 | -91 | -11.07%
On Hold | -25% to -10% | Project 90 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -10% to -5% | Project 90 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-27 17:00 | 2024-10-21 17:00 | -82 | -9.976%
On Hold | -10% to -5% | Project 90 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-27 17:00 | 2024-10-21 17:00 | -82 | -9.976%
On Hold | -25% to -10% | Project 90 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -25% to -10% | Project 90 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -25% to -10% | Project 90 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -25% to -10% | Project 90 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -10% to -5% | Project 90 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-03-03 17:00 | 2024-11-04 17:00 | -74 | -9.002%
On Hold | -10% to -5% | Project 90 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-03-05 17:00 | 2024-11-11 17:00 | -71 | -8.637%
On Hold | -25% to -10% | Project 90 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -10% to -5% | Project 90 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-27 17:00 | 2024-10-21 17:00 | -82 | -9.976%
On Hold | -25% to -10% | Project 90 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -10% to -5% | Project 90 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-03-05 17:00 | 2024-11-11 17:00 | -71 | -8.637%
On Hold | -5% to 0% | Project 90 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-31 17:00 | 2025-02-18 17:00 | -29 | -3.528%
On Hold | -5% to 0% | Project 90 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-11 17:00 | 2025-02-18 17:00 | -15 | -1.825%
On Hold | -5% to 0% | Project 90 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-21 17:00 | 2025-02-18 17:00 | -23 | -2.798%
On Hold | -5% to 0% | Project 90 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-26 17:00 | 2025-02-18 17:00 | -26 | -3.163%
On Hold | -5% to 0% | Project 90 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-05 17:00 | 2025-02-18 17:00 | -11 | -1.338%
On Hold | -5% to 0% | Project 90 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-10 17:00 | 2025-02-18 17:00 | -14 | -1.703%
On Hold | -5% to 0% | Project 90 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-13 17:00 | 2025-02-18 17:00 | -17 | -2.068%
On Hold | -5% to 0% | Project 90 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-21 17:00 | 2025-02-18 17:00 | -23 | -2.798%
On Hold | -5% to 0% | Project 90 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-04-04 17:00 | 2025-02-18 17:00 | -33 | -4.015%
On Hold | 0% to 5% | Project 90 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-03-18 17:00 | 41 | 4.988%
On Hold | 5% to 10% | Project 90 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-02-03 17:00 | 2025-05-02 17:00 | 61 | 7.421%
On Hold | 5% to 10% | Project 90 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-05-09 17:00 | 76 | 9.246%
On Hold | 5% to 10% | Project 90 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-02-03 17:00 | 2025-05-09 17:00 | 66 | 8.029%
On Hold | 5% to 10% | Project 90 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-02-03 17:00 | 2025-05-09 17:00 | 66 | 8.029%
On Hold | 10% to 25% | Project 90 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-05-23 17:00 | 86 | 10.46%
On Hold | 5% to 10% | Project 90 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-02-03 17:00 | 2025-05-30 17:00 | 81 | 9.854%
On Hold | 10% to 25% | Project 90 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-06-06 17:00 | 96 | 11.68%
On Hold | 10% to 25% | Project 90 | GO LIVE | Deliverable | Go-Live | On Hold | 2. Concept | Delay reason shown here | 2025-02-03 17:00 | 2025-06-12 17:00 | 89 | 10.83%
On Hold | 10% to 25% | Project 90 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-06-12 17:00 | 99 | 12.04%
On Hold | 10% to 25% | Project 90 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | On Hold | 2. Concept | Delay reason shown here | 2025-01-24 17:00 | 2025-06-20 08:00 | 99 | 12.04%
On Hold | 10% to 25% | Project 90 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | On Hold | 2. Concept | Delay reason shown here | 2025-02-03 17:00 | 2025-06-27 08:00 | 99 | 12.04%
On Hold | 10% to 25% | Project 90 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | On Hold | 2. Concept | Delay reason shown here | 2025-02-10 17:00 | 2025-07-04 08:00 | 99 | 12.04%
On Hold | 0% to 5% | Project 90 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | On Hold | 2. Concept | Delay reason shown here | 2025-06-27 17:00 | 2025-07-11 08:00 | 9 | 1.095%
On Hold | -25% to -10% | Project 90 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-27 17:00 | -87 | -10.58%
On Hold | -25% to -10% | Project 90 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-20 17:00 | 2024-10-04 17:00 | -87 | -10.58%
On Hold | -25% to -10% | Project 90 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-27 17:00 | 2024-10-14 17:00 | -87 | -10.58%
On Hold | -25% to -10% | Project 90 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-03-06 17:00 | 2024-09-20 17:00 | -107 | -13.02%
On Hold | -5% to 0% | Project 90 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-05 17:00 | 2025-02-18 17:00 | -11 | -1.338%
On Hold | -5% to 0% | Project 90 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-07 17:00 | 2025-02-18 17:00 | -13 | -1.582%
On Hold | 0% to 5% | Project 90 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-02-25 17:00 | 26 | 3.163%
On Hold | 5% to 10% | Project 90 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-05-16 17:00 | 81 | 9.854%
On Hold | 5% to 10% | Project 90 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-05-16 17:00 | 81 | 9.854%
On Hold | 0% to 5% | Project 90 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-02-25 17:00 | 26 | 3.163%
On Hold | -5% to 0% | Project 90 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-18 17:00 | 2025-02-18 17:00 | -20 | -2.433%
On Hold | -5% to 0% | Project 90 | 4.04 HYB Definition of Done | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-25 17:00 | 2025-02-18 17:00 | -25 | -3.041%
On Hold | N/A | Project 54 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 08:00
On Hold | N/A | Project 54 | 5.04 Training Management Plan Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 08:00
On Hold | N/A | Project 54 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-01-20 17:00
On Hold | N/A | Project 54 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 08:00
On Hold | N/A | Project 54 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-12-06 17:00
On Hold | -25% to -10% | Project 90 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-01-30 17:00 | 2024-08-30 17:00 | -97 | -11.8%
On Hold | -25% to -10% | Project 90 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -5% to 0% | Project 90 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-05 17:00 | 2025-02-18 17:00 | -11 | -1.338%
On Hold | 5% to 10% | Project 90 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-05-09 17:00 | 76 | 9.246%
On Hold | N/A | Project 54 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-01-22 17:00
On Hold | N/A | Project 54 | 5.03 Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 17:00
On Hold | N/A | Project 54 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 17:00
On Hold | N/A | Project 54 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-11 08:00
On Hold | N/A | Project 54 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-11 08:00
On Hold | N/A | Project 54 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-11 08:00
On Hold | N/A | Project 54 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-11 17:00
On Hold | N/A | Project 54 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-04 08:00
On Hold | N/A | Project 54 | 3.08 Release Plan | Deliverable | Project Kickoff | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-04 08:00
On Hold | N/A | Project 54 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-09-13 17:00
On Hold | N/A | Project 54 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-04 08:00
On Hold | N/A | Project 54 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-09-13 17:00
On Hold | -5% to 0% | Project 90 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-03 17:00 | 2025-02-18 17:00 | -9 | -1.095%
On Hold | -5% to 0% | Project 90 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-06 17:00 | 2025-02-18 17:00 | -12 | -1.46%
On Hold | -5% to 0% | Project 90 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-04-04 17:00 | 2025-02-18 17:00 | -33 | -4.015%
On Hold | -5% to 0% | Project 90 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-04-01 17:00 | 2025-02-18 17:00 | -30 | -3.65%
On Hold | 10% to 25% | Project 90 | 6.01 Training Docs & App H'over Checklist Complete | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-06-06 17:00 | 96 | 11.68%
On Hold | N/A | Project 54 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-12-10 17:00
On Hold | 10% to 25% | Project 90 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-06-06 17:00 | 96 | 11.68%
On Hold | 5% to 10% | Project 90 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2025-05-09 17:00 | 76 | 9.246%
On Hold | -5% to 0% | Project 90 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-18 17:00 | 2025-02-18 17:00 | -20 | -2.433%
On Hold | N/A | Project 54 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-11 17:00
On Hold | 0% | Project 84 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | On Hold | 7. Closure | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0
On Hold | 0% | Project 84 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | On Hold | 7. Closure | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0
On Hold | 0% | Project 84 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | On Hold | 7. Closure | Delay reason shown here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0
On Hold | -25% to -10% | Project 90 | DEP IN: Inbound Dependency | External | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-17 17:00 | 2024-08-02 17:00 | -109 | -13.26%
On Hold | N/A | Project 54 | HDO>>EPS Program UAT Commencement 30/9 | External | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-09-30 17:00
On Hold | -25% to -10% | Project 90 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -25% to -10% | Project 90 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -25% to -10% | Project 90 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -11.19%
On Hold | -10% to -5% | Project 90 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-02-27 17:00 | 2024-10-21 17:00 | -82 | -9.976%
On Hold | -25% to -10% | Project 44 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | On Hold | 3. Evaluate | Delay reason shown here | 2026-08-28 17:00 | 2025-06-13 17:00 | -298 | -24.27%
On Hold | 0% | Project 144 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2024-10-17 17:00 | 2024-10-17 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0%
On Hold | -5% to 0% | Project 44 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-07 17:00 | 2024-11-04 17:00 | -58 | -4.723%
On Hold | -5% to 0% | Project 44 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-14 17:00 | 2024-12-02 17:00 | -43 | -3.502%
On Hold | -25% to -10% | Project 44 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2025-06-13 17:00 | 2024-11-22 17:00 | -130 | -10.59%
On Hold | -5% to 0% | Project 44 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-14 17:00 | 2024-11-21 17:00 | -50 | -4.072%
On Hold | N/A | Project 44 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here |  | 2024-11-04 17:00
On Hold | -25% to -10% | Project 44 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2025-06-13 17:00 | 2024-12-02 17:00 | -124 | -10.1%
On Hold | N/A | Project 44 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here |  | 2024-12-06 17:00
On Hold | -10% to -5% | Project 44 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2025-04-17 17:00 | 2024-12-02 17:00 | -87 | -7.085%
On Hold | N/A | Project 44 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here |  | 2024-12-06 17:00
On Hold | N/A | Project 44 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here |  | 2024-11-15 17:00
On Hold | -5% to 0% | Project 44 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-14 17:00 | 2024-11-15 17:00 | -54 | -4.397%
On Hold | N/A | Project 44 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here |  | 2024-11-04 17:00
On Hold | -25% to -10% | Project 44 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2025-11-28 17:00 | 2024-11-20 17:00 | -251 | -20.44%
On Hold | -5% to 0% | Project 44 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2024-11-29 17:00 | 2024-11-12 17:00 | -13 | -1.059%
On Hold | 0% to 5% | Project 44 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2024-09-27 17:00 | 2024-11-01 17:00 | 24 | 1.954%
On Hold | 0% to 5% | Project 44 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2024-09-27 17:00 | 2024-11-14 17:00 | 33 | 2.687%
On Hold | 0% | Project 44 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0%
On Hold | -5% to 0% | Project 44 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-07 17:00 | 2024-11-04 17:00 | -58 | -4.723%
On Hold | -5% to 0% | Project 44 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-07 17:00 | 2024-11-11 17:00 | -53 | -4.316%
On Hold | -5% to 0% | Project 44 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-07 17:00 | 2024-11-18 17:00 | -48 | -3.909%
On Hold | -25% to -10% | Project 44 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | On Hold | 3. Evaluate | Delay reason shown here | 2025-06-13 17:00 | 2024-11-25 17:00 | -129 | -10.5%
On Hold | 0% | Project 144 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-24 17:00 | 2025-02-24 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-25 17:00 | 2025-02-25 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-17 17:00 | 2025-02-17 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-04 17:00 | 2025-02-04 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-07 17:00 | 2025-02-07 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-06 17:00 | 2025-02-06 17:00 | 0 | 0%
On Hold | 0% | Project 144 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00 | 2024-12-13 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-01-07 17:00 | 2025-01-07 17:00 | 0 | 0%
On Hold | 0% | Project 144 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-01-10 17:00 | 2025-01-10 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0%
On Hold | 0% | Project 144 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2024-12-19 17:00 | 2024-12-19 17:00 | 0 | 0%
On Hold | -25% to -10% | Project 44 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-01-23 17:00 | -151 | -12.3%
On Hold | -25% to -10% | Project 44 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2024-12-20 17:00 | -165 | -13.44%
On Hold | N/A | Project 44 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here |  | 2025-01-10 17:00
On Hold | N/A | Project 44 | 4.04 HYB Definition of Done | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here |  | 2025-01-17 17:00
On Hold | -25% to -10% | Project 44 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-01-24 17:00 | -150 | -12.21%
On Hold | N/A | Project 44 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here |  | 2025-01-30 17:00
On Hold | -25% to -10% | Project 44 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2024-11-22 17:00 | -185 | -15.07%
On Hold | -25% to -10% | Project 44 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-01-20 17:00 | -154 | -12.54%
On Hold | -25% to -10% | Project 44 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2024-12-20 17:00 | -165 | -13.44%
On Hold | -10% to -5% | Project 44 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-04-24 17:00 | 2025-01-08 17:00 | -73 | -5.945%
On Hold | -25% to -10% | Project 44 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-08-29 17:00 | 2025-01-13 17:00 | -159 | -12.95%
On Hold | -25% to -10% | Project 44 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-11-28 17:00 | 2025-01-16 17:00 | -220 | -17.92%
On Hold | -25% to -10% | Project 44 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-12-12 17:00 | 2025-01-21 17:00 | -227 | -18.49%
On Hold | -25% to -10% | Project 44 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-12-12 17:00 | 2024-12-20 17:00 | -239 | -19.46%
On Hold | -25% to -10% | Project 44 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-12-12 17:00 | 2025-01-08 17:00 | -236 | -19.22%
On Hold | -25% to -10% | Project 44 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-09-26 17:00 | 2025-01-07 17:00 | -183 | -14.9%
On Hold | -25% to -10% | Project 44 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-12-12 17:00 | 2025-01-30 17:00 | -221 | -18%
On Hold | -25% to -10% | Project 44 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-09-05 17:00 | 2025-02-20 17:00 | -137 | -11.16%
On Hold | -25% to -10% | Project 44 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-11-28 17:00 | 2025-03-06 17:00 | -186 | -15.15%
On Hold | -25% to -10% | Project 44 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-11-28 17:00 | 2025-03-20 17:00 | -176 | -14.33%
On Hold | N/A | Project 44 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here |  | 2025-02-20 17:00
On Hold | -25% to -10% | Project 44 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-11-28 17:00 | 2025-04-03 17:00 | -166 | -13.52%
On Hold | -25% to -10% | Project 44 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-11-28 17:00 | 2025-04-03 17:00 | -166 | -13.52%
On Hold | -25% to -10% | Project 44 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-11-28 17:00 | 2025-04-03 17:00 | -166 | -13.52%
On Hold | -25% to -10% | Project 44 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-11-28 17:00 | 2025-04-03 17:00 | -166 | -13.52%
On Hold | -25% to -10% | Project 44 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-11-28 17:00 | 2025-04-03 17:00 | -166 | -13.52%
On Hold | <-25% | Project 44 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-08-28 17:00 | 2025-04-09 17:00 | -341 | -27.77%
On Hold | <-25% | Project 44 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-08-28 17:00 | 2025-04-15 17:00 | -337 | -27.44%
On Hold | <-25% | Project 44 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-08-28 17:00 | 2025-04-23 17:00 | -333 | -27.12%
On Hold | 0% | Project 44 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0%
On Hold | N/A | Project 44 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here |  | 2025-04-09 17:00
On Hold | <-25% | Project 44 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-08-28 17:00 | 2025-05-06 17:00 | -325 | -26.47%
On Hold | <-25% | Project 44 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-08-28 17:00 | 2025-05-12 17:00 | -321 | -26.14%
On Hold | <-25% | Project 44 | GO LIVE | Deliverable | Go-Live | On Hold | 3. Evaluate | Delay reason shown here | 2026-08-28 17:00 | 2025-05-16 17:00 | -317 | -25.81%
On Hold | <-25% | Project 44 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-08-28 17:00 | 2025-05-30 08:00 | -308 | -25.08%
On Hold | -5% to 0% | Project 44 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-07 17:00 | 2024-12-03 17:00 | -37 | -3.013%
On Hold | -5% to 0% | Project 44 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2025-02-07 17:00 | 2024-12-05 17:00 | -35 | -2.85%
On Hold | 0% | Project 151 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.03 HYB Team Charter (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.04 HYB Definition of Done | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-11-01 17:00 | 2024-11-01 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-11-13 17:00 | 2024-11-13 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.09 Test Plan Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.10 Traceability Matrix Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-12-10 17:00 | 2024-12-10 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-12-13 17:00 | 2024-12-13 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-12-18 17:00 | 2024-12-18 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-10 17:00 | 2024-10-10 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-11-25 17:00 | 2024-11-25 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.00 P80 Cost Estimate Ready | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-01-08 17:00 | 2025-01-08 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.01 Test Cases Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-01-15 17:00 | 2025-01-15 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-01-22 17:00 | 2025-01-22 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-01-08 17:00 | 2025-01-08 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.06 Release Requested (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.00 Service Continuity Runbook Complete | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-03-25 17:00 | 2025-03-25 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-04-04 17:00 | 2025-04-04 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.02 Implementation Plan Complete | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-04-08 17:00 | 2025-04-08 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-04-24 17:00 | 2025-04-24 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.04 HYB Release Retrospective Complete | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-03-21 17:00 | 2025-03-21 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-05-07 17:00 | 2025-05-07 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.00 Application Handover Checklist Complete | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-05-19 17:00 | 2025-05-19 17:00 | 0 | 0%
On Hold | 0% | Project 151 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-14 17:00 | 2024-10-14 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-16 17:00 | 2024-10-16 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-10 17:00 | 2024-10-10 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-21 17:00 | 2024-10-21 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-11-26 17:00 | 2024-11-26 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-11-27 17:00 | 2024-11-27 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-11-25 17:00 | 2024-11-25 17:00 | 0 | 0%
On Hold | 0% | Project 151 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2026-07-31 17:00 | 2026-07-31 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-05-07 17:00 | 2025-05-07 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-05-21 17:00 | 2025-05-21 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-04 17:00 | 2025-06-04 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-04 17:00 | 2025-06-04 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-19 17:00 | 2025-06-19 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-19 17:00 | 2025-06-19 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-19 17:00 | 2025-06-19 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-19 17:00 | 2025-06-19 17:00 | 0 | 0%
On Hold | 0% | Project 137 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-19 17:00 | 2025-06-19 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-25 17:00 | 2025-06-25 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-07-01 17:00 | 2025-07-01 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-07-07 17:00 | 2025-07-07 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-07-11 17:00 | 2025-07-11 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-25 17:00 | 2025-06-25 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-07-17 17:00 | 2025-07-17 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-07-23 17:00 | 2025-07-23 17:00 | 0 | 0%
On Hold | 0% | Project 137 | GO LIVE | Deliverable | Go-Live | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-07-29 17:00 | 2025-07-29 17:00 | 0 | 0%
On Hold | 0% | Project 137 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | On Hold | 4. Analyse & Design | Delay reason shown here | 2026-06-30 17:00 | 2026-06-30 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | On Hold | 4. Analyse & Design | Delay reason shown here | 2026-06-30 17:00 | 2026-06-30 17:00 | 0 | 0%
On Hold | 0% | Project 137 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | On Hold | 4. Analyse & Design | Delay reason shown here | 2026-06-30 17:00 | 2026-06-30 17:00 | 0 | 0%
On Hold | 0% | Project 137 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | On Hold | 4. Analyse & Design | Delay reason shown here | 2026-06-30 17:00 | 2026-06-30 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0%
On Hold | 0% | Project 132 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | Delay reason shown here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0%
On Hold | -25% to -10% | Project 54 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-01-17 17:00 | 2024-08-28 08:00 | -92 | -12.62%
On Hold | -25% to -10% | Project 54 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-12-11 17:00 | 2024-08-28 08:00 | -75 | -10.29%
On Hold | 0% | Project 84 | Procurement Strategy | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2022-12-23 | 2022-12-23 | 0
On Hold | 0% | Project 84 | Identify the upstream and down stream Apps | Unassigned | Yes | On Hold | 7. Closure | Delay reason shown here | 2023-09-28 17:00 | 2023-09-28 17:00 | 0
On Hold | <-25% | Project 54 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 17:00 | 2023-09-28 08:00 | -269 | -36.9%
On Hold | 0% | Project 84 | Investment Brief signed off | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2022-10-14 | 2022-10-14 | 0
On Hold | 0% | Project 84 | SAD Approved and Signed off | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2020-07-03 | 2020-07-03 | 0
On Hold | 0% | Project 151 | Ph2 (Cloud) Migration Discovery Complete | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
On Hold | 0% | Project 151 | Ph2 (Cloud) Migration Analysis Complete | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0%
On Hold | 0% | Project 151 | TCSS Mig'n Build & Test Complete | Governance | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0%
On Hold | 0% | Project 151 | TCSS Mig'n Implementation & Go Live | Deliverable | Go-Live | On Hold | 5. Build & Test | Delay reason shown here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0%
On Hold | 0% | Project 84 | PCR#1 Approval | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2023-08-31 | 2023-08-31 | 0
On Hold | 0% | Project 84 | Obtain Sign off to the options | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2020-07-06 | 2020-07-06 | 0
On Hold | 0% | Project 151 | Ph2 (Cloud) Migration Scratch & Design Complet | Governance | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0%
On Hold | 0% | Project 84 | Obtain Sign off on PACT | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2022-09-29 | 2022-09-29 | 0
On Hold | 0% | Project 151 | Ph2 (Cloud) Migration Build and Test Complete | Governance | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0%
On Hold | 0% | Project 151 | Ph2 (Cloud) Migration Implementation & go-live | Governance | Go-Live | On Hold | 5. Build & Test | Delay reason shown here | 2025-12-12 17:00 | 2025-12-12 17:00 | 0 | 0%
On Hold | 0% | Project 84 | Concept Phase Complete | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2022-09-30 | 2022-09-30 | 0
On Hold | -25% to -10% | Project 54 | Build Complete | Unassigned | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 08:00 | 2024-04-10 08:00 | -143 | -19.62%
On Hold | <-25% | Project 54 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-11 08:00 | 2023-10-06 08:00 | -249 | -34.16%
On Hold | -10% to -5% | Project 54 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-02-28 17:00 | 2024-11-07 08:00 | -71 | -9.739%
On Hold | <-25% | Project 54 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-11-29 17:00 | 2023-12-01 17:00 | -244 | -33.47%
On Hold | -10% to -5% | Project 54 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 08:00 | 2024-08-02 17:00 | -62 | -8.505%
On Hold | -25% to -10% | Project 54 | BUILD & TEST PHASE COMPLETE | Governance | Yes | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-12-20 17:00 | 2024-08-09 17:00 | -94 | -12.89%
On Hold | 0% | Project 84 | Detailed Design Document Sign-off | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2022-10-06 | 2022-10-06 | 0
On Hold | -25% to -10% | Project 54 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-12-09 17:00 | 2024-08-23 17:00 | -75 | -10.29%
On Hold | -10% to -5% | Project 54 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-01-31 17:00 | 2024-10-15 08:00 | -68 | -9.328%
On Hold | -10% to -5% | Project 54 | 7.03 Closure Checklist & Memo Sign Off | Deliverable | Gate 3 Approval | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-02-24 17:00 | 2024-10-31 17:00 | -71 | -9.739%
On Hold | 0% | Project 84 | Business Case for Phase 2 Complete | Deliverable | Project Kickoff | On Hold | 7. Closure | Delay reason shown here | 2024-06-21 17:00 | 2024-06-21 17:00 | 0
On Hold | 0% | Project 84 | Prod environment for HCL DX Platform | Unassigned | Yes | On Hold | 7. Closure | Delay reason shown here | 2024-05-13 08:00 | 2024-05-13 08:00 | 0
On Hold | 0% | Project 151 | Ramsys & Trackware Migrt. Build & Test Complete | Governance | Unassigned | On Hold | 5. Build & Test | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
On Hold | 0% | Project 151 | Ramsys & Trackware Migrt. Implementation & Go Live | Governance | Go-Live | On Hold | 5. Build & Test | Delay reason shown here | 2024-12-16 08:00 | 2024-12-16 08:00 | 0 | 0%
On Hold | 0% | Project 84 | Completion of Post-Production Support & Handover | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0
On Hold | 0% | Project 84 | WebSphere UI Migration Complete | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0
On Hold | -25% to -10% | Project 54 | GO LIVE | Deliverable | Go-Live | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-01-31 17:00 | 2024-08-30 17:00 | -98 | -13.44%
On Hold | <-25% | Project 54 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Yes | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 08:00 | 2023-09-27 17:00 | -268 | -36.76%
On Hold | <-25% | Project 54 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 08:00 | 2023-09-27 17:00 | -268 | -36.76%
On Hold | <-25% | Project 54 | Data Risk Assessment Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-11 08:00 | 2023-10-20 17:00 | -238 | -32.65%
On Hold | -25% to -10% | Project 54 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 08:00 | 2024-04-24 17:00 | -132 | -18.11%
On Hold | -25% to -10% | Project 54 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-02-14 17:00 | 2024-08-23 17:00 | -113 | -15.5%
On Hold | -25% to -10% | Project 54 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-02-21 17:00 | 2024-10-14 17:00 | -83 | -11.39%
On Hold | -10% to -5% | Project 54 | UAT Complete | Unassigned | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 08:00 | 2024-07-26 17:00 | -67 | -9.191%
On Hold | -25% to -10% | Project 54 | SIT Complete | Unassigned | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-31 08:00 | 2024-06-21 17:00 | -92 | -12.62%
On Hold | N/A | Project 90 | Release to Pre-Prod | Unassigned | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-03-11 17:00
On Hold | N/A | Project 90 | Release Scope Close | Unassigned | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-01-24 08:00
On Hold | N/A | Project 90 | Release to SIT | Unassigned | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-02-14 17:00
On Hold | N/A | Project 90 | UAT Exit Q-Gate | Unassigned | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-04-10 08:00
On Hold | N/A | Project 90 | Regression Exit Q-Gate | Unassigned | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-05-14 08:00
On Hold | N/A | Project 90 | Release Scope Close | Unassigned | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-07-28 08:00
On Hold | N/A | Project 90 | Release to SIT | Unassigned | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-08-21 08:00
On Hold | N/A | Project 90 | Release to Pre-Prod | Unassigned | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-09-12 08:00
On Hold | N/A | Project 90 | UAT Exit Q-Gate | Unassigned | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-10-14 08:00
On Hold | N/A | Project 90 | Regression Exit Q-Gate | Unassigned | Unassigned | On Hold | 2. Concept | Delay reason shown here | 2025-11-12 08:00
On Hold | 0% | Project 84 | Production Go-live | Unassigned | Go-Live | On Hold | 7. Closure | Delay reason shown here | 2024-05-20 08:00 | 2024-05-20 08:00 | 0
On Hold | <-25% | Project 54 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-09-13 17:00 | 2023-10-16 17:00 | -224 | -30.73%
On Hold | 0% | Project 84 | Architecting Cloud landing zones approvals for Pha | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2023-04-06 | 2023-04-06 | 0
On Hold | 0% | Project 84 | The HCL contact drafts for WPS upgrade & DB upgard | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2023-03-10 | 2023-03-10 | 0
On Hold | 0% | Project 84 | Resource re-alignment post Cloud PDA approvals | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2023-04-17 | 2023-04-17 | 0
On Hold | 0% | Project 84 | Re-baseline the project by excemption | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2023-05-12 | 2023-05-12 | 0
On Hold | 0% | Project 84 | Investment Brief Signed off | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2022-12-23 | 2022-12-23 | 0
On Hold | 0% | Project 84 | Concept SGR Completed | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2022-12-23 | 2022-12-23 | 0
On Hold | 0% | Project 84 | Project Management Plan | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2023-08-31 | 2023-08-31 | 0
On Hold | 0% | Project 84 | Evaluate SGR Completed | Unassigned | Unassigned | On Hold | 7. Closure | Delay reason shown here | 2023-08-31 | 2023-08-31 | 0
On Hold | <-25% | Project 54 | 4.14 Detailed Service design & Defn Onboard pk | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2024-10-11 08:00 | 2023-11-10 17:00 | -223 | -30.59%
On Hold | 0% | Project 84 | Migration approach document post application disco | Unassigned | Yes | On Hold | 7. Closure | Delay reason shown here | 2023-09-27 17:00 | 2023-09-27 17:00 | 0
On Hold | 0% | Project 84 | SIT environment for HCL DX Platform | Unassigned | Yes | On Hold | 7. Closure | Delay reason shown here | 2023-12-18 17:00 | 2023-12-18 17:00 | 0
On Hold | N/A | Project 57 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | N/A | Project 57 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | N/A | Project 57 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | N/A | Project 57 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | N/A | Project 57 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | N/A | Project 57 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | N/A | Project 57 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | N/A | Project 57 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | N/A | Project 57 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | N/A | Project 57 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | N/A | Project 57 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | N/A | Project 57 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | N/A | Project 57 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here
On Hold | 0% | Project 57 | End of Sprint 6 | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-17 17:00 | 2025-06-17 17:00 | 0 | 0%
On Hold | 0% | Project 57 | Sprint Plan | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-17 17:00 | 2025-06-17 17:00 | 0 | 0%
On Hold | 0% | Project 57 | Sprint Review | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-17 17:00 | 2025-06-17 17:00 | 0 | 0%
On Hold | 0% | Project 57 | Sprint Retrospective | Deliverable | Unassigned | On Hold | 4. Analyse & Design | Delay reason shown here | 2025-06-17 17:00 | 2025-06-17 17:00 | 0 | 0%
On Hold | N/A | Project 94 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | N/A | Project 94 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | Delay reason shown here | 2025-06-30 17:00
On Hold | 0% | Project 151 | Ph2 (Cloud) Migration Establishment | Deliverable | Yes | On Hold | 5. Build & Test | Delay reason shown here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Oracle Apex - GSU Migration Build and Test | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-02-19 17:00 | 2024-02-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Oracle Apex - GSU Migration Scratch and Design | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-02-16 17:00 | 2024-02-16 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Applications ITSI Dashboards - complete (AWS) | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-07-19 17:00 | 2024-07-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Applications ITSI Dashboards - complete (AZURE) | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-07-19 17:00 | 2024-07-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Implements across AWS & Azure Anycloud - complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-07-19 17:00 | 2024-07-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 120 | Procurement Documentation Complete | Unassigned | Yes | Assumed Completed | 6. Implement | Delay reason shown here | 2024-04-04 17:00 | 2024-04-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 91 | Project: Redgate Migration Complete | Deliverable | Go-Live | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-28 08:00 | 2024-03-28 08:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 91 | Project: PCM Migration to DOMO Complete | Deliverable | Go-Live | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-30 17:00 | 2024-03-28 08:00 | -21 | -1.913%
Assumed Completed | -5% to 0% | Project 91 | Project: FMCS Decommission Complete | Deliverable | Go-Live | Assumed Completed | 7. Closure | Delay reason shown here | 2024-01-22 08:00 | 2023-12-29 08:00 | -10 | -0.9107%
Assumed Completed | 0% | Project 132 | Commence Contract Negotiation | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2023-11-13 17:00 | 2023-11-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | FIP approval to award vendor contract | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-03-15 17:00 | 2024-03-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-05-12 17:00 | 2022-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-06-02 17:00 | 2022-06-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Obtain Funding to Support Procurement | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-07-04 17:00 | 2022-07-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2023-07-27 17:00 | 2023-07-27 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Briefing Note Approval to Recruit IT Delivery Lead | Governance | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-07-30 17:00 | 2024-07-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Briefing Note Approval to Recruit Remaining Roles | Governance | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0%
Assumed Completed | N/A | Project 33 | Test Complete | Unassigned | Unassigned | Assumed Completed | Unassigned | Delay reason shown here | 2024-05-31 08:00
Assumed Completed | N/A | Project 33 | Implement Complete | Unassigned | Unassigned | Assumed Completed | Unassigned | Delay reason shown here | 2024-07-19 08:00
Assumed Completed | N/A | Project 33 | 533 AIMS Enhancement Complete | Unassigned | Unassigned | Assumed Completed | Unassigned | Delay reason shown here | 2024-07-19 08:00
Assumed Completed | 0% | Project 163 | Pilot Test Plan signed off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2023-02-13 17:00 | 2023-02-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-05-24 17:00 | 2024-05-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-08 17:00 | 2024-04-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-07-11 17:00 | 2024-07-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-08 17:00 | 2024-04-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | PCR Approved 8 Feb'24 | Governance | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-02-08 08:00 | 2024-02-08 08:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-09-21 17:00 | 2023-09-21 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-09-21 17:00 | 2023-09-21 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.16 Stakeholder Assessment & Eng Plan | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-10-30 17:00 | 2023-10-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.01 Non-Standard Service Request Submitted | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2022-12-16 17:00 | 2022-12-16 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 4.12 Comms Plan Sign-off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.02 GR Cyber Security Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.03 GR Cyber Security Assessment Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | GR4.16 Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | FPE-ST Decomm Complete | Deliverable | Unassigned | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | IIMSS IMPLEMENTATION 2 (5 Aug'24) | Deliverable | Go-Live | Assumed Completed | 7. Closure | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Assumed Completed | N/A | Project 54 | 2.00 Investment Brief (IB) / SoW Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-09-15 17:00
Assumed Completed | N/A | Project 54 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-09-15 17:00
Assumed Completed | N/A | Project 54 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-09-15 17:00
Assumed Completed | 0% | Project 82 | PCR-01: Enhancements SalesForce 2 way Integration | Governance | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-01-24 17:00 | 2024-01-24 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 82 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-08 17:00 | 2024-10-04 17:00 | -24 | -4.982%
Assumed Completed | 0% | Project 82 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Assumed Completed | N/A | Project 55 | IMPLEMENT PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-10-30 17:00
Assumed Completed | N/A | Project 55 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-11-30 17:00
Assumed Completed | N/A | Project 55 | 6.03 Go Live Readiness Complete | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-09-26 17:00
Assumed Completed | N/A | Project 55 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-05-17 17:00
Assumed Completed | N/A | Project 55 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-05-24 17:00
Assumed Completed | N/A | Project 55 | 5.03 Release Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 55 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-05-17 17:00
Assumed Completed | N/A | Project 54 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 91 | (PDA) Architecture & Security Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-05-04 17:00
Assumed Completed | N/A | Project 91 | Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-05-04 17:00
Assumed Completed | N/A | Project 91 | P20 Cost Estimate Approved | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-05-04 17:00
Assumed Completed | N/A | Project 91 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-05-31 17:00
Assumed Completed | N/A | Project 91 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 91 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Assumed Completed | 7. Closure | Delay reason shown here | 2024-07-10 17:00
Assumed Completed | N/A | Project 91 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Assumed Completed | 7. Closure | Delay reason shown here | 2024-07-10 17:00
Assumed Completed | N/A | Project 91 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Assumed Completed | 7. Closure | Delay reason shown here | 2024-07-10 17:00
Assumed Completed | N/A | Project 91 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Assumed Completed | 7. Closure | Delay reason shown here | 2024-07-24 17:00
Assumed Completed | 0% | Project 87 | Investment Brief (IB)/SoW Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-07-09 17:00 | 2024-07-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 87 | (PDA) Architecture & Security Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-07-09 17:00 | 2024-07-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 87 | Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-07-09 17:00 | 2024-07-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 87 | P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-07-09 17:00 | 2024-07-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 87 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-07-09 17:00 | 2024-07-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-09-13 17:00 | 2023-09-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-09-13 17:00 | 2023-09-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-11 17:00 | 2024-12-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-03-03 17:00 | 2025-03-03 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 123 | 6.03 Go Live Readiness Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-24 17:00 | 2025-04-08 17:00 | -10 | -1.701%
Assumed Completed | -10% to -5% | Project 123 | 6.05 Service Design & Definition Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-24 17:00 | 2025-03-05 17:00 | -34 | -5.782%
Assumed Completed | -5% to 0% | Project 163 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-12-05 17:00 | 2024-11-29 08:00 | -5 | -0.9025%
Assumed Completed | 0% | Project 163 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-26 17:00 | 2024-04-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-07-24 17:00 | 2024-07-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.11 Prelim Solution Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-15 17:00 | 2024-03-15 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 163 | DEP OUT: TRAK2 is a Soft Dependency for Solaris | Unassigned | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-12-09 17:00 | 2024-12-06 17:00 | -1 | -0.1805%
Assumed Completed | 0% | Project 163 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-10 17:00 | 2024-04-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-10 17:00 | 2024-04-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-10 17:00 | 2024-04-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-10 17:00 | 2024-04-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-12 17:00 | 2024-04-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-05-24 17:00 | 2024-05-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-10-30 17:00 | 2023-10-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 6.05 Service Design & Definition Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | GR:6.07 Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | PCR-02: Extend project to end Aug'24 | Governance | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-06-20 17:00 | 2024-06-20 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | Service Continuity Runbook Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-08 17:00 | 2024-04-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | GR5.07 Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-05-24 17:00 | 2024-05-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 5.03 Release Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-05-24 17:00 | 2024-05-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-05-24 17:00 | 2024-05-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-19 08:00 | 2024-04-19 08:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2023-09-07 17:00 | 2023-09-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | GR4.17 Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 2.00 Investment Brief (IB) / SoW Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2022-08-18 17:00 | 2022-08-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2022-08-18 17:00 | 2022-08-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2022-08-18 17:00 | 2022-08-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2022-08-18 17:00 | 2022-08-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.00 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2022-11-25 17:00 | 2022-11-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 5.03 Release Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-21 17:00 | 2024-11-21 17:00 | 0 | 0%
Assumed Completed | N/A | Project 54 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-06-28 17:00
Assumed Completed | N/A | Project 54 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-06-28 17:00
Assumed Completed | 0% | Project 121 | PCR-02: Extend project to FY25 Q2 (Approved 26/6) | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-06-26 17:00 | 2024-06-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-06-27 17:00 | 2024-06-27 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-06-27 17:00 | 2024-06-27 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-06-27 17:00 | 2024-06-27 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-06-27 17:00 | 2024-06-27 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-06-27 17:00 | 2024-06-27 17:00 | 0 | 0%
Assumed Completed | N/A | Project 46 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2019-10-21 17:00
Assumed Completed | N/A | Project 46 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2019-10-21 17:00
Assumed Completed | N/A | Project 46 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2019-10-21 17:00
Assumed Completed | N/A | Project 46 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Assumed Completed | N/A | Project 46 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-30 17:00
Assumed Completed | N/A | Project 46 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-30 17:00
Assumed Completed | N/A | Project 46 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-30 17:00
Assumed Completed | N/A | Project 46 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-30 17:00
Assumed Completed | N/A | Project 46 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-30 17:00
Assumed Completed | N/A | Project 46 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-30 17:00
Assumed Completed | N/A | Project 46 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-30 17:00
Assumed Completed | N/A | Project 46 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-30 17:00
Assumed Completed | N/A | Project 46 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-30 17:00
Assumed Completed | N/A | Project 46 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-30 17:00
Assumed Completed | -10% to -5% | Project 87 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-09-18 17:00 | 2024-08-02 17:00 | -33 | -6.846%
Assumed Completed | -10% to -5% | Project 87 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-09-18 17:00 | 2024-08-02 17:00 | -33 | -6.846%
Assumed Completed | -5% to 0% | Project 87 | 3.04 PACT Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-09-02 17:00 | 2024-08-02 17:00 | -21 | -4.357%
Assumed Completed | -5% to 0% | Project 87 | 3.06 Business Requirements Document Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-09-02 17:00 | 2024-08-02 17:00 | -21 | -4.357%
Assumed Completed | -5% to 0% | Project 87 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-09-02 17:00 | 2024-08-02 17:00 | -21 | -4.357%
Assumed Completed | -5% to 0% | Project 87 | 3.14 Project Management Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-09-02 17:00 | 2024-08-02 17:00 | -21 | -4.357%
Assumed Completed | -10% to -5% | Project 87 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-09-30 17:00 | 2024-08-02 17:00 | -41 | -8.506%
Assumed Completed | 0% | Project 5 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-07 17:00 | 2024-08-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-07 17:00 | 2024-08-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-07-15 17:00 | 2024-07-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-07-01 17:00 | 2024-07-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-07-24 17:00 | 2024-07-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-07-19 17:00 | 2024-07-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-22 17:00 | 2024-08-22 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-22 17:00 | 2024-08-22 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-09-17 17:00 | 2024-09-17 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 2.00 Investment Brief Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-04-28 17:00 | 2023-04-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-04-28 17:00 | 2023-04-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-04-28 17:00 | 2023-04-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-04-28 17:00 | 2023-04-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-04-28 17:00 | 2023-04-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 123 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-24 17:00 | 2025-03-31 17:00 | -16 | -2.721%
Assumed Completed | -5% to 0% | Project 123 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-01 17:00 | 2025-03-10 17:00 | -16 | -2.721%
Assumed Completed | -5% to 0% | Project 123 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-24 17:00 | 2025-03-28 17:00 | -17 | -2.891%
Assumed Completed | 0% | Project 123 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-26 17:00 | 2024-11-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-26 17:00 | 2024-11-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-26 17:00 | 2024-11-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-27 17:00 | 2024-11-27 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-06-24 17:00 | 2024-06-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-10 17:00 | 2024-10-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | HDI>>ODS Control Systems 23/8 (Andrew Wilson) | External | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | SDI>>ODS Control Systems 23/8 (Andrew Wilson) | External | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-07-11 17:00 | 2024-07-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-07-19 17:00 | 2024-07-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-06-14 17:00 | 2024-06-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2021-07-01 17:00 | 2021-07-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2021-09-30 17:00 | 2021-09-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2021-09-30 17:00 | 2021-09-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2021-07-30 17:00 | 2021-07-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2021-09-30 17:00 | 2021-09-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-07-04 17:00 | 2022-07-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 2.00 Investment Brief (IB / BN) / SoW Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-07-04 17:00 | 2022-07-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-07-04 17:00 | 2022-07-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-07-04 17:00 | 2022-07-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-11-07 17:00 | 2024-11-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-01-06 17:00 | 2025-01-06 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-01-23 17:00 | 2025-01-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-11-21 17:00 | 2024-11-21 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-12-18 17:00 | 2024-12-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-11-21 17:00 | 2024-11-21 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 137 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-09 17:00 | 2025-04-17 17:00 | 6 | 0.4721%
Assumed Completed | 5% to 10% | Project 163 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-04 17:00 | 2024-11-22 17:00 | 34 | 6.137%
Assumed Completed | 0% to 5% | Project 163 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-22 17:00 | 2024-11-29 17:00 | 5 | 0.9025%
Assumed Completed | 0% to 5% | Project 163 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-01 17:00 | 2024-11-15 17:00 | 10 | 1.805%
Assumed Completed | 0% to 5% | Project 163 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-25 17:00 | 2024-11-22 17:00 | 20 | 3.61%
Assumed Completed | 0% | Project 163 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-28 17:00 | 2024-10-28 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 163 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-25 17:00 | 2024-10-28 17:00 | 1 | 0.1805%
Assumed Completed | 0% to 5% | Project 163 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-09 17:00 | 2024-10-28 17:00 | 13 | 2.347%
Assumed Completed | 0% to 5% | Project 163 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-01 17:00 | 2024-11-08 17:00 | 5 | 0.9025%
Assumed Completed | 0% to 5% | Project 163 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-25 17:00 | 2024-10-28 17:00 | 1 | 0.1805%
Assumed Completed | 0% to 5% | Project 163 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-25 17:00 | 2024-10-28 17:00 | 1 | 0.1805%
Assumed Completed | 0% to 5% | Project 163 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-21 17:00 | 2024-10-28 17:00 | 5 | 0.9025%
Assumed Completed | 0% to 5% | Project 163 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-21 17:00 | 2024-10-28 17:00 | 5 | 0.9025%
Assumed Completed | 0% to 5% | Project 163 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-01 17:00 | 2024-10-28 17:00 | 18 | 3.249%
Assumed Completed | 0% to 5% | Project 163 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-01 17:00 | 2024-10-28 17:00 | 18 | 3.249%
Assumed Completed | 0% to 5% | Project 163 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-01 17:00 | 2024-10-28 17:00 | 18 | 3.249%
Assumed Completed | 0% | Project 163 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 5 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0%
Assumed Completed | 5% to 10% | Project 157 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-12-02 17:00 | 2025-02-28 17:00 | 53 | 7.593%
Assumed Completed | 0% | Project 157 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-09-11 17:00 | 2024-09-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-12 17:00 | 2024-08-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-12 17:00 | 2024-08-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-12 17:00 | 2024-08-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-08-12 17:00 | 2024-08-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 157 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 157 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-10-31 17:00 | 2024-11-01 17:00 | 1 | 0.1433%
Assumed Completed | -5% to 0% | Project 157 | 4.01 Sol'n Architecture Design (SAD) ProgArchV1.4 | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-04 17:00 | 2025-02-26 17:00 | -27 | -3.868%
Assumed Completed | -10% to -5% | Project 157 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-14 17:00 | 2025-02-21 17:00 | -36 | -5.158%
Assumed Completed | -10% to -5% | Project 157 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-30 17:00 | 2025-02-14 17:00 | -50 | -7.163%
Assumed Completed | -10% to -5% | Project 157 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-05-05 17:00 | 2025-01-31 17:00 | -63 | -9.026%
Assumed Completed | -10% to -5% | Project 157 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-05-06 17:00 | 2025-02-27 17:00 | -45 | -6.447%
Assumed Completed | 0% | Project 132 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-06 17:00 | 2024-08-06 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-06-05 17:00 | 2024-06-05 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-25 17:00 | 2025-02-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-07-24 17:00 | 2024-07-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-25 17:00 | 2025-02-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-05 17:00 | 2024-08-05 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-25 17:00 | 2025-02-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-09 17:00 | 2024-10-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-10 17:00 | 2024-10-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-20 17:00 | 2024-09-20 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 92 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-17 17:00 | 2025-04-01 17:00 | -12 | -2.948%
Assumed Completed | 0% | Project 123 | 3.12 Program Architecture Guide Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 141 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 141 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-09 17:00 | 2024-09-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 141 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-23 17:00 | 2024-09-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 141 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-23 17:00 | 2024-09-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 141 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-12-15 17:00 | 2023-12-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-08-31 17:00 | 2023-08-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-08-31 17:00 | 2023-08-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-08-31 17:00 | 2023-08-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-08-31 17:00 | 2023-08-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-08-31 17:00 | 2023-08-31 17:00 | 0 | 0%
Assumed Completed | -10% to -5% | Project 44 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-06 17:00 | 2024-06-28 17:00 | -114 | -9.283%
Assumed Completed | -10% to -5% | Project 44 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-06 17:00 | 2024-06-28 17:00 | -114 | -9.283%
Assumed Completed | -25% to -10% | Project 44 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-31 17:00 | 2024-06-28 17:00 | -143 | -11.64%
Assumed Completed | -25% to -10% | Project 44 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-31 17:00 | 2024-06-28 17:00 | -143 | -11.64%
Assumed Completed | -25% to -10% | Project 44 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-31 17:00 | 2024-06-28 17:00 | -143 | -11.64%
Assumed Completed | 10% to 25% | Project 44 | 7.02 PIR Sign Off (done for Phase 2 Only) | Deliverable | Gate 3 Approval | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-30 17:00 | 2025-06-20 17:00 | 194 | 15.8%
Assumed Completed | 0% | Project 108 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-24 17:00 | 2024-09-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 108 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-24 17:00 | 2024-09-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 108 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-24 17:00 | 2024-09-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 108 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 108 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-24 17:00 | 2024-09-24 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 108 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 08:00 | -1 | -0.3205%
Assumed Completed | -25% to -10% | Project 108 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-17 17:00 | 2025-01-31 08:00 | -55 | -17.63%
Assumed Completed | -25% to -10% | Project 108 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-31 17:00 | 2025-02-14 08:00 | -32 | -10.26%
Assumed Completed | 0% | Project 144 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-05-10 17:00 | 2024-05-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-05 17:00 | 2024-08-05 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-07 17:00 | 2024-08-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-09 17:00 | 2024-08-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-04-24 17:00 | 2024-04-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-04-26 17:00 | 2024-04-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-04-29 17:00 | 2024-04-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-04-30 17:00 | 2024-04-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-05-24 17:00 | 2024-05-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-12 17:00 | 2024-08-12 17:00 | 0 | 0%
Assumed Completed | -25% to -10% | Project 147 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2024-12-20 17:00 | -59 | -13.38%
Assumed Completed | 0% | Project 143 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-14 17:00 | 2024-10-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-21 17:00 | 2024-10-21 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-11 17:00 | 2024-11-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-20 17:00 | 2024-11-20 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-09 17:00 | 2025-01-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-19 17:00 | 2024-11-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-06 17:00 | 2024-11-06 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-19 17:00 | 2024-11-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-19 17:00 | 2024-11-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-05-10 17:00 | 2024-05-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-09 17:00 | 2024-10-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-06 17:00 | 2024-11-06 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-04 17:00 | 2024-12-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-28 17:00 | 2025-01-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-18 17:00 | 2025-02-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-19 17:00 | 2024-11-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-19 17:00 | 2025-02-19 17:00 | 0 | 0%
Assumed Completed | -25% to -10% | Project 34 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2024-12-20 17:00 | -59 | -18.27%
Assumed Completed | -5% to 0% | Project 34 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-17 17:00 | 2025-04-04 17:00 | -9 | -2.786%
Assumed Completed | 0% | Project 34 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-03 17:00 | 2025-02-03 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-04 17:00 | 2024-12-04 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 34 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-24 17:00 | 2025-04-30 17:00 | 3 | 0.9288%
Assumed Completed | -5% to 0% | Project 59 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-27 17:00 | -1 | -0.3731%
Assumed Completed | 0% to 5% | Project 59 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-21 17:00 | 2025-02-28 17:00 | 5 | 1.866%
Assumed Completed | 5% to 10% | Project 59 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2025-01-31 17:00 | 19 | 7.09%
Assumed Completed | 0% | Project 59 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-24 17:00 | 2025-01-24 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 59 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-14 17:00 | 2025-02-27 17:00 | -11 | -4.104%
Assumed Completed | -10% to -5% | Project 59 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-07 17:00 | 2025-02-03 17:00 | -24 | -8.955%
Assumed Completed | 5% to 10% | Project 59 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2025-02-11 17:00 | 26 | 9.701%
Assumed Completed | -10% to -5% | Project 59 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-10 17:00 | -14 | -5.224%
Assumed Completed | 10% to 25% | Project 59 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-21 17:00 | 2025-04-04 17:00 | 30 | 11.19%
Assumed Completed | 0% | Project 167 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 167 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 167 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 167 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 167 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 167 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-22 17:00 | 2024-11-04 17:00 | -14 | -4.107%
Assumed Completed | 0% | Project 167 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 167 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-22 17:00 | 2024-11-08 17:00 | -10 | -2.934%
Assumed Completed | 0% | Project 167 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0%
Assumed Completed | -25% to -10% | Project 167 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-17 17:00 | 2024-11-12 17:00 | -38 | -11.15%
Assumed Completed | -25% to -10% | Project 167 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-17 17:00 | 2024-11-14 17:00 | -36 | -10.56%
Assumed Completed | -25% to -10% | Project 167 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-21 17:00 | 2024-11-13 17:00 | -61 | -17.9%
Assumed Completed | -25% to -10% | Project 167 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-13 17:00 | 2024-11-08 17:00 | -36 | -10.56%
Assumed Completed | <-25% | Project 167 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-24 17:00 | 2024-11-15 17:00 | -101 | -29.63%
Assumed Completed | 0% | Project 167 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-06 17:00 | 2024-09-06 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-09 17:00 | 2024-09-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-10 17:00 | 2024-09-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-11 17:00 | 2024-09-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-12 17:00 | 2024-09-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-09 17:00 | 2024-10-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-01 17:00 | 2024-11-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-09 17:00 | 2024-10-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-04 17:00 | 2024-12-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 142 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-09 17:00 | 2025-04-01 17:00 | -6 | -3.896%
Assumed Completed | 0% | Project 142 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 4.00 Infra' Sol'n Design Sign Off - LLID DEV+SIT | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-01 17:00 | 2024-11-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-11 17:00 | 2024-11-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-04 17:00 | 2024-11-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-01 17:00 | 2024-11-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-04 17:00 | 2024-12-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-06 17:00 | 2024-12-06 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-06 17:00 | 2024-12-06 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-01-15 17:00 | 2025-01-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | GO LIVE | Deliverable | Go-Live | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 142 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-28 17:00 | 2024-10-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-16 17:00 | 2024-10-16 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-22 17:00 | 2024-11-22 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-28 17:00 | 2024-10-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-28 17:00 | 2024-10-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-09 17:00 | 2024-09-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | EVALUATE END (DOCUMENTUM) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-02-11 17:00 | 2025-02-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | GO LIVE Oracle Solaris: MY TIME & PAY | Deliverable | Go-Live | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-09-24 17:00 | 2024-09-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-09-26 17:00 | 2024-09-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-14 17:00 | 2024-10-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-06 17:00 | 2024-11-06 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-14 17:00 | 2024-10-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-06 17:00 | 2024-11-06 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 166 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-03-31 17:00 | 2025-03-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 92 | BUILD & TEST PHASE COMPLETE (TPS) | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-08-05 17:00 | 2024-08-05 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-08-05 17:00 | 2024-08-05 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-19 17:00 | 2024-12-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-10 17:00 | 2024-09-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-05 17:00 | 2024-09-05 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-12 17:00 | 2024-09-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-08 17:00 | 2024-10-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-12 17:00 | 2024-09-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-19 17:00 | 2024-12-19 17:00 | 0 | 0%
Assumed Completed | -25% to -10% | Project 139 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-14 17:00 | 2025-02-28 17:00 | -31 | -14.03%
Assumed Completed | 0% | Project 139 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 139 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-17 17:00 | 2025-04-04 17:00 | -9 | -4.072%
Assumed Completed | 0% | Project 139 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-08-28 17:00 | 2024-08-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 139 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-12 17:00 | 2024-09-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2021-09-01 17:00 | 2021-09-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2021-09-01 17:00 | 2021-09-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2021-09-01 17:00 | 2021-09-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2021-09-01 17:00 | 2021-09-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2021-09-01 17:00 | 2021-09-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 165 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 165 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-01-15 17:00 | 2024-11-29 17:00 | -23 | -1.071%
Assumed Completed | -5% to 0% | Project 165 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-02-21 17:00 | 2024-11-29 17:00 | -49 | -2.282%
Assumed Completed | -5% to 0% | Project 165 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-02-24 17:00 | 2024-11-29 17:00 | -50 | -2.329%
Assumed Completed | 0% | Project 123 | OT-IT Phase 2 Drop 1 Go Live | Deliverable | Go-Live | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 123 | OT-IT Phase 2 Drop 3 Go Live | Deliverable | Go-Live | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-28 17:00 | 2025-04-14 17:00 | -7 | -1.19%
Assumed Completed | 0% | Project 123 | OT-IT Phase 2 Drop 2 Go Live | Deliverable | Go-Live | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-01 17:00 | 2024-11-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | PCR-02: Extend project to end Mar'25 | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0%
Assumed Completed | 5% to 10% | Project 132 | 4.02 Functional Specification Sign Off (R1.1) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-17 17:00 | 2026-01-13 17:00 | 176 | 6.622%
Assumed Completed | -5% to 0% | Project 147 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2025-02-28 17:00 | -20 | -4.536%
Assumed Completed | 0% | Project 147 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0%
Assumed Completed | -10% to -5% | Project 147 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-11 17:00 | 2025-03-03 17:00 | -29 | -6.578%
Assumed Completed | 0% | Project 147 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-03 17:00 | 2025-03-03 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-19 17:00 | 2024-09-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 147 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-19 17:00 | 2024-09-19 17:00 | 0 | 0%
Assumed Completed | -25% to -10% | Project 144 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-03 17:00 | 2024-12-04 17:00 | -52 | -10.28%
Assumed Completed | -10% to -5% | Project 144 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-03 17:00 | 2024-12-12 17:00 | -46 | -9.091%
Assumed Completed | 0% | Project 144 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-15 17:00 | 2025-04-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-17 17:00 | 2025-04-17 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-23 17:00 | 2025-04-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-28 17:00 | 2025-04-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-15 17:00 | 2025-04-15 17:00 | 0 | 0%
Assumed Completed | N/A | Project 144 | 4.05 Sprint Plan (Repeat for each sprint) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-03 17:00
Assumed Completed | N/A | Project 144 | 4.06 Sprint Review (Repeat for each sprint) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-03 17:00
Assumed Completed | N/A | Project 144 | 4.07 Sprint Retrospective (Repeat for each sprint) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-03 17:00
Assumed Completed | N/A | Project 22 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-03-28 17:00
Assumed Completed | N/A | Project 22 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-03-28 17:00
Assumed Completed | N/A | Project 22 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-03-28 17:00
Assumed Completed | N/A | Project 22 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-03-28 17:00
Assumed Completed | N/A | Project 22 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-03-28 17:00
Assumed Completed | N/A | Project 22 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-14 17:00
Assumed Completed | N/A | Project 22 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-14 17:00
Assumed Completed | N/A | Project 22 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-14 17:00
Assumed Completed | N/A | Project 22 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-14 17:00
Assumed Completed | N/A | Project 22 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-14 17:00
Assumed Completed | N/A | Project 22 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-14 17:00
Assumed Completed | N/A | Project 22 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-14 17:00
Assumed Completed | N/A | Project 22 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-14 17:00
Assumed Completed | N/A | Project 22 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-14 17:00
Assumed Completed | N/A | Project 22 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-28 17:00
Assumed Completed | N/A | Project 22 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-28 17:00
Assumed Completed | N/A | Project 22 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-28 17:00
Assumed Completed | N/A | Project 22 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-28 17:00
Assumed Completed | N/A | Project 22 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-28 17:00
Assumed Completed | N/A | Project 22 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-28 17:00
Assumed Completed | N/A | Project 22 | GO LIVE | Deliverable | Go-Live | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-28 17:00
Assumed Completed | N/A | Project 22 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-06-28 17:00
Assumed Completed | N/A | Project 22 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Assumed Completed | N/A | Project 22 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | N/A | Project 22 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Assumed Completed | 0% | Project 82 | IIMSS IMPLEMENTATION 3 (30 Sep'24) | Deliverable | Go-Live | Assumed Completed | 7. Closure | Delay reason shown here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-03-26 17:00 | 2024-03-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-07 17:00 | 2024-11-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-15 17:00 | 2024-10-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-10 17:00 | 2024-12-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-13 17:00 | 2024-11-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-17 17:00 | 2024-10-17 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-28 17:00 | 2024-10-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00 | 2024-12-13 17:00 | 0 | 0%
Assumed Completed | 5% to 10% | Project 154 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-17 17:00 | 2025-02-24 17:00 | 25 | 7.53%
Assumed Completed | 0% | Project 154 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 154 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-18 17:00 | 2024-11-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2022-12-12 17:00 | 2022-12-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-03-21 17:00 | 2023-03-21 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-01-23 17:00 | 2023-01-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | GO LIVE TMC Digital Rostering System (Ph 1) | Deliverable | Go-Live | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-04 17:00 | 2024-11-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 140 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-17 17:00 | 2025-04-17 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-28 17:00 | 2025-04-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-28 17:00 | 2025-04-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-28 17:00 | 2025-04-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-28 17:00 | 2025-04-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-28 17:00 | 2025-04-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 98 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | PLM1060 System Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-05-21 17:00 | 2024-05-21 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 123 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-30 17:00 | 2025-04-22 17:00 | -5 | -0.8503%
Assumed Completed | 0% to 5% | Project 123 | 4.00 Technical Sol'n Design Sign Off - PLM1080 | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-30 17:00 | 2025-05-19 17:00 | 13 | 2.211%
Assumed Completed | 0% | Project 142 | PCR-01: Scope & Timeline Change SUBMITTED | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 5.01 Test Cases Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 151 | 5.06 Release Requested (Opt) | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-03-07 17:00 | 2025-03-31 17:00 | 16 | 0.9883%
Assumed Completed | 0% to 5% | Project 151 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-03-17 17:00 | 2025-03-31 17:00 | 10 | 0.6177%
Assumed Completed | 0% | Project 151 | 5.01 Test Cases Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-04-07 17:00 | 2025-04-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 5.06 Release Requested (Opt) | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-03-17 17:00 | 2025-03-17 17:00 | 0 | 0%
Assumed Completed | 0% | Project 137 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-03-17 17:00 | 2025-03-17 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | Integrations (EiPaaS or TIBCO) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | Java 6 to Java 17 Migration | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | WebSphere to Tomcat | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | Spring to Springboot Conversion | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | OUD to Smart ID Connect | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | Oracle 11g to Oracle 19C | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | Solaris to RHEL | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | JAVA 6 to 17 Upgrade | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | IBM Websphere to Springboot Framework Migration | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | Pilot Build Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | Pilot Solution Architecture Design Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | OUD Replacement with Entra ID Solution | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | Automation Test Suite Assessment | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-16 17:00 | 2024-12-16 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | Pilot Outcomes Review Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-27 17:00 | 2025-02-27 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-07-05 17:00 | 2024-07-05 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-11 17:00 | 2025-03-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-09-16 17:00 | 2024-09-16 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 5.01 Test Cases Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-09-09 17:00 | 2024-09-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-02-24 17:00 | 2025-02-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 5.06 Release Requested - Primavera | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-11-04 17:00 | 2024-11-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 5.00 Service Continuity Runbook Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-02-24 17:00 | 2025-02-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Primavera BUILD & TEST PHASE COMPLETE | Governance | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-02-24 17:00 | 2025-02-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 6.02 Implementation Plan Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 6.00 Application Handover Checklist Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-03-03 17:00 | 2025-03-03 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Primavera GO LIVE | Deliverable | Go-Live | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-03-03 17:00 | 2025-03-03 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Primavera ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 59 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-15 17:00 | 2024-11-28 17:00 | 9 | 3.358%
Assumed Completed | 0% | Project 59 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-28 17:00 | 2024-11-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 59 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 59 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 59 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0%
Assumed Completed | -10% to -5% | Project 59 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-02 17:00 | -14 | -5.224%
Assumed Completed | 0% to 5% | Project 59 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-22 17:00 | 2024-11-28 17:00 | 4 | 1.493%
Assumed Completed | 0% | Project 151 | BlockSheets ANALYSIS & DESIGN PHASE COMPLETE | Governance | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 5.01 Test Cases Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-02-03 17:00 | 2025-02-03 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | BlockSheets BUILD & TEST PHASE COMPLETE | Governance | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 151 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-04-11 17:00 | 2025-03-31 17:00 | -9 | -0.5559%
Assumed Completed | -5% to 0% | Project 151 | 6.00 Application Handover Checklist Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-04-17 17:00 | 2025-03-31 17:00 | -13 | -0.803%
Assumed Completed | 0% | Project 151 | SSTS ANALYSIS & DESIGN PHASE COMPLETE | Governance | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 5.01 Test Cases Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2025-03-07 17:00 | 2025-03-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Final Decision: RAMSYS TRACKWARE CANCELLED | Governance | Unassigned | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 72 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 72 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 72 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 72 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 72 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 120 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 120 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2025-02-27 17:00 | 2025-03-03 17:00 | 2 | 0.2635%
Assumed Completed | 0% | Project 120 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-03-26 17:00 | 2024-03-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 120 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 120 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 120 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 120 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 141 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-21 17:00 | 2025-01-21 17:00 | 0 | 0%
Assumed Completed | 0% | Project 72 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-11-07 17:00 | 2024-11-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 72 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-04 17:00 | 2025-04-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 72 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-04 17:00 | 2025-04-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 72 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 72 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-29 17:00 | 2025-04-17 17:00 | -5 | -2.033%
Assumed Completed | 0% to 5% | Project 72 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-29 17:00 | 2025-04-30 17:00 | 1 | 0.4065%
Assumed Completed | 0% | Project 72 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-03 17:00 | 2025-02-03 17:00 | 0 | 0%
Assumed Completed | 0% | Project 72 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0%
Assumed Completed | N/A | Project 169 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-06 17:00
Assumed Completed | 0% | Project 142 | 4.00 LLID for Pre Production & Prod Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | N/A | Project 158 | Kick Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2024-11-01 17:00
Assumed Completed | 0% | Project 154 | 3.21 Final Business Case Sign Off 3/12 | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-03 17:00 | 2024-12-03 17:00 | 0 | 0%
Assumed Completed | 0% | Project 120 | EOI Submission Complete | Unassigned | Yes | Assumed Completed | 6. Implement | Delay reason shown here | 2024-05-07 17:00 | 2024-05-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | Pilot SIT Completed | Deliverable | Yes | Assumed Completed | 7. Closure | Delay reason shown here | 2023-11-28 17:00 | 2023-11-28 17:00 | 0 | 0%
Assumed Completed | N/A | Project 128 | Concept Phase Complete | Unassigned | Yes | Assumed Completed | 2. Concept | Delay reason shown here | 2023-10-13 17:00
Assumed Completed | 0% | Project 151 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-11-01 17:00 | 2023-11-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.21 Strategic Business Case (SBC) Approved (FIAC) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-08 08:00 | 2024-03-08 08:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 46 | TMS R4 UAT environment setup- Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-26 17:00 | 2024-10-01 17:00 | 47 | 2.744%
Assumed Completed | 0% | Project 163 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-09-01 17:00 | 2023-09-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-12-15 17:00 | 2023-12-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-12-15 17:00 | 2023-12-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 44 | Business Justification signed off | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-07-28 | 2022-07-28 | 0 | 0%
Assumed Completed | 0% | Project 44 | Concept Phase Complete | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-02-07 | 2022-02-07 | 0 | 0%
Assumed Completed | 0% | Project 44 | Evaluate Phase complete | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-08-18 | 2022-08-18 | 0 | 0%
Assumed Completed | 0% | Project 121 | Build Phase Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-04-20 | 2023-04-20 | 0 | 0%
Assumed Completed | 0% | Project 165 | 3.06 Business Requirements Document Sign Off | Unassigned | Unassigned | Assumed Completed | 5. Build & Test | Delay reason shown here | 2021-09-23 17:00 | 2021-09-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 44 | SAD signed off | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-09-15 | 2022-09-15 | 0 | 0%
Assumed Completed | 0% | Project 91 | Investment Brief (IB)/SoW Sign Off (Phase 1) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-05-04 | 2023-05-04 | 0 | 0%
Assumed Completed | 0% | Project 165 | 3.14 Project Management Plan Sign Off | Unassigned | Unassigned | Assumed Completed | 5. Build & Test | Delay reason shown here | 2021-09-23 17:00 | 2021-09-23 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 165 | 3.21 Strategic/Final Business Case Approved (FIAC) | Unassigned | Unassigned | Assumed Completed | 5. Build & Test | Delay reason shown here | 2021-06-14 17:00 | 2021-09-23 17:00 | 73 | 3.4%
Assumed Completed | 0% | Project 165 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 91 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-05-04 | 2023-05-04 | 0 | 0%
Assumed Completed | 0% | Project 44 | Build and Test SGR Completed | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-12-02 | 2022-12-02 | 0 | 0%
Assumed Completed | 0% | Project 44 | Test strategy and plan signed off | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-10-05 | 2022-10-05 | 0 | 0%
Assumed Completed | 0% | Project 44 | Test Summary Report | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-12-02 | 2022-12-02 | 0 | 0%
Assumed Completed | 0% | Project 82 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-08 17:00 | 2024-04-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | Pilot PSAD signed off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2023-10-05 08:00 | 2023-10-05 08:00 | 0 | 0%
Assumed Completed | <-25% | Project 55 | UAT Execution and completion | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-09-13 17:00 | 2024-01-29 17:00 | -160 | -36.61%
Assumed Completed | 0% | Project 151 | Oracle Apex - GSU Migration Discovery Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-12-04 17:00 | 2023-12-04 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 55 | Investment Brief (IB) or SoW Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-09-28 17:00 | 2023-09-01 17:00 | -19 | -4.348%
Assumed Completed | 0% to 5% | Project 163 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-15 17:00 | 2024-11-29 17:00 | 10 | 1.805%
Assumed Completed | -5% to 0% | Project 55 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-09-29 17:00 | 2023-09-08 17:00 | -15 | -3.432%
Assumed Completed | 0% | Project 151 | Oracle Apex - GSU Migration Analysis Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0%
Assumed Completed | -25% to -10% | Project 55 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-11-10 17:00 | 2023-09-08 17:00 | -44 | -10.07%
Assumed Completed | 0% | Project 151 | Ph1 - GovDC Migration Establishment | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Ph1 - GovDC uplift Migration Discovery Complet | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-02-28 17:00 | 2024-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Ph1 - Migration Analysis Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-04-02 17:00 | 2024-04-02 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Oracle Apex - GSU Migration Implementation and go- | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-04-22 17:00 | 2024-04-22 17:00 | 0 | 0%
Assumed Completed | 0% | Project 91 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-05-04 | 2023-05-04 | 0 | 0%
Assumed Completed | 0% | Project 151 | Oracle Apex - GSU Migration Establishment | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-10-23 17:00 | 2023-10-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Ph1 - GovDC uplift Migration Scratch and Desig | Governance | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-07-01 17:00 | 2024-07-01 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 163 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-12-05 17:00 | 2024-12-05 08:00 | -1 | -0.1805%
Assumed Completed | 0% | Project 44 | Develop Implementation plan | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-11-23 | 2022-11-23 | 0 | 0%
Assumed Completed | <-25% | Project 55 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-09-13 17:00 | 2024-01-16 08:00 | -169 | -38.67%
Assumed Completed | <-25% | Project 55 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-09-25 17:00 | 2024-01-12 08:00 | -179 | -40.96%
Assumed Completed | 0% | Project 46 | 2.00 Investment Brief (IB) / SoW Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2019-10-21 | 2019-10-21 | 0 | 0%
Assumed Completed | -5% to 0% | Project 46 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-04-06 17:00 | 2023-04-06 | -1 | -0.05838%
Assumed Completed | 0% | Project 44 | Pilot Phase Business Go-Live for Digital Roster an | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-12-12 | 2022-12-12 | 0 | 0%
Assumed Completed | -5% to 0% | Project 46 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2019-10-21 17:00 | 2019-10-21 | -1 | -0.05838%
Assumed Completed | 0% | Project 121 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 55 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-11-07 17:00 | 2023-11-17 08:00 | 7 | 1.602%
Assumed Completed | 0% to 5% | Project 46 | TMS R4 SIT Test summary report- Complete | Deliverable | Yes | Assumed Completed | 6. Implement | Delay reason shown here | 2024-06-28 17:00 | 2024-08-27 17:00 | 42 | 2.452%
Assumed Completed | -25% to -10% | Project 44 | 7.03 Closure Memo Sign Off for Phase 2 | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-28 17:00 | 2024-01-31 08:00 | -287 | -23.37%
Assumed Completed | 0% | Project 55 | P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-07-25 17:00 | 2023-07-25 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 46 | TMS R4 SIT Test summary report- Commencement | Deliverable | Yes | Assumed Completed | 6. Implement | Delay reason shown here | 2024-06-28 17:00 | 2024-08-21 17:00 | 38 | 2.218%
Assumed Completed | 0% | Project 44 | Implementation Pilot phase complete | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2023-01-13 | 2023-01-13 | 0 | 0%
Assumed Completed | 0% | Project 165 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-07-14 17:00 | 2023-07-14 17:00 | 0 | 0%
Assumed Completed | <-25% | Project 55 | GO LIVE - Tactical Fix: SQL 2000 DB Upg to 2014 | Deliverable | Go-Live | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-10-22 17:00 | 2024-02-02 17:00 | -182 | -41.65%
Assumed Completed | 0% | Project 44 | Phase 2 (all Maritime) Business Go-Live for Digita | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2023-07-24 | 2023-07-24 | 0 | 0%
Assumed Completed | 0% | Project 151 | CMS Phase 1 Migration Establishment | Deliverable | Yes | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 54 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-09-29 17:00 | 2023-09-29 08:00 | -1 | -0.1372%
Assumed Completed | -10% to -5% | Project 54 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-12-08 17:00 | 2023-09-22 08:00 | -55 | -7.545%
Assumed Completed | 0% | Project 151 | Rail.hr Migration Implementation and go-live | Deliverable | Go-Live | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 55 | P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-08-25 17:00 | 2023-08-25 17:00 | 0 | 0%
Assumed Completed | 0% | Project 151 | Ramsys & Trackware Migrt. Scratch &Design Complete | Governance | Unassigned | Assumed Completed | 5. Build & Test | Delay reason shown here | 2024-07-01 17:00 | 2024-07-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2022-11-25 17:00 | 2022-11-25 17:00 | 0 | 0%
Assumed Completed | -10% to -5% | Project 54 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-11-30 17:00 | 2023-09-28 17:00 | -44 | -6.036%
Assumed Completed | 0% to 5% | Project 46 | Execute TMS R4 SIT test cases- Complete | Unassigned | Yes | Assumed Completed | 6. Implement | Delay reason shown here | 2024-06-24 17:00 | 2024-08-06 17:00 | 31 | 1.81%
Assumed Completed | 0% | Project 121 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2022-02-23 17:00 | 2022-02-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 44 | Deliverable 1 Finished | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2021-11-08 | 2021-11-08 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-01-11 17:00 | 2023-01-11 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 46 | Execute TMS R4 SIT test cases- Commencement | Deliverable | Yes | Assumed Completed | 6. Implement | Delay reason shown here | 2024-05-31 17:00 | 2024-07-10 17:00 | 27 | 1.576%
Assumed Completed | 0% | Project 165 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 54 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-11-24 17:00 | 2023-11-24 17:00 | 0 | 0%
Assumed Completed | 0% | Project 54 | Project Health Check Complete 1/12 | Governance | Yes | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-12-01 17:00 | 2023-12-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-02-29 08:00 | 2024-02-29 08:00 | 0 | 0%
Assumed Completed | 0% | Project 44 | Raise shopping cart to create PO | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-05-30 | 2022-05-30 | 0 | 0%
Assumed Completed | 0% | Project 44 | Build Complete | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-10-17 | 2022-10-17 | 0 | 0%
Assumed Completed | 0% | Project 121 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-07 17:00 | 2023-02-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2022-08-18 17:00 | 2022-08-18 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 46 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00 | 2023-07-31 | -1 | -0.05838%
Assumed Completed | 0% | Project 82 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-10-16 17:00 | 2023-10-16 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 46 | TMS R4 UAT Interface & Testing Support Commenced | Deliverable | Yes | Assumed Completed | 6. Implement | Delay reason shown here | 2024-06-28 17:00 | 2024-10-17 17:00 | 78 | 4.553%
Assumed Completed | -5% to 0% | Project 46 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-06-30 17:00 | 2023-06-30 | -1 | -0.05838%
Assumed Completed | -25% to -10% | Project 54 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-09-15 17:00 | 2023-04-05 | -114 | -15.64%
Assumed Completed | 0% | Project 121 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 46 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-31 17:00 | 2023-07-31 | -1 | -0.05838%
Assumed Completed | 0% | Project 82 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-07-25 | 2023-07-25 | 0 | 0%
Assumed Completed | 0% | Project 82 | 2.00 Investment Brief (IB) / SoW Sign Off | Deliverable | Yes | Assumed Completed | 7. Closure | Delay reason shown here | 2023-09-21 17:00 | 2023-09-21 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-09-21 17:00 | 2023-09-21 17:00 | 0 | 0%
Assumed Completed | 0% | Project 172 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-03-26 17:00 | 2024-03-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-10-30 17:00 | 2023-10-30 17:00 | 0 | 0%
Assumed Completed | 0% | Project 172 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-01-20 17:00 | 2025-01-20 17:00 | 0 | 0%
Assumed Completed | 0% | Project 172 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-01-21 17:00 | 2025-01-21 17:00 | 0 | 0%
Assumed Completed | 0% | Project 172 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-01-22 17:00 | 2025-01-22 17:00 | 0 | 0%
Assumed Completed | 0% | Project 172 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-01-23 17:00 | 2025-01-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2024-03-26 17:00 | 2024-03-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.14 Project Management Plan | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-06-18 17:00 | 2024-06-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-01-20 17:00 | 2025-01-20 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-01-21 17:00 | 2025-01-21 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-01-22 17:00 | 2025-01-22 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-01-23 17:00 | 2025-01-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 4.01 Solution Arch Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2023-09-07 17:00 | 2023-09-07 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 82 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-08 17:00 | 2024-10-31 17:00 | -6 | -1.245%
Assumed Completed | 0% | Project 83 | System Architect Discovery & Analysis | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-27 17:00 | 2025-02-27 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | Automation Test Suite Migration ¦ DMBS SGT | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-15 17:00 | 2025-01-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 83 | Pilot Regression Validation and Verification | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-18 17:00 | 2025-02-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 120 | Demonstrations Complete | Deliverable | Yes | Assumed Completed | 6. Implement | Delay reason shown here | 2024-09-23 17:00 | 2024-09-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-02-16 17:00 | 2024-02-16 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 163 | TECHNICAL DEPLOYMENT | Unassigned | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-12-06 17:00 | 2024-12-06 08:00 | -1 | -0.1805%
Assumed Completed | 0% | Project 82 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-05-28 17:00 | 2024-05-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-05-28 17:00 | 2024-05-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-29 17:00 | 2024-04-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 82 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-08 17:00 | 2024-10-25 17:00 | -10 | -2.076%
Assumed Completed | 0% | Project 121 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-03-27 17:00 | 2023-03-27 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | Pilot Test strategy signed off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2023-11-03 08:00 | 2023-11-03 08:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | IIMSS GO LIVE 1 | Deliverable | Go-Live | Assumed Completed | 7. Closure | Delay reason shown here | 2024-06-03 17:00 | 2024-06-03 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | EVALUATE PHASE COMPLETE (GATE 1) | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | MIL: Phase 1 Design & Analysis - complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-04-12 17:00 | 2024-04-12 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | MIL: Phase 1 Build - complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-05-30 17:00 | 2024-05-30 17:00 | 0 | 0%
Assumed Completed | -10% to -5% | Project 163 | SIT Complete | Unassigned | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-10-15 17:00 | 2024-08-30 08:00 | -32 | -5.776%
Assumed Completed | 0% | Project 123 | MIL: Phase 1 Implement - complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-06-14 17:00 | 2024-06-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | Pilot UAT Complete | Deliverable | Yes | Assumed Completed | 7. Closure | Delay reason shown here | 2023-12-11 17:00 | 2023-12-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | MIL: Phase 1 - complete | Deliverable | Go-Live | Assumed Completed | 6. Implement | Delay reason shown here | 2024-06-14 17:00 | 2024-06-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | ANALYSIS & DESIGN PHASE 2 COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | Pilot Build complete | Deliverable | Yes | Assumed Completed | 7. Closure | Delay reason shown here | 2023-11-10 17:00 | 2023-11-10 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 123 | BUILD & TEST PHASE 2 COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-24 17:00 | 2025-03-31 17:00 | -16 | -2.721%
Assumed Completed | -5% to 0% | Project 123 | IMPLEMENT PHASE 2 COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-28 17:00 | 2025-04-15 17:00 | -6 | -1.02%
Assumed Completed | 0% | Project 82 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2023-09-01 17:00 | 2023-09-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | BUILD & TEST PHASE COMPLETE | Governance | Yes | Assumed Completed | 6. Implement | Delay reason shown here | 2024-08-16 17:00 | 2024-08-16 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-08-25 | 2023-08-25 | 0 | 0%
Assumed Completed | 0% | Project 163 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-09-13 17:00 | 2023-09-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 4.11 Security Risk Assessment (Opt) Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2023-10-23 17:00 | 2023-10-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-09-14 17:00 | 2023-09-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | Pilot - Business Requirements Document Signed Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2023-11-09 08:00 | 2023-11-09 08:00 | 0 | 0%
Assumed Completed | 0% | Project 82 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-05-27 17:00 | 2024-05-27 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-11-17 17:00 | 2023-11-17 17:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | 3.21 Final Business Case (FBC) Approved (FIAC) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-04-10 08:00 | 2024-04-10 08:00 | 0 | 0%
Assumed Completed | 0% | Project 163 | Pilot Solution Architecture Design Signed Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2023-12-05 17:00 | 2023-12-05 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 82 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-08 17:00 | 2024-10-11 17:00 | -20 | -4.152%
Assumed Completed | 0% to 5% | Project 163 | 6.05 Service Design & Definition Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-12-02 17:00 | 2024-12-05 08:00 | 2 | 0.361%
Assumed Completed | 0% to 5% | Project 163 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-01 17:00 | 2024-11-08 17:00 | 5 | 0.9025%
Assumed Completed | 0% | Project 163 | Pilot Test Summary Report signed off | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2023-12-14 17:00 | 2023-12-14 17:00 | 0 | 0%
Assumed Completed | -10% to -5% | Project 54 | 3.11 Prelim Solution Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-11-30 17:00 | 2023-09-28 17:00 | -44 | -6.036%
Assumed Completed | 0% | Project 82 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2023-08-01 | 2023-08-01 | 0 | 0%
Assumed Completed | 0% | Project 44 | Implementation SGR Completed | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2023-07-24 | 2023-07-24 | 0 | 0%
Assumed Completed | 0% to 5% | Project 163 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-13 17:00 | 2024-11-14 17:00 | 1 | 0.1805%
Assumed Completed | -5% to 0% | Project 163 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 08:00 | -1 | -0.1805%
Assumed Completed | 0% | Project 144 | TrackAR AnyCloud Development & Test | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-10 17:00 | 2025-01-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | Safecomm AnyCloud Development & Test | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-07 17:00 | 2025-02-07 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 144 | TrackAR AnyCloud Prod Deployment | Deliverable | Go-Live | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-01-29 17:00 | -22 | -4.348%
Assumed Completed | -5% to 0% | Project 144 | Safecomm AnyCloud Prod Deployment | Deliverable | Go-Live | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-20 17:00 | -6 | -1.186%
Assumed Completed | -25% to -10% | Project 54 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2023-09-15 17:00 | 2023-04-05 | -114 | -15.64%
Assumed Completed | N/A | Project 128 | Obtain Sign off on Concept paper | Unassigned | Yes | Assumed Completed | 2. Concept | Delay reason shown here | 2023-02-21
Assumed Completed | 0% to 5% | Project 46 | TMS R4 UAT environment setup- Commencement | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2024-05-31 17:00 | 2024-09-25 17:00 | 82 | 4.787%
Assumed Completed | 0% | Project 163 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | Delay reason shown here | 2024-06-07 17:00 | 2024-06-07 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 163 | BUSINESS GO LIVE | Deliverable | Go-Live | Assumed Completed | 7. Closure | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 08:00 | -1 | -0.1805%
Assumed Completed | 0% | Project 163 | Project Health Check Completed 8 Mar'24 | Governance | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-03-08 08:00 | 2024-03-08 08:00 | 0 | 0%
Assumed Completed | 5% to 10% | Project 46 | Freight Timetable Data (TRIMS) interfaces unit tes | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2023-12-08 17:00 | 2024-05-09 17:00 | 95 | 5.546%
Assumed Completed | -5% to 0% | Project 46 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | Delay reason shown here | 2023-02-20 17:00 | 2023-02-20 | -1 | -0.05838%
Assumed Completed | 0% | Project 120 | Approval for RFP | Deliverable | Yes | Assumed Completed | 6. Implement | Delay reason shown here | 2024-10-10 17:00 | 2024-10-10 17:00 | 0 | 0%
Assumed Completed | 0% | Project 172 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-11 17:00 | 2025-04-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 172 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-03 17:00 | 2025-04-03 17:00 | 0 | 0%
Assumed Completed | 0% | Project 172 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-16 17:00 | 2025-04-16 17:00 | 0 | 0%
Assumed Completed | 0% | Project 172 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-05-01 17:00 | 2025-05-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 172 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-03-11 17:00 | 2025-03-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 44 | Business Requirements signed off | Unassigned | Yes | Assumed Completed | 3. Evaluate | Delay reason shown here | 2022-07-15 | 2022-07-15 | 0 | 0%
Assumed Completed | 0% | Project 172 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-03-17 17:00 | 2025-03-17 17:00 | 0 | 0%
Assumed Completed | -5% to 0% | Project 163 | UAT Complete | Unassigned | Unassigned | Assumed Completed | 7. Closure | Delay reason shown here | 2024-11-29 17:00 | 2024-11-21 08:00 | -7 | -1.264%
Assumed Completed | 0% | Project 57 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-17 17:00 | 2025-04-17 17:00 | 0 | 0%
Assumed Completed | 0% to 5% | Project 57 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-01 17:00 | 2025-04-15 17:00 | 10 | 2.519%
Assumed Completed | -5% to 0% | Project 57 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-17 17:00 | 2025-04-15 17:00 | -2 | -0.5038%
Assumed Completed | 0% to 5% | Project 57 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-17 17:00 | 2025-04-24 17:00 | 3 | 0.7557%
Assumed Completed | 0% to 5% | Project 57 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-17 17:00 | 2025-04-24 17:00 | 3 | 0.7557%
Assumed Completed | 0% to 5% | Project 57 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-17 17:00 | 2025-04-24 17:00 | 3 | 0.7557%
Assumed Completed | 0% to 5% | Project 57 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-17 17:00 | 2025-04-24 17:00 | 3 | 0.7557%
Assumed Completed | 0% to 5% | Project 57 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-17 17:00 | 2025-04-24 17:00 | 3 | 0.7557%
Assumed Completed | 0% to 5% | Project 57 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-01 17:00 | 2025-04-17 17:00 | 12 | 3.023%
Assumed Completed | 0% to 5% | Project 57 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-01 17:00 | 2025-04-17 17:00 | 12 | 3.023%
Assumed Completed | 0% | Project 92 | PCR-236824 Approved for EoT to Aug'25 | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-02-20 17:00 | 2025-02-20 17:00 | 0 | 0%
Assumed Completed | N/A | Project 160 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2025-03-14 17:00
Assumed Completed | N/A | Project 160 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2025-03-31 17:00
Assumed Completed | N/A | Project 161 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2025-03-14 17:00
Assumed Completed | N/A | Project 161 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2025-03-31 17:00
Assumed Completed | 0% | Project 159 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | Delay reason shown here | 2025-03-31 17:00 | 2025-03-31 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | PCR-01 | Governance | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-03 17:00 | 2025-02-03 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Cloud hosting decision paper endorse by GSIT PDA | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Cloud design endorse by GSIT PDA | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-07-18 17:00 | 2024-07-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Network Design & AVD Deployment Solution | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-07 17:00 | 2025-03-07 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | TPS.Plan DEV01 environment handover to SIEMENS | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | TPS.Plan Sandpit environment handover to SIEMENS a | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-23 17:00 | 2024-10-23 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | TPS.Plan TEST environment handover to SIEMENS | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-09 17:00 | 2025-01-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | TPS.Plan DEV02 environment handover to SIEMENS | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-15 17:00 | 2025-01-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | TPS.Plan PREPROD environment readiness | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-11 17:00 | 2025-04-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Integration SAD sign-off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-17 17:00 | 2025-03-17 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Integration solution build | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Procurement service request and engagement | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-13 17:00 | 2024-08-13 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Procurement strategy sign-off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Procurement documents and RFP packing | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Release RFP for tender | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-21 17:00 | 2024-10-21 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Tender evaluation report and approval | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-11 17:00 | 2025-03-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | HCL Briefing & Engagement | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Draft Test Strategy | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 132 | Test Strategy review and sign-off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0%
Assumed Completed | 0% | Project 123 | PCR-03: Extend project to end Jun'25 | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-02-26 17:00 | 2025-02-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | Vendor Onboarding Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 34 | Vendor Solution Design Submitted for Review | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-14 17:00 | 2025-03-14 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | 0% | Project 144 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Assumed Completed | N/A | Project 167 | PCR-01 | Governance | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-02-26 17:00
Assumed Completed | 0% | Project 143 | PCR-01 - inc. Scope, Resource Avail., Time & Cost | Governance | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-11 17:00 | 2025-03-11 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Phase 1 Go Live | Deliverable | Go-Live | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0%
Assumed Completed | N/A | Project 132 | 4.01 Sol'n Architecture Design (SAD) Sign Off 1.1 | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-17 17:00
Assumed Completed | 0% | Project 57 | Kick Off Sprint 1 | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-03-26 17:00 | 2025-03-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | End of Sprint 1 | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-08 17:00 | 2025-04-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | End of Sprint 2 | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-22 17:00 | 2025-04-22 17:00 | 0 | 0%
Assumed Completed | N/A | Project 139 | SQUIZ - CI PORTAL GO LIVE | Deliverable | Go-Live | Assumed Completed | 6. Implement | Delay reason shown here | 2025-04-28 17:00
Assumed Completed | 0% | Project 143 | Kick Off Sprint 1 | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-04 17:00 | 2025-03-04 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | End of Sprint 1 | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-18 17:00 | 2025-03-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | End of Sprint 2 | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | End of Sprint 3 | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-15 17:00 | 2025-04-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | End of Sprint 4 | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-29 17:00 | 2025-04-29 17:00 | 0 | 0%
Assumed Completed | N/A | Project 144 | Safecomm Legacy AWS Decommissioning | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-31 17:00
Assumed Completed | N/A | Project 144 | TrackAR Legacy AWS Decommissioning | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-31 17:00
Assumed Completed | 0% | Project 98 | Vendor SoW Sign Off by GSIT | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-27 17:00 | 2025-03-27 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | Sprint Plan | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-08 17:00 | 2025-04-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | Sprint Retrospective | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-08 17:00 | 2025-04-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | Sprint Review | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-08 17:00 | 2025-04-08 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | Sprint Plan | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-22 17:00 | 2025-04-22 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | Sprint Review | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-22 17:00 | 2025-04-22 17:00 | 0 | 0%
Assumed Completed | 0% | Project 57 | Sprint Retrospective | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-22 17:00 | 2025-04-22 17:00 | 0 | 0%
Assumed Completed | 0% | Project 121 | PCR-03: Extend project to Oct'25 (Approved 26/3) | Governance | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-03-26 17:00 | 2025-03-26 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-18 17:00 | 2025-03-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-18 17:00 | 2025-03-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-03-18 17:00 | 2025-03-18 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-15 17:00 | 2025-04-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-15 17:00 | 2025-04-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-15 17:00 | 2025-04-15 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Sprint Plan | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-29 17:00 | 2025-04-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Sprint Review | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-29 17:00 | 2025-04-29 17:00 | 0 | 0%
Assumed Completed | 0% | Project 143 | Sprint Retrospective | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-29 17:00 | 2025-04-29 17:00 | 0 | 0%
Assumed Completed | N/A | Project 139 | CI PORTAL UAT COMPLETE | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-03-28 17:00
Assumed Completed | N/A | Project 139 | CI Portal Transitional Support to GSIT from Corp | Deliverable | Unassigned | Assumed Completed | 6. Implement | Delay reason shown here | 2025-03-31 17:00
Assumed Completed | -5% to 0% | Project 72 | PCR-0001 - Extension to Oct'25 | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | Delay reason shown here | 2025-04-02 17:00 | 2025-04-02 08:00 | -1 | -0.4065%
Prepare for Closure | -25% to -10% | Project 163 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Prepare for Closure | 7. Closure | Delay reason shown here | 2025-05-16 17:00 | 2025-02-14 17:00 | -62 | -11.19%
Prepare for Closure | -25% to -10% | Project 163 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Prepare for Closure | 7. Closure | Delay reason shown here | 2025-05-16 17:00 | 2025-02-14 17:00 | -62 | -11.19%
Prepare for Closure | <-25% | Project 55 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Prepare for Closure | 4. Analyse & Design | Delay reason shown here | 2025-05-01 08:00 | 2024-02-05 17:00 | -303 | -69.34%
Prepare for Closure | <-25% | Project 55 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Prepare for Closure | 4. Analyse & Design | Delay reason shown here | 2025-05-01 08:00 | 2024-02-09 17:00 | -299 | -68.42%
Prepare for Closure | -25% to -10% | Project 163 | 7.03 Closure Checklist & Memo Sign Off | Deliverable | Gate 3 Approval | Prepare for Closure | 7. Closure | Delay reason shown here | 2025-05-16 17:00 | 2025-02-14 17:00 | -62 | -11.19%
Prepare for Closure | -25% to -10% | Project 163 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Prepare for Closure | 7. Closure | Delay reason shown here | 2025-05-16 17:00 | 2025-02-14 17:00 | -62 | -11.19%
Completed | 0% | Project 151 | CIS Applications(RTTA, PMG)Migration Establishment | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-12-19 08:00 | 2023-12-19 08:00 | 0 | 0%
Completed | 0% | Project 151 | CIS Migrt. Scratch &Design Comple | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2024-04-02 08:00 | 2024-04-02 08:00 | 0 | 0%
Completed | 0% | Project 151 | CIS Migration Analysis Complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2024-02-19 08:00 | 2024-02-19 08:00 | 0 | 0%
Completed | 0% | Project 151 | CIS Migration Discovery Complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2024-01-31 08:00 | 2024-01-31 08:00 | 0 | 0%
Completed | 0% | Project 151 | Azure ASEv3 Platform (including Security)-complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2024-04-30 08:00 | 2024-04-30 08:00 | 0 | 0%
Completed | 0% | Project 151 | Integration with AnyCloud Accounts - complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2024-04-02 08:00 | 2024-04-02 08:00 | 0 | 0%
Completed | 0% | Project 151 | Security Alerts integrations - complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2024-02-19 08:00 | 2024-02-19 08:00 | 0 | 0%
Completed | 0% | Project 151 | Security Alerts integrations | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-08-01 08:00 | 2023-08-01 08:00 | 0 | 0%
Completed | 0% | Project 151 | Integration with AnyCloud Subscription - complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2024-04-02 08:00 | 2024-04-02 08:00 | 0 | 0%
Completed | 0% | Project 151 | Security Alerts integrations - complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2024-02-19 08:00 | 2024-02-19 08:00 | 0 | 0%
Completed | 0% | Project 151 | Establish Tagging Standard - complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0%
Completed | 0% | Project 151 | Define/Identify Governance Reports - complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2024-02-19 08:00 | 2024-02-19 08:00 | 0 | 0%
Completed | -10% to -5% | Project 106 | Production migration | Deliverable | Go-Live | Completed | 7. Closure | Delay reason shown here | 2024-05-27 08:00 | 2024-04-24 17:00 | -21 | -5.385%
Completed | -5% to 0% | Project 106 | Data Analysis and Extraction | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-04-26 08:00 | 2024-04-19 08:00 | -4 | -1.026%
Completed | -5% to 0% | Project 106 | Migration Scripts Development and build | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-05-07 08:00 | 2024-04-18 08:00 | -12 | -3.077%
Completed | -5% to 0% | Project 106 | UAT Complete | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-05-17 08:00 | 2024-04-26 08:00 | -15 | -3.846%
Completed | 0% | Project 106 | P20 Cost Estimate Approved | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-01-11 08:00 | 2024-01-11 08:00 | 0 | 0%
Completed | 0% | Project 106 | PSAD signed off | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-01-31 08:00 | 2024-01-31 08:00 | 0 | 0%
Completed | -5% to 0% | Project 106 | Vendor On Boarding Complete | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-02-19 08:00 | 2024-01-29 08:00 | -15 | -3.846%
Completed | -5% to 0% | Project 106 | Solution Architecture Design Signed Off | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-02-16 08:00 | 2024-01-29 08:00 | -14 | -3.59%
Completed | -10% to -5% | Project 106 | Access provisioning | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-03-15 08:00 | 2024-01-25 08:00 | -35 | -8.974%
Completed | -5% to 0% | Project 106 | Analysis of security and Acces control mapping | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-04-11 08:00 | 2024-04-02 08:00 | -7 | -1.795%
Completed | 0% | Project 101 | Evaluate- PMP | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-03-22 08:00 | 2024-03-22 08:00 | 0 | 0%
Completed | 0% | Project 101 | Evaluate- BRD | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-03-19 17:00 | 2024-03-19 17:00 | 0 | 0%
Completed | 0% | Project 132 | Complete Tender Evaluation | Deliverable | Unassigned | Completed | 3. Evaluate | Delay reason shown here | 2022-10-12 08:00 | 2022-10-12 08:00 | 0 | 0%
Completed | 0% | Project 132 | Release RFP | Deliverable | Unassigned | Completed | 3. Evaluate | Delay reason shown here | 2022-05-02 08:00 | 2022-05-02 08:00 | 0 | 0%
Completed | 0% | Project 132 | Limited Trial Evaluation Report | Deliverable | Unassigned | Completed | 3. Evaluate | Delay reason shown here | 2023-05-11 08:00 | 2023-05-11 08:00 | 0 | 0%
Completed | 0% | Project 132 | Finalise Funding Approval for Stage 1 - FIAC | Governance | Unassigned | Completed | 3. Evaluate | Delay reason shown here | 2023-12-22 08:00 | 2023-12-22 08:00 | 0 | 0%
Completed | 0% | Project 132 | Present P20 IT Estimation to Stakeholders | Deliverable | Unassigned | Completed | 3. Evaluate | Delay reason shown here | 2022-06-08 08:00 | 2022-06-08 08:00 | 0 | 0%
Completed | 0% | Project 132 | Conceptual Architecture Design | Deliverable | Unassigned | Completed | 3. Evaluate | Delay reason shown here | 2023-09-14 08:00 | 2023-09-14 08:00 | 0 | 0%
Completed | 0% | Project 132 | Present Conceptual Architecture to TAC | Governance | Unassigned | Completed | 3. Evaluate | Delay reason shown here | 2023-09-28 08:00 | 2023-09-28 08:00 | 0 | 0%
Completed | 0% | Project 132 | Present Conceptual Architecture to GSIT PDA | Governance | Unassigned | Completed | 3. Evaluate | Delay reason shown here | 2023-11-02 08:00 | 2023-11-02 08:00 | 0 | 0%
Completed | 0% | Project 132 | Complete IT Delivery Org Design | Deliverable | Unassigned | Completed | 3. Evaluate | Delay reason shown here | 2023-09-27 08:00 | 2023-09-27 08:00 | 0 | 0%
Completed | 0% | Project 132 | Present IT Delivery Org to Stakeholders | Governance | Unassigned | Completed | 3. Evaluate | Delay reason shown here | 2023-10-10 08:00 | 2023-10-10 08:00 | 0 | 0%
Completed | 0% | Project 122 | Raise Change Request | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-12-18 08:00 | 2023-12-15 17:00 | 0 | 0%
Completed | 0% | Project 122 | Test Phase UAT | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-01-16 17:00 | 2024-01-16 17:00 | 0 | 0%
Completed | 0% | Project 122 | Business Training | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-01-29 08:00 | 2024-01-25 17:00 | 0 | 0%
Completed | 0% | Project 109 | Test completion report signed off | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2023-12-05 17:00 | 2023-12-05 17:00 | 0 | 0%
Completed | 0% | Project 109 | Implement- SGR Completed | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2023-12-05 17:00 | 2023-12-05 17:00 | 0 | 0%
Completed | 0% | Project 109 | Closure phase complete | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2023-12-15 17:00 | 2023-12-15 17:00 | 0 | 0%
Completed | 0% | Project 109 | Business Go-Live | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2023-12-05 17:00 | 2023-12-05 17:00 | 0 | 0%
Completed | 0% | Project 56 | Create project delivery milestone | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-02-09 08:00 | 2024-02-09 08:00 | 0 | 0%
Completed | 0% | Project 56 | Analysis & Design, BRD, SAD completion | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0%
Completed | 0% | Project 56 | Solution Detailed design/SOW/Procurement | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0%
Completed | 0% | Project 56 | Development | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-05-03 08:00 | 2024-05-03 08:00 | 0 | 0%
Completed | 0% | Project 56 | SIT | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-06-05 17:00 | 2024-06-05 17:00 | 0 | 0%
Completed | 0% | Project 56 | UAT | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-06-19 17:00 | 2024-06-19 17:00 | 0 | 0%
Completed | 0% | Project 56 | GO-LIVE | Deliverable | Go-Live | Completed | 6. Implement | Delay reason shown here | 2024-06-27 08:00 | 2024-06-27 08:00 | 0 | 0%
Completed | 0% | Project 56 | Warranty and Acceptance | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-08-09 17:00 | 2024-08-09 17:00 | 0 | 0%
Completed | 0% | Project 42 | Analysis & Design, BRD signoff | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-12-12 08:00 | 2023-12-12 08:00 | 0 | 0%
Completed | 0% | Project 42 | SOW (WIPRO), PO/Procurement completion | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-03-22 17:00 | 2024-03-22 17:00 | 0 | 0%
Completed | 0% | Project 42 | GO LIVE Part 1 -6 Sep now 10 Sep to accom DCV Proj | Deliverable | Go-Live | Completed | 7. Closure | Delay reason shown here | 2024-09-24 17:00 | 2024-09-24 17:00 | 0 | 0%
Completed | 0% | Project 56 | Reporting requrements signoff | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-05-10 08:00 | 2024-05-10 08:00 | 0 | 0%
Completed | 0% | Project 56 | Reporting Development Resource Assignment Complete | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-06-14 08:00 | 2024-06-14 08:00 | 0 | 0%
Completed | 0% | Project 56 | eMFT server feed business engagement E STATE AUTOM | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-05-24 08:00 | 2024-05-24 08:00 | 0 | 0%
Completed | N/A | Project 33 | Supplier Engagement Complete | Unassigned | Unassigned | Completed | Unassigned | Delay reason shown here | 2024-04-05 17:00
Completed | N/A | Project 33 | Build Complete | Unassigned | Unassigned | Completed | Unassigned | Delay reason shown here | 2024-05-08 08:00
Completed | 0% | Project 166 | Contract issued and Executed | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-08-14 17:00 | 2024-08-14 17:00 | 0 | 0%
Completed | 0% | Project 101 | EOI Closure | Deliverable | Yes | Completed | 7. Closure | Delay reason shown here | 2024-05-07 08:00 | 2024-05-07 08:00 | 0 | 0%
Completed | 0% | Project 101 | Demonstrations Complete | Deliverable | Yes | Completed | 7. Closure | Delay reason shown here | 2024-08-09 17:00 | 2024-08-09 17:00 | 0 | 0%
Completed | 0% | Project 101 | Decision | Deliverable | Yes | Completed | 7. Closure | Delay reason shown here | 2024-09-16 17:00 | 2024-09-16 17:00 | 0 | 0%
Completed | 0% | Project 155 | UAT Sign Off | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-07-08 17:00 | 2024-07-08 17:00 | 0 | 0%
Completed | 0% | Project 155 | GO LIVE (Technical) | Deliverable | Go-Live | Completed | 7. Closure | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Completed | 0% | Project 92 | 2.00 Investment Brief (IB) / SoW Sign Off | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-03-13 17:00 | 2024-03-13 17:00 | 0 | 0%
Completed | 0% | Project 92 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 92 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 92 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 92 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 121 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-11-15 08:00 | 2024-11-15 08:00 | 0 | 0%
Completed | 0% | Project 42 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0%
Completed | 0% | Project 42 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0%
Completed | 0% | Project 42 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2025-02-26 17:00 | 2025-02-26 17:00 | 0 | 0%
Completed | 0% | Project 42 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2025-02-26 17:00 | 2025-02-26 17:00 | 0 | 0%
Completed | 0% | Project 42 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0%
Completed | 0% | Project 42 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-08-29 17:00 | 2024-08-29 17:00 | 0 | 0%
Completed | 0% | Project 42 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0%
Completed | 0% | Project 42 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0%
Completed | 0% | Project 42 | HYB6.04 Release Retrospective Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-09-02 08:00 | 2024-09-02 08:00 | 0 | 0%
Completed | 0% | Project 42 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0%
Completed | 0% | Project 42 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0%
Completed | 0% | Project 42 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Completed | 7. Closure | Delay reason shown here | 2025-02-19 17:00 | 2025-02-19 17:00 | 0 | 0%
Completed | 0% | Project 155 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Completed | 0% | Project 155 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0%
Completed | 0% | Project 56 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Completed | 6. Implement | Delay reason shown here | 2024-08-12 17:00 | 2024-08-12 17:00 | 0 | 0%
Completed | 0% | Project 56 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Completed | 6. Implement | Delay reason shown here | 2024-08-14 17:00 | 2024-08-14 17:00 | 0 | 0%
Completed | 0% | Project 56 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Completed | 6. Implement | Delay reason shown here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0%
Completed | 0% | Project 56 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Completed | 6. Implement | Delay reason shown here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0%
Completed | 0% | Project 42 | GO LIVE Part 2 (WIPRO Reconciliation Work) | Deliverable | Go-Live | Completed | 7. Closure | Delay reason shown here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0%
Completed | 0% | Project 137 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Completed | 4. Analyse & Design | Delay reason shown here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0%
Completed | 0% | Project 137 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Completed | 4. Analyse & Design | Delay reason shown here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0%
Completed | 0% | Project 42 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-04-05 17:00 | 2024-04-05 17:00 | 0 | 0%
Completed | 0% | Project 42 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-04-05 17:00 | 2024-04-05 17:00 | 0 | 0%
Completed | 0% | Project 42 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-04-05 17:00 | 2024-04-05 17:00 | 0 | 0%
Completed | 0% | Project 42 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-04-05 17:00 | 2024-04-05 17:00 | 0 | 0%
Completed | 0% | Project 42 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-04-05 17:00 | 2024-04-05 17:00 | 0 | 0%
Completed | -5% to 0% | Project 157 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Completed | 4. Analyse & Design | Delay reason shown here | 2025-04-04 17:00 | 2025-02-27 17:00 | -26 | -3.725%
Completed | 0% | Project 168 | MIL: Analysis & Design phase - complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 168 | MIL: Seed funding released | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 168 | MIL: Concept phase - complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 168 | MIL: Evaluate phase - complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 168 | MIL: Build& Test phase - complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 168 | MIL: Go Live | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 168 | MIL: Implement phase - complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 168 | MIL: Procurement contract awarded | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 168 | MIL: Project closed | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 92 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0%
Completed | 0% | Project 92 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0%
Completed | 0% | Project 92 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0%
Completed | 0% | Project 92 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0%
Completed | 0% | Project 92 | 3.05 Business Impact Assessment Sign Off MTAP | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0%
Completed | 0% | Project 92 | 3.06 Business Requirements Document Sign Off MTAP | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-08-09 17:00 | 2024-08-09 17:00 | 0 | 0%
Completed | 0% | Project 92 | EVALUATE END (MY TIME & PAY) | Governance | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-09-06 17:00 | 2024-09-06 17:00 | 0 | 0%
Completed | 0% | Project 144 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-10-23 17:00 | 2024-10-23 17:00 | 0 | 0%
Completed | 0% | Project 98 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-03-26 17:00 | 2024-03-26 17:00 | 0 | 0%
Completed | 0% | Project 147 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 92 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2025-01-10 17:00 | 2025-01-10 17:00 | 0 | 0%
Completed | 0% | Project 92 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Completed | N/A | Project 92 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 92 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0%
Completed | N/A | Project 92 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 92 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-09-06 17:00 | 2024-09-06 17:00 | 0 | 0%
Completed | N/A | Project 92 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 92 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-09-06 17:00 | 2024-09-06 17:00 | 0 | 0%
Completed | 0% | Project 166 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | Delay reason shown here | 2024-09-16 17:00 | 2024-09-16 17:00 | 0 | 0%
Completed | N/A | Project 166 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here
Completed | 0% | Project 166 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-11-18 17:00 | 2024-11-18 17:00 | 0 | 0%
Completed | N/A | Project 166 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here
Completed | 0% | Project 166 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Completed | 0% | Project 166 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Completed | 0% | Project 166 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Completed | 0% | Project 166 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-11-20 17:00 | 2024-11-20 17:00 | 0 | 0%
Completed | 0% | Project 166 | BUSINESS GO LIVE | Deliverable | Go-Live | Completed | 7. Closure | Delay reason shown here | 2024-11-22 17:00 | 2024-11-22 17:00 | 0 | 0%
Completed | 0% | Project 166 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-12-19 17:00 | 2024-12-19 17:00 | 0 | 0%
Completed | 0% | Project 166 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2025-01-31 08:00 | 2025-01-31 08:00 | 0 | 0%
Completed | 0% | Project 166 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0%
Completed | 0% | Project 166 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0%
Completed | 0% | Project 166 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0%
Completed | 0% | Project 92 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Completed | 0% | Project 92 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-10-17 17:00 | 2024-10-17 17:00 | 0 | 0%
Completed | 0% | Project 92 | EVALUATE END (MY TIME & PAY) | Governance | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-10-17 17:00 | 2024-10-17 17:00 | 0 | 0%
Completed | 0% | Project 92 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Completed | 0% | Project 92 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-17 17:00 | 2024-10-17 17:00 | 0 | 0%
Completed | N/A | Project 92 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 92 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Completed | 0% | Project 92 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0%
Completed | 0% | Project 92 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0%
Completed | N/A | Project 92 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 92 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 92 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-09-26 17:00 | 2024-09-26 17:00 | 0 | 0%
Completed | 0% | Project 92 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-09-26 17:00 | 2024-09-26 17:00 | 0 | 0%
Completed | 0% | Project 139 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0%
Completed | 0% | Project 139 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Completed | 0% | Project 139 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Completed | 0% | Project 139 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Completed | 0% | Project 139 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Completed | N/A | Project 139 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 139 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0%
Completed | 0% | Project 139 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Completed | 0% | Project 139 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0%
Completed | 0% | Project 139 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Completed | 0% | Project 139 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0%
Completed | -10% to -5% | Project 139 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2025-03-19 17:00 | 2025-02-28 17:00 | -13 | -5.882%
Completed | 0% | Project 139 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Completed | 0% | Project 139 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-11-25 17:00 | 2024-11-25 17:00 | 0 | 0%
Completed | 0% | Project 139 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-22 17:00 | 2024-10-22 17:00 | 0 | 0%
Completed | N/A | Project 139 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 139 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-09-12 17:00 | 2024-09-12 17:00 | 0 | 0%
Completed | -10% to -5% | Project 139 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Completed | 6. Implement | Delay reason shown here | 2025-03-21 17:00 | 2025-02-28 17:00 | -15 | -6.787%
Completed | -5% to 0% | Project 139 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2025-03-03 17:00 | 2025-02-28 17:00 | -1 | -0.4525%
Completed | 0% | Project 42 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0%
Completed | 0% | Project 42 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0%
Completed | 0% | Project 42 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0%
Completed | 0% | Project 42 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0%
Completed | 0% | Project 42 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0%
Completed | 0% | Project 42 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0%
Completed | 0% | Project 42 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0%
Completed | 0% | Project 42 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0%
Completed | 0% | Project 42 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0%
Completed | 0% | Project 42 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0%
Completed | 0% | Project 42 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0%
Completed | 0% | Project 42 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0%
Completed | 0% | Project 42 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0%
Completed | 0% | Project 42 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0%
Completed | 0% | Project 42 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0%
Completed | 0% | Project 42 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-04-05 17:00 | 2024-04-05 17:00 | 0 | 0%
Completed | 0% | Project 42 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0%
Completed | 0% | Project 42 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0%
Completed | 0% | Project 42 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-06-03 17:00 | 2024-06-03 17:00 | 0 | 0%
Completed | 0% | Project 42 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-06-11 17:00 | 2024-06-11 17:00 | 0 | 0%
Completed | 0% | Project 42 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-09-03 17:00 | 2024-09-03 17:00 | 0 | 0%
Completed | 0% | Project 42 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-06-28 08:00 | 2024-06-28 08:00 | 0 | 0%
Completed | 0% | Project 42 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0%
Completed | 0% | Project 42 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-09-03 17:00 | 2024-09-03 17:00 | 0 | 0%
Completed | 0% | Project 42 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-06-03 17:00 | 2024-06-03 17:00 | 0 | 0%
Completed | 0% | Project 42 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-09-18 17:00 | 2024-09-18 17:00 | 0 | 0%
Completed | 0% | Project 42 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-09-10 17:00 | 2024-09-10 17:00 | 0 | 0%
Completed | 0% | Project 140 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-01-23 17:00 | 2023-01-23 17:00 | 0 | 0%
Completed | N/A | Project 140 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 140 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 140 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 140 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 140 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 140 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-28 17:00 | 2024-10-28 17:00 | 0 | 0%
Completed | 0% | Project 140 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Completed | 0% | Project 140 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-09-27 17:00 | 2024-09-27 17:00 | 0 | 0%
Completed | 0% | Project 140 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-09-09 17:00 | 2024-09-09 17:00 | 0 | 0%
Completed | N/A | Project 140 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 140 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 140 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 140 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 140 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 140 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 140 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Completed | N/A | Project 140 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 140 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-09-19 17:00 | 2024-09-19 17:00 | 0 | 0%
Completed | 0% | Project 140 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Completed | N/A | Project 140 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 140 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 140 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Completed | N/A | Project 140 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 140 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Completed | 0% | Project 140 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-31 08:00 | 2024-10-31 08:00 | 0 | 0%
Completed | 0% | Project 140 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-03 17:00 | 2024-10-03 17:00 | 0 | 0%
Completed | 0% | Project 140 | 6.01 Training Docs & App H'over Checklist Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0%
Completed | 0% | Project 140 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0%
Completed | N/A | Project 140 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | N/A | Project 140 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 92 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off MTAP | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-08-06 17:00 | 2024-08-06 17:00 | 0 | 0%
Completed | N/A | Project 92 | 3.20 Test Strategy Sign Off MTAP | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 98 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Completed | 3. Evaluate | Delay reason shown here | 2025-01-22 17:00 | 2025-01-22 17:00 | 0 | 0%
Completed | 0% | Project 98 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Completed | 3. Evaluate | Delay reason shown here | 2025-01-24 17:00 | 2025-01-24 17:00 | 0 | 0%
Completed | 0% | Project 59 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 59 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 59 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 59 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 0% | Project 59 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0%
Completed | 5% to 10% | Project 59 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-11-07 17:00 | 2024-11-28 17:00 | 15 | 5.597%
Completed | 0% | Project 59 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-11-22 17:00 | 2024-11-22 17:00 | 0 | 0%
Completed | -25% to -10% | Project 59 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2025-03-14 17:00 | 2024-11-29 17:00 | -64 | -23.88%
Completed | 0% | Project 59 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0%
Completed | 0% | Project 59 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-11-21 17:00 | 2024-11-21 17:00 | 0 | 0%
Completed | N/A | Project 169 | Project Team Kick Off | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-09-30 17:00
Completed | N/A | Project 169 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-11-06 17:00
Completed | N/A | Project 169 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-11-06 17:00
Completed | N/A | Project 169 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-11-06 17:00
Completed | N/A | Project 169 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2024-11-06 17:00
Completed | N/A | Project 169 | SIT Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2025-04-16 08:00
Completed | N/A | Project 169 | Code Migration / Setup Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2025-04-11 17:00
Completed | N/A | Project 169 | Build VIM Instances existing Azure Infra Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2025-02-14 08:00
Completed | N/A | Project 169 | Vendor PO Release & Onboarding Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-11-15 17:00
Completed | 0% | Project 155 | Briefing Note | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-07-01 | 2022-07-01 | 0 | 0%
Completed | 0% | Project 155 | PACT | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-07-01 | 2022-07-01 | 0 | 0%
Completed | 0% | Project 101 | Concept SGR Completed | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-11-30 | 2022-11-30 | 0 | 0%
Completed | 0% | Project 155 | Concept SGR Completed | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-07-01 | 2022-07-01 | 0 | 0%
Completed | 0% | Project 151 | Program Schedule | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 08:00 | 2023-11-30 08:00 | 0 | 0%
Completed | 0% | Project 101 | PACT | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-09-26 | 2022-09-26 | 0 | 0%
Completed | 0% | Project 109 | SAD signed off | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-12-09 17:00 | 2022-12-09 17:00 | 0 | 0%
Completed | 0% | Project 164 | Test strategy and plan signed off | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-04-20 | 2023-04-20 | 0 | 0%
Completed | 0% | Project 101 | Investment Brief | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-11-30 | 2022-11-30 | 0 | 0%
Completed | 0% | Project 151 | Business Case Issued for Approval | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-15 08:00 | 2023-11-15 08:00 | 0 | 0%
Completed | N/A | Project 56 | PMP signed off | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here
Completed | 0% | Project 164 | Analyse and Design Phase complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-06-05 | 2023-06-05 | 0 | 0%
Completed | 0% | Project 151 | WBS Set up | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-08-31 08:00 | 2023-08-31 08:00 | 0 | 0%
Completed | 0% | Project 109 | Test strategy and plan signed off | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-10-13 17:00 | 2023-10-13 17:00 | 0 | 0%
Completed | 0% | Project 46 | Present DTIP HL report to Customer Ops and DSP | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2020-10-20 | 2020-10-20 | 0 | 0%
Completed | 0% | Project 101 | Test completion report signed off | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-04-09 17:00 | 2024-04-09 17:00 | 0 | 0%
Completed | 0% | Project 165 | Endorsement to proceed with contract - TCOPS Steer | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2023-02-13 | 2023-02-13 | 0 | 0%
Completed | 0% | Project 46 | TMS R3 TEST (SIT) environment setup - Commencement | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-07-03 | 2023-07-03 | 0 | 0%
Completed | 0% | Project 165 | FIP - Approval to award contract | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2023-02-27 | 2023-02-27 | 0 | 0%
Completed | 0% | Project 109 | Service design signed off | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-07-21 | 2023-07-21 | 0 | 0%
Completed | 0% | Project 46 | CTM interfaces (Passenger TT) - R3 - Release data | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2021-02-08 | 2021-02-08 | 0 | 0%
Completed | 0% | Project 109 | Analyse and Design Phase complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-10-13 17:00 | 2023-10-13 17:00 | 0 | 0%
Completed | 0% | Project 46 | Execute TMS R3 SIT test cases- commencement | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-07-03 | 2023-07-03 | 0 | 0%
Completed | 0% | Project 140 | PMP signed off | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-02-15 | 2023-02-15 | 0 | 0%
Completed | 0% | Project 122 | Obtain Sign off on Concept paper | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2022-09-01 | 2022-09-01 | 0 | 0%
Completed | 0% | Project 101 | Business Requirements Document | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-12-23 | 2022-12-23 | 0 | 0%
Completed | 0% | Project 151 | Azure ASEv3 Platform (including Security) - start | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0%
Completed | 0% | Project 121 | UAT Complete | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2024-02-29 17:00 | 2024-02-29 17:00 | 0 | 0%
Completed | 0% | Project 101 | Project Management Plan | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-01-27 | 2023-01-27 | 0 | 0%
Completed | 0% | Project 155 | P1S2.1 Asset Association Design & Analysis Complet | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-03-16 | 2023-03-16 | 0 | 0%
Completed | 0% | Project 101 |  | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-03-20 08:00 | 2024-03-20 08:00 | 0 | 0%
Completed | 0% | Project 151 | Integration with AnyCloud Accounts Data Streams | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-07-17 08:00 | 2023-07-17 08:00 | 0 | 0%
Completed | 0% | Project 46 | TMS R3 UAT interface testing & support- Commenceme | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-08-09 | 2023-08-09 | 0 | 0%
Completed | 0% | Project 151 | Security Alerts integrations | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-07-17 08:00 | 2023-07-17 08:00 | 0 | 0%
Completed | 0% | Project 164 | Go Live complete | Unassigned | Go-Live | Completed | 7. Closure | Delay reason shown here | 2024-04-02 08:00 | 2024-04-02 08:00 | 0 | 0%
Completed | 0% | Project 46 | Test Plan | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-06-20 | 2023-06-20 | 0 | 0%
Completed | 0% | Project 165 | Negotiation Strategy Completed and Approved | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2022-12-05 | 2022-12-05 | 0 | 0%
Completed | 0% | Project 151 | Applications ITSI Dashboards (FY24 Progress. task) | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-10-20 17:00 | 2023-10-20 17:00 | 0 | 0%
Completed | 0% | Project 122 | Business Requirements signed off | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2022-09-14 | 2022-09-14 | 0 | 0%
Completed | 0% | Project 46 | SAD | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-02-20 | 2023-02-20 | 0 | 0%
Completed | 0% | Project 165 | Awareness to Steer Co regarding decision to procee | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2022-12-07 | 2022-12-07 | 0 | 0%
Completed | 0% | Project 151 | Integration with AnyCloud Subscription Data Stream | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-10-23 08:00 | 2023-10-23 08:00 | 0 | 0%
Completed | 0% | Project 101 |  | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-03-28 08:00 | 2024-03-28 08:00 | 0 | 0%
Completed | 0% | Project 109 | Build and Test phase complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-10-27 17:00 | 2023-10-27 17:00 | 0 | 0%
Completed | 0% | Project 151 | Applications ITSI Dashboards (FY24 Progress. task) | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-10-20 17:00 | 2023-10-20 17:00 | 0 | 0%
Completed | 0% | Project 46 | Gather estimation for PROD data access solution | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2022-09-08 | 2022-09-08 | 0 | 0%
Completed | 0% | Project 151 | Establish Tagging Standard | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-10-23 08:00 | 2023-10-23 08:00 | 0 | 0%
Completed | 0% | Project 151 | Define/Identify Governance Reports and Process | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-10-20 17:00 | 2023-10-20 17:00 | 0 | 0%
Completed | 0% to 5% | Project 46 | TMS R3 Go-live (TBC) | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2024-03-28 17:00 | 2024-05-20 17:00 | 34 | 1.985%
Completed | 0% | Project 164 | Implementation phase complete | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-04-02 08:00 | 2024-04-02 08:00 | 0 | 0%
Completed | -25% to -10% | Project 55 | SIT Complete | Unassigned | Yes | Completed | 4. Analyse & Design | Delay reason shown here | 2024-05-24 08:00 | 2023-12-22 08:00 | -96 | -21.97%
Completed | 0% | Project 151 | Implements across AWS & Azure Anycloud Accts/ Subs | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-10-20 17:00 | 2023-10-20 17:00 | 0 | 0%
Completed | 0% | Project 164 | Closure phase complete | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-04-15 08:00 | 2024-04-15 08:00 | 0 | 0%
Completed | -25% to -10% | Project 55 | Build complete | Unassigned | Yes | Completed | 4. Analyse & Design | Delay reason shown here | 2024-05-24 08:00 | 2023-12-22 08:00 | -96 | -21.97%
Completed | 0% | Project 55 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Unassigned | Completed | 4. Analyse & Design | Delay reason shown here | 2023-09-25 17:00 | 2023-09-25 17:00 | 0 | 0%
Completed | 0% | Project 122 | Production go-live | Deliverable | Go-Live | Completed | 6. Implement | Delay reason shown here | 2024-02-02 17:00 | 2024-02-02 17:00 | 0 | 0%
Completed | 0% | Project 122 | Concept Phase Complete | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2023-03-03 | 2023-03-03 | 0 | 0%
Completed | 0% | Project 55 | 3.04 PACT Sign Off | Deliverable | Unassigned | Completed | 4. Analyse & Design | Delay reason shown here | 2023-09-08 17:00 | 2023-09-08 17:00 | 0 | 0%
Completed | 0% | Project 152 | Review and Update Critical Application Business Ow | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2023-10-20 08:00 | 2023-10-20 08:00 | 0 | 0%
Completed | 0% | Project 46 | TMS R4 TEST (SIT) environment setup - Complete | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2024-07-02 17:00 | 2024-07-02 17:00 | 0 | 0%
Completed | 0% | Project 55 | Solution Architecture Design Signed Off | Unassigned | Unassigned | Completed | 4. Analyse & Design | Delay reason shown here | 2023-09-07 17:00 | 2023-09-07 17:00 | 0 | 0%
Completed | 0% | Project 122 | Development Phase | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2023-12-15 17:00 | 2023-12-15 17:00 | 0 | 0%
Completed | 0% | Project 155 | P1S6.2 Read & Understood into UAT | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-02-29 08:00 | 2024-02-29 08:00 | 0 | 0%
Completed | 0% | Project 121 | TLA Technical Design Completed | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-01-30 | 2023-01-30 | 0 | 0%
Completed | 0% | Project 56 | Investment Brief Sign-off | Deliverable | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2022-11-15 | 2022-11-15 | 0 | 0%
Completed | 0% | Project 55 | Analyse and Design SGR Completed | Unassigned | Unassigned | Completed | 4. Analyse & Design | Delay reason shown here | 2023-09-15 17:00 | 2023-09-15 17:00 | 0 | 0%
Completed | 0% | Project 46 | TMS R3 Test summary report (SIT)- Complete | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-07-24 | 2023-07-24 | 0 | 0%
Completed | 0% | Project 155 | P1S3.3a Missing Crew | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-07-01 | 2022-07-01 | 0 | 0%
Completed | 0% | Project 151 | TCSS - Digital Mobility Migration Establishment | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0%
Completed | 0% | Project 165 | Phase 0 - Value Committment for All - Acceptance | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-27 08:00 | 2023-11-27 08:00 | 0 | 0%
Completed | 0% | Project 151 | TCSS Migration Analysis Complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2024-02-28 08:00 | 2024-02-28 08:00 | 0 | 0%
Completed | 0% | Project 165 | P1a - VC for R&S - MVP & Optimisation | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2024-01-31 17:00 | 2024-01-31 17:00 | 0 | 0%
Completed | 0% | Project 82 | Technical deployment | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0%
Completed | 0% | Project 46 | TMS R4 UAT environment setup- Completed | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0%
Completed | 0% | Project 46 | DTIP- R4 - Governance Forums and ADRB Endorsement | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2021-06-17 | 2021-06-17 | 0 | 0%
Completed | 0% | Project 155 | Drop 5 Two Way TA (scope added) into UAT | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-02-29 08:00 | 2024-02-29 08:00 | 0 | 0%
Completed | 0% | Project 55 | Raise ICT Release Request | Unassigned | Unassigned | Completed | 4. Analyse & Design | Delay reason shown here | 2023-07-19 17:00 | 2023-07-19 17:00 | 0 | 0%
Completed | 0% | Project 46 | TMS R4 TIBCO Interface contracts- Complete | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-08-28 | 2023-08-28 | 0 | 0%
Completed | 0% | Project 155 | Drop 1 One Way TA no interfaces | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-03-07 | 2022-03-07 | 0 | 0%
Completed | 0% | Project 122 | Deploy in SandPit | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-12-20 17:00 | 2023-12-20 17:00 | 0 | 0%
Completed | 0% | Project 155 | Drop 2 One Way TA Standby Sync Increased | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-05-12 | 2023-05-12 | 0 | 0%
Completed | 0% | Project 151 | TCSS - Digital Mobility Migration Disc. Comple | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0%
Completed | 0% | Project 155 | Drop 3 eSCDs Distribution List | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-03-07 | 2022-03-07 | 0 | 0%
Completed | 0% | Project 155 | MyRoster+ Application Changes | Deliverable | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-07-19 08:00 | 2024-07-19 08:00 | 0 | 0%
Completed | 0% | Project 155 | P1S3.3 Stopping Pattern Report MVP | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-07-01 | 2022-07-01 | 0 | 0%
Completed | 0% | Project 46 | TMS R4 - Solution build complete | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2024-06-25 17:00 | 2024-06-25 17:00 | 0 | 0%
Completed | 0% | Project 165 | Negotiation sessions Complete | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2023-02-08 | 2023-02-08 | 0 | 0%
Completed | 0% | Project 155 | Drop 3 Task Assigner PBIs for IVR Swith Off | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-10-04 | 2022-10-04 | 0 | 0%
Completed | 0% | Project 55 | Security Risk Assesment Completed | Unassigned | Yes | Completed | 4. Analyse & Design | Delay reason shown here | 2023-12-22 17:00 | 2023-12-22 17:00 | 0 | 0%
Completed | 0% | Project 155 | Drop 4 One Way TA Real-Time Updates | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-08-21 | 2023-08-21 | 0 | 0%
Completed | 0% | Project 164 | P80 estimate for delivery phase signed off | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-03-25 | 2022-03-25 | 0 | 0%
Completed | -5% to 0% | Project 46 | TMS R4 UAT completed | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2025-05-30 17:00 | 2025-04-28 17:00 | -24 | -1.401%
Completed | 0% | Project 164 | Closure Memo Completed | Unassigned | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2024-05-15 08:00 | 2024-05-15 08:00 | 0 | 0%
Completed | 0% | Project 151 | CMS Phase 1 Migration Discovery Complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0%
Completed | -5% to 0% | Project 46 | DTIP interfaces unit testing- Complete | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2024-05-31 17:00 | 2024-04-10 17:00 | -36 | -2.102%
Completed | 0% | Project 109 | Investment Brief Signed off (if applicable) | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-06-05 | 2023-06-05 | 0 | 0%
Completed | 0% | Project 151 | CMS Phase 1 Migration Analysis Complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-10-31 08:00 | 2023-10-31 08:00 | 0 | 0%
Completed | 0% | Project 155 | P2S1.3 CoPAL Complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-12-12 | 2022-12-12 | 0 | 0%
Completed | 0% | Project 122 | VIM Proof of Concept phase complete | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2023-06-16 | 2023-06-16 | 0 | 0%
Completed | 0% | Project 151 | CMS Phase 1 Migration Scratch & Design Complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-07 08:00 | 2023-11-07 08:00 | 0 | 0%
Completed | 0% | Project 151 | CMS Phase 1 Migration Build and Test Complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-15 08:00 | 2023-11-15 08:00 | 0 | 0%
Completed | 0% | Project 155 | P2S1.3 MVP Clearance of Planned Annual Leave (COPA | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2021-10-05 | 2021-10-05 | 0 | 0%
Completed | 0% | Project 46 | TMS R3 UAT environment setup- Complete | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-08-14 | 2023-08-14 | 0 | 0%
Completed | 0% | Project 151 | CMS Phase 1 Migration Implementation and go-live | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 08:00 | 2023-11-30 08:00 | 0 | 0%
Completed | 0% | Project 151 | Rail.hr (GovDC) Migration Discovery Complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-10-23 08:00 | 2023-10-23 08:00 | 0 | 0%
Completed | 0% | Project 101 | Closure memo - Signed off | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-03-28 08:00 | 2024-03-28 08:00 | 0 | 0%
Completed | 0% | Project 164 | Contract signed off | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-12-22 | 2022-12-22 | 0 | 0%
Completed | 0% | Project 151 | Rail.hr Migration Analysis Complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-10-23 08:00 | 2023-10-23 08:00 | 0 | 0%
Completed | 0% | Project 151 | Rail.hr Migration Scratch and Design Complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-10-23 08:00 | 2023-10-23 08:00 | 0 | 0%
Completed | 0% | Project 151 | Rail.hr Migration Build and Test Complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0%
Completed | 0% | Project 164 | Build Complete | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2023-10-31 17:00 | 2023-10-31 17:00 | 0 | 0%
Completed | 0% | Project 109 | PMP | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-06-26 | 2023-06-26 | 0 | 0%
Completed | 0% | Project 151 | Ramsys & Trackware Migration Discovery Complete | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2024-02-19 08:00 | 2024-02-19 08:00 | 0 | 0%
Completed | 0% | Project 109 | Maritime SOW signed off | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-06-05 | 2023-06-05 | 0 | 0%
Completed | 0% | Project 164 | RFx activities | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-08-08 | 2022-08-08 | 0 | 0%
Completed | 0% | Project 151 | Ramsys & Trackware Migration Analysis Complete | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2024-02-28 08:00 | 2024-02-28 08:00 | 0 | 0%
Completed | 0% | Project 46 | TMS R3 TEST (SIT) environment setup - Complete | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-07-13 | 2023-07-13 | 0 | 0%
Completed | 0% | Project 121 | Obtain Sign off on Concept paper | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2022-08-18 | 2022-08-18 | 0 | 0%
Completed | 0% | Project 109 | UAT Complete | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2023-10-31 17:00 | 2023-10-31 17:00 | 0 | 0%
Completed | 0% to 5% | Project 46 | TMS R3 UAT interface testing & support- Complete | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2023-12-08 17:00 | 2024-02-14 17:00 | 37 | 2.16%
Completed | 0% | Project 56 | Business Justification (Lean Business Case) Sign-o | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2023-10-13 17:00 | 2023-10-13 17:00 | 0 | 0%
Completed | 0% | Project 151 | Scoping and piroritisation - FY24 | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 08:00 | 2023-11-30 08:00 | 0 | 0%
Completed | 0% | Project 109 | Build complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-10-13 17:00 | 2023-10-13 17:00 | 0 | 0%
Completed | 0% | Project 46 | Present PROD data access solution to DSP | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2022-08-25 | 2022-08-25 | 0 | 0%
Completed | 0% | Project 151 | Integrum Archival and Decomm | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 08:00 | 2023-11-30 08:00 | 0 | 0%
Completed | 0% | Project 151 | FPE-ST Archival Complete | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2024-05-27 17:00 | 2024-05-27 17:00 | 0 | 0%
Completed | 0% | Project 46 | DSP repurpose of funds to implement PROD data acce | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-06-13 | 2023-06-13 | 0 | 0%
Completed | 0% | Project 151 | LIU Legacy Decomm | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 08:00 | 2023-11-30 08:00 | 0 | 0%
Completed | 0% | Project 151 | Archiving & Decommission - Applications/DBs 4-6 | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-12-15 08:00 | 2023-12-15 08:00 | 0 | 0%
Completed | 0% | Project 121 | Network Connectivity- PROD environment connectivit | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2024-02-29 17:00 | 2024-02-29 17:00 | 0 | 0%
Completed | 0% | Project 121 | Solutions Options Paper signed off | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2022-07-07 | 2022-07-07 | 0 | 0%
Completed | 0% | Project 56 | Business Requirements Document signed off | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2023-02-28 | 2023-02-28 | 0 | 0%
Completed | 0% | Project 56 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2023-11-15 17:00 | 2023-11-15 17:00 | 0 | 0%
Completed | 0% | Project 151 | COM Options paper for PSG | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-12-15 08:00 | 2023-12-15 08:00 | 0 | 0%
Completed | 0% | Project 151 | COM - Steerco and PSG recommendations | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-10-31 08:00 | 2023-10-31 08:00 | 0 | 0%
Completed | 0% | Project 121 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Completed | 6. Implement | Delay reason shown here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0%
Completed | 0% | Project 82 | SIT Complete | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-03-28 08:00 | 2024-03-28 08:00 | 0 | 0%
Completed | 0% | Project 155 | Business Case | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-02-04 | 2022-02-04 | 0 | 0%
Completed | 0% | Project 155 | Drop 1 eSCDs MVP | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2021-11-01 | 2021-11-01 | 0 | 0%
Completed | 0% | Project 82 | UAT Complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-05-22 08:00 | 2024-05-22 08:00 | 0 | 0%
Completed | 0% | Project 155 | Drop 2 eSCDs Offline Documents | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-02-08 | 2022-02-08 | 0 | 0%
Completed | 0% | Project 82 | IIMSS Build Complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-02-16 17:00 | 2024-02-16 17:00 | 0 | 0%
Completed | 0% | Project 164 | PMP Approved | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-07-15 | 2022-07-15 | 0 | 0%
Completed | 0% | Project 82 | Vendor On Boarding Complete | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2023-10-04 17:00 | 2023-10-04 17:00 | 0 | 0%
Completed | 0% | Project 46 | Present PROD data access solution estimation to DS | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-03-02 | 2023-03-02 | 0 | 0%
Completed | 0% | Project 55 | 3.11 Prelim Solution Arch Design (PSAD) Sign Off | Deliverable | Unassigned | Completed | 4. Analyse & Design | Delay reason shown here | 2023-08-18 | 2023-08-18 | 0 | 0%
Completed | 0% | Project 155 | 7.03 Closure Checklist & Memo Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2024-11-25 17:00 | 2024-11-25 17:00 | 0 | 0%
Completed | 0% | Project 109 | Finalise the SOW with VIPRO | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-04-21 | 2023-04-21 | 0 | 0%
Completed | 0% | Project 155 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Completed | 7. Closure | Delay reason shown here | 2024-11-25 17:00 | 2024-11-25 17:00 | 0 | 0%
Completed | 0% | Project 164 | PSAD | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-07-15 | 2022-07-15 | 0 | 0%
Completed | 0% | Project 46 | TMS R3 Test summary report (SIT)- Commencement | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-07-11 | 2023-07-11 | 0 | 0%
Completed | 0% | Project 82 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Completed | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Completed | 0% | Project 46 | Digital Timetable Information Portal (DTIP) interf | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2024-03-26 17:00 | 2024-03-26 17:00 | 0 | 0%
Completed | 0% | Project 155 | P1S6.1 eSCDs Complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-08-15 | 2022-08-15 | 0 | 0%
Completed | 0% | Project 46 | TMS R4 Solution Architecture design approval- Comp | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-02-17 | 2023-02-17 | 0 | 0%
Completed | 0% | Project 165 | Execution of contract | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 | 2023-03-13 | 0 | 0%
Completed | 0% | Project 165 | Procurement Strategy Revision (TfNSW) Sign-Off | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2022-08-30 | 2022-08-30 | 0 | 0%
Completed | 0% | Project 155 | P2S1.3 MVP Clearance of Planned Annual Leave (COPA | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2021-10-05 | 2021-10-05 | 0 | 0%
Completed | 0% | Project 122 | Vendor On Boarding Complete | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2022-08-16 | 2022-08-16 | 0 | 0%
Completed | 0% | Project 101 | Investment Brief/BC Completed | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-11-30 | 2022-11-30 | 0 | 0%
Completed | 0% | Project 46 | TMS R4 TIBCO Interface contracts- Commencement | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-02-14 | 2023-02-14 | 0 | 0%
Completed | 0% | Project 101 | Investment Brief/BC Commenced | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-08-01 | 2022-08-01 | 0 | 0%
Completed | 0% | Project 165 | Tender Evaluation Completed | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2022-11-24 | 2022-11-24 | 0 | 0%
Completed | 0% | Project 165 | Phase 0 - VC for All - Commencement | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2023-06-01 | 2023-06-01 | 0 | 0%
Completed | 0% | Project 46 | Present PROD data access solution to SAF | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2022-08-11 | 2022-08-11 | 0 | 0%
Completed | 0% | Project 164 | Obtain Sign off on Concept paper | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-01-19 | 2022-01-19 | 0 | 0%
Completed | 0% | Project 164 | Obtain Sign off on PACT | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-01-19 | 2022-01-19 | 0 | 0%
Completed | 0% | Project 46 | TMS R3 UAT completed | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2024-04-12 17:00 | 2024-04-12 17:00 | 0 | 0%
Completed | 0% | Project 164 | Business Requirements Specification signed off | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-03-11 | 2022-03-11 | 0 | 0%
Completed | 0% | Project 165 | Procurement Complete - Product & System Integrator | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2023-03-13 | 2023-03-13 | 0 | 0%
Completed | 0% | Project 101 | Solutions Options Paper signed off | Unassigned | Yes | Completed | 7. Closure | Delay reason shown here | 2024-01-31 17:00 | 2024-01-31 17:00 | 0 | 0%
Completed | 0% | Project 46 | TMS Data Interfaces- Separable Portion initiation | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2020-06-01 | 2020-06-01 | 0 | 0%
Completed | 0% | Project 109 | Obtain Sign off on PACT | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-04-28 | 2023-04-28 | 0 | 0%
Completed | 0% | Project 46 | DSP repurpose of funds to implement PROD data acc | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-05-31 | 2023-05-31 | 0 | 0%
Completed | 0% | Project 46 | Present PROD data access solution estimation to DS | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-01-09 | 2023-01-09 | 0 | 0%
Completed | 0% | Project 56 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Completed | 6. Implement | Delay reason shown here | 2022-11-30 17:00 | 2022-11-30 17:00 | 0 | 0%
Completed | 0% | Project 56 | Investment Brief | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2022-11-15 | 2022-11-15 | 0 | 0%
Completed | 0% | Project 56 | PACT | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2022-11-15 | 2022-11-15 | 0 | 0%
Completed | 0% | Project 109 | Business Requirements signed off | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-06-30 | 2023-06-30 | 0 | 0%
Completed | 0% | Project 46 | TMS R3 - Design approval | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2022-05-23 | 2022-05-23 | 0 | 0%
Completed | 0% | Project 46 | Execute TMS R3 SIT test cases- Complete | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-07-17 | 2023-07-17 | 0 | 0%
Completed | 0% | Project 164 | Vendor On Boarding - Completed | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-03-22 | 2023-03-22 | 0 | 0%
Completed | 0% | Project 121 | Network Connectivity- NonProd environment connecti | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-07-03 | 2023-07-03 | 0 | 0%
Completed | 0% | Project 46 | Document PROD data access solution | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2022-07-21 | 2022-07-21 | 0 | 0%
Completed | 0% | Project 46 | TMS R3 TPS / CTM interface unit testing | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2022-08-01 | 2022-08-01 | 0 | 0%
Completed | 0% to 5% | Project 46 | FARS interfaces unit testing- Commencement | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-11-24 17:00 | 2024-01-09 | 21 | 1.226%
Completed | 0% | Project 46 | TMS R4 TEST (SIT) environment setup - Commencement | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2024-06-26 17:00 | 2024-06-26 17:00 | 0 | 0%
Completed | 0% | Project 46 | FARS interfaces unit testing- Complete | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-06-28 | 2023-06-28 | 0 | 0%
Completed | 0% | Project 164 | Concept Phase Complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-01-21 | 2022-01-21 | 0 | 0%
Completed | 0% | Project 46 | TMS R3 UAT environment setup- Commencement | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-07-25 | 2023-07-25 | 0 | 0%
Completed | 0% | Project 164 | Evaluate Phase complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2022-03-25 | 2022-03-25 | 0 | 0%
Completed | 0% | Project 46 | TRIMS interfaces unit testing- Complete | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2024-05-13 17:00 | 2024-05-13 17:00 | 0 | 0%
Completed | 0% | Project 109 | Concept Phase Complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-06-05 | 2023-06-05 | 0 | 0%
Completed | 0% | Project 164 | SAD signed off | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-05-15 | 2023-05-15 | 0 | 0%
Completed | 0% | Project 56 | Solutions Options - PSAD endorsed by PDA | Unassigned | Yes | Completed | 6. Implement | Delay reason shown here | 2023-03-10 | 2023-03-10 | 0 | 0%
Completed | 0% | Project 109 | Evaluate Phase complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2023-08-08 | 2023-08-08 | 0 | 0%
Completed | 0% | Project 46 | TMS R4 Solution Architecture design approval- Comm | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2023-01-31 | 2023-01-31 | 0 | 0%
Completed | 0% | Project 46 | PROD data access endorsement from IT stakeholders | Unassigned | Unassigned | Completed | 6. Implement | Delay reason shown here | 2022-10-20 | 2022-10-20 | 0 | 0%
Completed | 0% | Project 145 | MIL: Analysis & Design phase - complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2018-02-28 17:00 | 2018-02-28 17:00 | 0 | 0%
Completed | 0% | Project 145 | MIL: Seed funding released | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2018-01-12 17:00 | 2018-01-12 17:00 | 0 | 0%
Completed | 0% | Project 145 | MIL: Concept phase - complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2018-01-16 17:00 | 2018-01-16 17:00 | 0 | 0%
Completed | 0% | Project 145 | MIL: Evaluate phase - complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2018-01-17 17:00 | 2018-01-17 17:00 | 0 | 0%
Completed | 0% | Project 145 | MIL: Build & Test phase - complete | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2018-03-06 17:00 | 2018-03-06 17:00 | 0 | 0%
Completed | 0% | Project 145 | MIL: Procurement contract awarded | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2018-02-06 17:00 | 2018-02-06 17:00 | 0 | 0%
Completed | 0% | Project 145 | MIL: Project closed | Unassigned | Unassigned | Completed | 7. Closure | Delay reason shown here | 2018-05-24 17:00 | 2018-05-24 17:00 | 0 | 0%
Completed | 0% | Project 95 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2024-11-19 17:00 | 2024-11-19 17:00 | 0 | 0%
Completed | 0% | Project 95 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2025-02-07 17:00 | 2025-02-07 17:00 | 0 | 0%
Completed | 0% | Project 95 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0%
Completed | 0% | Project 95 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0%
Completed | 0% | Project 95 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Completed | 3. Evaluate | Delay reason shown here | 2025-02-26 17:00 | 2025-02-26 17:00 | 0 | 0%
Completed | 0% | Project 151 | Ramsys & Trackware Migration Establishment | Unassigned | Unassigned | Completed | 5. Build & Test | Delay reason shown here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0%
Completed | 0% | Project 151 | Rail.hr (GovDC) Migration Establishment | Unassigned | Yes | Completed | 5. Build & Test | Delay reason shown here | 2023-10-23 08:00 | 2023-10-23 08:00 | 0 | 0%
Cancelled | 0% | Project 152 | PACT | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-05-30 17:00 | 2024-05-30 17:00 | 0 | 0%
Cancelled | 0% | Project 152 | Go live | Deliverable | Go-Live | Cancelled | 7. Closure | Delay reason shown here | 2023-12-20 17:00 | 2023-12-20 17:00 | 0 | 0%
Cancelled | N/A | Project 55 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-10-31 17:00
Cancelled | N/A | Project 55 | 6.05 Service Design & Definition Complete (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-23 08:00
Cancelled | N/A | Project 55 | GR:6.07 Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-23 08:00
Cancelled | N/A | Project 55 | 6.04 Release Retrospective | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-23 08:00
Cancelled | N/A | Project 55 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-11-12 17:00
Cancelled | N/A | Project 55 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-12-13 17:00
Cancelled | N/A | Project 54 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-16 17:00
Cancelled | N/A | Project 54 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-02 17:00
Cancelled | N/A | Project 54 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-02 17:00
Cancelled | N/A | Project 54 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-03-26 17:00
Cancelled | N/A | Project 54 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-10-04 08:00
Cancelled | 0% | Project 163 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0%
Cancelled | N/A | Project 82 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | 0% | Project 82 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0%
Cancelled | N/A | Project 54 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-09-16 17:00
Cancelled | N/A | Project 54 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-10-11 17:00
Cancelled | N/A | Project 54 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-10-25 17:00
Cancelled | N/A | Project 54 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-09-16 17:00
Cancelled | N/A | Project 54 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-10-11 17:00
Cancelled | N/A | Project 54 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-10-11 17:00
Cancelled | 0% | Project 121 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Cancelled | 0% | Project 121 | DCS REGISTRATION COMPLETE | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0%
Cancelled | 0% | Project 121 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0%
Cancelled | 0% | Project 121 | GR5.07 Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-08-15 08:00 | 2024-08-15 08:00 | 0 | 0%
Cancelled | 0% | Project 121 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-08-16 08:00 | 2024-08-16 08:00 | 0 | 0%
Cancelled | 0% | Project 121 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-11-18 08:00 | 2024-11-18 08:00 | 0 | 0%
Cancelled | N/A | Project 54 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-16 17:00
Cancelled | N/A | Project 54 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-16 17:00
Cancelled | N/A | Project 54 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-16 17:00
Cancelled | N/A | Project 46 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2023-07-31 08:00
Cancelled | N/A | Project 46 | 3.22 IT Work Package (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2023-07-31 08:00
Cancelled | N/A | Project 46 | DCS REGISTRATION COMPLETE | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2023-07-31 17:00
Cancelled | N/A | Project 46 | GR4.16 Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-08-05 17:00
Cancelled | N/A | Project 46 | GR4.17 Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-08-05 17:00
Cancelled | N/A | Project 46 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-08-05 17:00
Cancelled | N/A | Project 46 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-08-05 17:00
Cancelled | N/A | Project 46 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-08-05 17:00
Cancelled | N/A | Project 46 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-08-05 17:00
Cancelled | N/A | Project 46 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-08-05 17:00
Cancelled | N/A | Project 46 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2025-09-30 08:00
Cancelled | N/A | Project 46 | 4.03 HYB Team Charter (Optional) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-08-02 17:00
Cancelled | N/A | Project 46 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-08-02 17:00
Cancelled | N/A | Project 87 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here |  | 2024-08-02 17:00
Cancelled | N/A | Project 87 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here |  | 2024-08-02 17:00
Cancelled | N/A | Project 87 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here |  | 2024-08-02 17:00
Cancelled | 0% | Project 87 | 3.05 Business Impact Assessment Sign Off | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0%
Cancelled | 0% | Project 87 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0%
Cancelled | N/A | Project 87 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here |  | 2024-08-02 17:00
Cancelled | 0% | Project 87 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0%
Cancelled | N/A | Project 87 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here |  | 2024-08-02 17:00
Cancelled | N/A | Project 87 | 3.17 Change on a Page Complete | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here |  | 2024-08-02 17:00
Cancelled | 0% | Project 87 | 3.18 Change Management Plan Complete | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0%
Cancelled | 0% | Project 87 | 3.20 Test Strategy Sign Off | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0%
Cancelled | 0% | Project 87 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0%
Cancelled | N/A | Project 87 | 3.22 IT Work Package (Opt) | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here |  | 2024-08-02 17:00
Cancelled | 0% | Project 87 | DCS REGISTRATION COMPLETE | Governance | Unassigned | Cancelled | 2. Concept | Delay reason shown here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0%
Cancelled | N/A | Project 87 | 3.00 P50 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here |  | 2024-08-02 17:00
Cancelled | 0% | Project 5 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0%
Cancelled | 0% | Project 5 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0%
Cancelled | 0% | Project 123 | GR: Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Cancelled | 0% | Project 123 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Cancelled | 0% | Project 123 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Cancelled | 0% | Project 123 | 3.17 Change on a Page Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Cancelled | 0% | Project 123 | 3.22 IT Work Package (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Cancelled | 0% | Project 123 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0%
Cancelled | N/A | Project 123 | 5.03 Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 123 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-11-01 08:00 | 2024-11-01 08:00 | 0 | 0%
Cancelled | N/A | Project 123 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 123 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 123 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0%
Cancelled | N/A | Project 123 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 123 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 123 | 4.14 Detailed Service Design & Def'n Onboard Pack | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-10-03 08:00 | 2024-10-03 08:00 | 0 | 0%
Cancelled | N/A | Project 123 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 123 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 123 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 123 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-11-28 17:00 | 2024-11-28 17:00 | 0 | 0%
Cancelled | N/A | Project 137 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | 0% | Project 137 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-28 17:00 | 2024-08-28 17:00 | 0 | 0%
Cancelled | 0% | Project 137 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-28 17:00 | 2024-08-28 17:00 | 0 | 0%
Cancelled | N/A | Project 137 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 163 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here |  | 2024-12-05 17:00
Cancelled | N/A | Project 163 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here |  | 2024-12-05 17:00
Cancelled | N/A | Project 163 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here |  | 2024-10-28 17:00
Cancelled | N/A | Project 163 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here |  | 2024-10-28 17:00
Cancelled | N/A | Project 163 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here |  | 2024-09-13 17:00
Cancelled | 0% | Project 5 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0%
Cancelled | 0% | Project 5 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0%
Cancelled | 0% | Project 5 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0%
Cancelled | 0% | Project 5 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0%
Cancelled | 0% | Project 5 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0%
Cancelled | 0% | Project 5 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0%
Cancelled | 0% | Project 5 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0%
Cancelled | 0% | Project 5 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0%
Cancelled | N/A | Project 92 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 157 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0%
Cancelled | -10% to -5% | Project 157 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2025-04-11 17:00 | 2025-02-21 17:00 | -35 | -5.014%
Cancelled | -10% to -5% | Project 157 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2025-03-28 17:00 | 2025-01-24 17:00 | -44 | -6.304%
Cancelled | 0% | Project 157 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0%
Cancelled | N/A | Project 157 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here |  | 2024-09-30 17:00
Cancelled | N/A | Project 157 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here |  | 2024-09-30 17:00
Cancelled | N/A | Project 132 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 132 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
Cancelled | 0% | Project 132 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
Cancelled | 0% | Project 132 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
Cancelled | 0% | Project 132 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
Cancelled | 0% | Project 132 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
Cancelled | 0% | Project 132 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-09-13 17:00 | 2024-09-13 17:00 | 0 | 0%
Cancelled | 0% | Project 132 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-09-13 17:00 | 2024-09-13 17:00 | 0 | 0%
Cancelled | N/A | Project 92 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 3.10 Product Backlog Ready | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 92 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0%
Cancelled | N/A | Project 92 | 3.12 Program Architecture Guide Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 92 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0%
Cancelled | N/A | Project 92 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 92 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0%
Cancelled | 0% | Project 92 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0%
Cancelled | 0% | Project 92 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0%
Cancelled | 0% | Project 92 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0%
Cancelled | 0% | Project 92 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 157 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | 0% | Project 132 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-16 17:00 | 2024-08-16 17:00 | 0 | 0%
Cancelled | 0% | Project 132 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
Cancelled | 0% | Project 132 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
Cancelled | N/A | Project 44 | 7.03 Closure Memo Sign Off for Phase 3 | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | Delay reason shown here |  | 2025-06-27 17:00
Cancelled | N/A | Project 44 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Cancelled | 3. Evaluate | Delay reason shown here |  | 2025-06-30 08:00
Cancelled | N/A | Project 108 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 108 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 108 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 108 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 108 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 108 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 108 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 108 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 108 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-04-01 17:00
Cancelled | N/A | Project 108 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 108 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-04-01 17:00
Cancelled | N/A | Project 108 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 108 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 108 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 108 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 108 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-01-31 08:00 | 2025-01-31 08:00 | 0 | 0%
Cancelled | N/A | Project 108 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 108 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-01-31 08:00 | 2025-01-31 08:00 | 0 | 0%
Cancelled | N/A | Project 108 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 144 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0%
Cancelled | N/A | Project 144 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 98 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Cancelled | 0% | Project 98 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-27 17:00 | 2024-08-27 17:00 | 0 | 0%
Cancelled | 0% | Project 98 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-27 17:00 | 2024-08-27 17:00 | 0 | 0%
Cancelled | 0% | Project 98 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-27 17:00 | 2024-08-27 17:00 | 0 | 0%
Cancelled | 0% | Project 98 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-27 17:00 | 2024-08-27 17:00 | 0 | 0%
Cancelled | N/A | Project 98 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 98 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-01-24 17:00 | 2025-01-24 17:00 | 0 | 0%
Cancelled | 0% | Project 98 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-27 17:00 | 2024-08-27 17:00 | 0 | 0%
Cancelled | N/A | Project 98 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 147 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 08:00 | 2024-08-19 08:00 | 0 | 0%
Cancelled | N/A | Project 147 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 143 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | N/A | Project 143 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 143 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0%
Cancelled | N/A | Project 143 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 143 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 34 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0%
Cancelled | N/A | Project 34 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 34 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 34 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 34 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 34 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0%
Cancelled | N/A | Project 34 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 34 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-10-03 17:00 | 2024-10-03 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0%
Cancelled | N/A | Project 34 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 34 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 34 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-07 17:00 | 2025-02-07 17:00 | 0 | 0%
Cancelled | N/A | Project 34 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 34 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-03 17:00 | 2025-02-03 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-07 17:00 | 2025-02-07 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-03 17:00 | 2025-02-03 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-03-04 17:00 | 2025-03-04 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0%
Cancelled | 0% | Project 34 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-03-17 17:00 | 2025-03-17 17:00 | 0 | 0%
Cancelled | N/A | Project 34 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 34 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-05-05 17:00 | 2025-05-05 17:00 | 0 | 0%
Cancelled | N/A | Project 34 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 59 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here |  | 2025-02-27 17:00
Cancelled | N/A | Project 59 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here |  | 2025-01-24 17:00
Cancelled | N/A | Project 59 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here |  | 2025-01-28 17:00
Cancelled | N/A | Project 59 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here |  | 2025-02-28 17:00
Cancelled | N/A | Project 59 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here |  | 2025-02-20 17:00
Cancelled | N/A | Project 59 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here |  | 2025-02-26 17:00
Cancelled | 0% | Project 59 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0%
Cancelled | N/A | Project 59 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here |  | 2025-04-01 17:00
Cancelled | 0% | Project 59 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-05-01 17:00 | 2025-05-01 17:00 | 0 | 0%
Cancelled | N/A | Project 59 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here |  | 2025-05-19 17:00
Cancelled | 0% | Project 167 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | 0% | Project 167 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | 0% | Project 167 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | 0% | Project 167 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | 0% | Project 167 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | 0% | Project 167 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | N/A | Project 167 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | 0% | Project 167 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | 0% | Project 167 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | 0% | Project 167 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | -25% to -10% | Project 167 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00 | 2024-08-21 17:00 | -81 | -23.76%
Cancelled | 0% | Project 167 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | 0% | Project 167 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | -5% to 0% | Project 167 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00 | 2024-11-22 17:00 | -15 | -4.4%
Cancelled | N/A | Project 167 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | 0% | Project 167 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-03-31 17:00 | 2025-03-31 17:00 | 0 | 0%
Cancelled | 0% | Project 167 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | N/A | Project 167 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | N/A | Project 167 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | N/A | Project 167 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | N/A | Project 167 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | N/A | Project 167 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | N/A | Project 167 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | N/A | Project 167 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | 0% | Project 167 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0%
Cancelled | N/A | Project 167 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | N/A | Project 167 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | N/A | Project 167 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | N/A | Project 167 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-13 17:00
Cancelled | N/A | Project 167 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-05-01 17:00
Cancelled | 0% | Project 167 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-05-01 17:00 | 2025-05-01 17:00 | 0 | 0%
Cancelled | N/A | Project 167 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-05-01 17:00
Cancelled | N/A | Project 167 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-05-01 17:00
Cancelled | N/A | Project 167 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-05-01 17:00
Cancelled | N/A | Project 167 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | Delay reason shown here | 2025-06-13 17:00
Cancelled | N/A | Project 142 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 142 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-11-01 17:00 | 2024-11-01 17:00 | 0 | 0%
Cancelled | N/A | Project 142 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 142 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 108 | BUILD COMPLETE | Governance | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 108 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-06-05 17:00 | 2025-06-05 17:00 | 0 | 0%
Cancelled | N/A | Project 137 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 92 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 92 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2025-01-24 17:00 | 2025-01-24 17:00 | 0 | 0%
Cancelled | 0% | Project 92 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
Cancelled | 0% | Project 92 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2025-01-07 17:00 | 2025-01-07 17:00 | 0 | 0%
Cancelled | 0% | Project 92 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0%
Cancelled | 0% | Project 92 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-12-06 17:00 | 2024-12-06 17:00 | 0 | 0%
Cancelled | 0% | Project 92 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-12-06 17:00 | 2024-12-06 17:00 | 0 | 0%
Cancelled | 0% | Project 92 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2025-01-10 17:00 | 2025-01-10 17:00 | 0 | 0%
Cancelled | 0% | Project 92 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2025-01-23 17:00 | 2025-01-23 17:00 | 0 | 0%
Cancelled | N/A | Project 92 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 166 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Cancelled | 0% | Project 166 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0%
Cancelled | N/A | Project 166 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here
Cancelled | 0% | Project 166 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Cancelled | 0% | Project 166 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Cancelled | 0% | Project 166 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Cancelled | 0% | Project 166 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Cancelled | 0% | Project 166 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Cancelled | N/A | Project 166 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here
Cancelled | 0% | Project 166 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Cancelled | 0% | Project 166 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Cancelled | N/A | Project 166 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | N/A | Project 166 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here
Cancelled | 0% | Project 166 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Cancelled | 0% | Project 166 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Cancelled | 0% | Project 166 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Cancelled | 0% | Project 166 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Cancelled | 0% | Project 166 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Cancelled | 7. Closure | Delay reason shown here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0%
Cancelled | 0% | Project 166 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Cancelled | 0% | Project 166 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 7. Closure | Delay reason shown here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0%
Cancelled | N/A | Project 92 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 92 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2025-01-17 17:00 | 2025-01-17 17:00 | 0 | 0%
Cancelled | N/A | Project 92 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 92 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2025-02-05 17:00 | 2025-02-05 17:00 | 0 | 0%
Cancelled | 0% | Project 92 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0%
Cancelled | N/A | Project 92 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 92 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 139 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-12-10 17:00 | 2024-12-10 17:00 | 0 | 0%
Cancelled | N/A | Project 139 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 139 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2025-01-10 17:00 | 2025-01-10 17:00 | 0 | 0%
Cancelled | N/A | Project 139 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 139 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 139 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | Delay reason shown here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | Delay reason shown here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | Delay reason shown here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | Delay reason shown here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | Delay reason shown here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | Delay reason shown here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | Delay reason shown here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | Delay reason shown here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | Delay reason shown here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | Delay reason shown here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | Delay reason shown here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2023-03-29 17:00 | 2023-03-29 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2023-03-29 17:00 | 2023-03-29 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2023-03-29 17:00 | 2023-03-29 17:00 | 0 | 0%
Cancelled | N/A | Project 165 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2021-11-30 17:00
Cancelled | N/A | Project 165 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2021-11-30 17:00
Cancelled | N/A | Project 165 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2021-11-30 17:00
Cancelled | 0% | Project 165 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2023-03-29 17:00 | 2023-03-29 17:00 | 0 | 0%
Cancelled | 0% | Project 165 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2023-03-29 17:00 | 2023-03-29 17:00 | 0 | 0%
Cancelled | >25%+ | Project 165 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2021-11-30 17:00 | 2024-11-29 17:00 | 760 | 35.4%
Cancelled | 0% | Project 165 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2023-03-29 17:00 | 2023-03-29 17:00 | 0 | 0%
Cancelled | N/A | Project 165 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2021-11-30 17:00
Cancelled | N/A | Project 165 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2021-11-30 17:00
Cancelled | 0% | Project 165 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2024-09-27 17:00 | 2024-09-27 17:00 | 0 | 0%
Cancelled | N/A | Project 165 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2021-11-30 17:00
Cancelled | N/A | Project 165 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2021-11-30 17:00
Cancelled | 0% | Project 132 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-09-02 08:00 | 2024-09-02 08:00 | 0 | 0%
Cancelled | 0% | Project 132 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-09-02 08:00 | 2024-09-02 08:00 | 0 | 0%
Cancelled | N/A | Project 132 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 132 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 147 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | N/A | Project 147 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 147 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | 0% | Project 147 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0%
Cancelled | N/A | Project 147 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 147 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 147 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 147 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 147 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 147 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 147 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 147 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 147 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 147 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 147 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 147 | SAA BUILD COMPLETE (Vendor) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 44 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-23 17:00 | 2024-08-23 17:00 | 0 | 0%
Cancelled | 0% | Project 44 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-23 17:00 | 2024-08-23 17:00 | 0 | 0%
Cancelled | 0% | Project 44 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-23 17:00 | 2024-08-23 17:00 | 0 | 0%
Cancelled | 0% | Project 44 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-23 17:00 | 2024-08-23 17:00 | 0 | 0%
Cancelled | 0% | Project 44 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-08-23 17:00 | 2024-08-23 17:00 | 0 | 0%
Cancelled | N/A | Project 144 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 144 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 22 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Cancelled | N/A | Project 22 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here | 2024-04-30 17:00
Cancelled | N/A | Project 22 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Cancelled | N/A | Project 22 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here | 2024-05-31 17:00
Cancelled | N/A | Project 22 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 2. Concept | Delay reason shown here | 2024-06-28 17:00
Cancelled | 0% | Project 165 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2025-04-30 08:00 | 2025-04-30 08:00 | 0 | 0%
Cancelled | 0% | Project 165 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 5. Build & Test | Delay reason shown here | 2025-08-25 08:00 | 2025-08-25 08:00 | 0 | 0%
Cancelled | N/A | Project 154 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here |  | 2025-02-21 17:00
Cancelled | N/A | Project 154 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 154 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 140 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 140 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 98 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 98 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0%
Cancelled | N/A | Project 98 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 98 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0%
Cancelled | N/A | Project 98 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 98 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 98 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-17 08:00 | 2025-02-17 08:00 | 0 | 0%
Cancelled | 0% | Project 98 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-17 08:00 | 2025-02-17 08:00 | 0 | 0%
Cancelled | 0% | Project 98 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-03-31 08:00 | 2025-03-31 08:00 | 0 | 0%
Cancelled | N/A | Project 98 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | 0% | Project 98 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here | 2025-03-31 08:00 | 2025-03-31 08:00 | 0 | 0%
Cancelled | N/A | Project 151 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.04 HYB Release Retrospective Complete | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.04 HYB Release Retrospective Complete | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 137 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 137 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 83 | Pilot PSAD Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 83 | Pilot Business Requirements Document Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 83 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 83 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 83 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 83 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 151 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.04 HYB Release Retrospective Complete | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 59 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here |  | 2024-11-14 17:00
Cancelled | N/A | Project 59 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here |  | 2024-11-14 17:00
Cancelled | N/A | Project 59 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here |  | 2024-11-14 17:00
Cancelled | N/A | Project 59 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here |  | 2024-11-14 17:00
Cancelled | N/A | Project 59 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here |  | 2024-11-14 17:00
Cancelled | N/A | Project 59 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here |  | 2024-11-28 17:00
Cancelled | N/A | Project 59 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here |  | 2024-11-28 17:00
Cancelled | N/A | Project 59 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here |  | 2024-11-14 17:00
Cancelled | N/A | Project 59 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here |  | 2024-11-14 17:00
Cancelled | N/A | Project 59 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here |  | 2024-11-14 17:00
Cancelled | 0% | Project 59 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0%
Cancelled | N/A | Project 151 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 5.00 Service Continuity Runbook Complete | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here |  | 2025-02-28 17:00
Cancelled | N/A | Project 151 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.04 HYB Release Retrospective Complete | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.04 HYB Release Retrospective Complete | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 151 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Yes | Cancelled | 5. Build & Test | Delay reason shown here
Cancelled | N/A | Project 120 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 120 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | Delay reason shown here | 2024-12-13 17:00 | 2024-12-13 17:00 | 0 | 0%
Cancelled | N/A | Project 120 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | N/A | Project 120 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% | Project 141 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-24 17:00 | 2025-02-24 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-01-24 17:00 | 2025-01-24 17:00 | 0 | 0%
Cancelled | 0% | Project 141 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-01-24 17:00 | 2025-01-24 17:00 | 0 | 0%
Cancelled | N/A | Project 72 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 72 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here
Cancelled | N/A | Project 110 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-11-08 17:00
Cancelled | N/A | Project 110 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-11-08 17:00
Cancelled | N/A | Project 110 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-11-08 17:00
Cancelled | N/A | Project 110 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-11-08 17:00
Cancelled | N/A | Project 110 | 6.01 Training Docs & App H'over Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-11-08 17:00
Cancelled | N/A | Project 110 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-11-08 17:00
Cancelled | N/A | Project 110 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-11-08 17:00
Cancelled | N/A | Project 110 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-11-08 17:00
Cancelled | N/A | Project 59 | Cyber Sec Requirements Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | Delay reason shown here | 2025-03-07 08:00
Cancelled | N/A | Project 154 | Service Design & Def'n & Onb'ding Pack Prepared | Deliverable | Unassigned | Cancelled | 3. Evaluate | Delay reason shown here |  | 2025-02-28 08:00
Cancelled | N/A | Project 128 | Contract signed off | Unassigned | Yes | Cancelled | 2. Concept | Delay reason shown here | 2024-04-08 17:00
Cancelled | -25% to -10% | Project 44 | Closure- SGR Completed | Unassigned | Yes | Cancelled | 3. Evaluate | Delay reason shown here | 2024-12-20 17:00 | 2024-02-29 17:00 | -206 | -16.78%
Cancelled | <-25% | Project 55 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 4. Analyse & Design | Delay reason shown here | 2024-10-31 17:00 | 2024-02-05 17:00 | -188 | -43.02%
Cancelled | N/A | Project 128 | RFx activities complete | Unassigned | Yes | Cancelled | 2. Concept | Delay reason shown here | 2024-03-25 17:00
Cancelled | 0% | Project 151 | Archiving and Decommission - Applications/DBs 7-9 | Unassigned | Yes | Cancelled | 5. Build & Test | Delay reason shown here | 2025-06-13 17:00 | 2025-06-13 17:00 | 0 | 0%
Cancelled | N/A | Project 123 | GO LIVE - OT-IT Ph2 | Deliverable | Go-Live | Cancelled | 6. Implement | Delay reason shown here
Cancelled | 0% to 5% | Project 46 | TMS R4 UAT environment setup- Commencement | Deliverable | Unassigned | Cancelled | 6. Implement | Delay reason shown here | 2024-05-31 17:00 | 2024-09-25 17:00 | 82 | 4.787%
Cancelled | N/A | Project 172 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 172 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 160 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 160 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 161 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 159 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | Delay reason shown here
Cancelled | N/A | Project 57 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 6.01 Training Docs & App H'over Checklist Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | GO LIVE | Deliverable | Go-Live | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Cancelled | 4. Analyse & Design | Delay reason shown here
Cancelled | N/A | Project 57 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Cancelled | 4. Analyse & Design | Delay reason shown here