## Data Quality
MANUAL COL
114 | [6 empty] | 0 | 817 | 8 | 0 | 4 | 829
Work ID | Work Name | Sub-Portfolio | Project Manager | Work Status | Stage | PSR Date | PSR Updated? | Milestones Due | Risks Due | Risks - Mitigation Blank | Issues Due | Total Data Quality Issues | PMO Name Following Up | PMO Comments
1000292 | Project 1 | Sub-Portfolio 4 | Project Manager 3 | Prepare for Closure | 7. Closure | 11 Oct 24 | NA | 0 | 0 | 0 | 0 | 0 |  | Closed
1000293 | Project 2 | Sub-Portfolio 4 | Project Manager 18 | Prepare for Closure | 6. Implement | 19 Feb 24 - 01 Mar 24 | NA | 0 | 0 | 0 | 0 | 0 |  | project delivered in Feb 2024
1000294 | Project 3 | Sub-Portfolio 4 | Project Manager 4 | Open/Active | 3. Evaluate | 02 May 25 | Yes | 8 | 0 | 0 | 0 | 8 |  | 1/5: Followed up
1000296 | Project 5 | Sub-Portfolio 7 | Project Manager 8 | Open/Active | 3. Evaluate | Apr-2025 | Yes | 15 | 0 | 0 | 0 | 15 |  | 1/5: Followed up
1000297 | Project 6 | Sub-Portfolio 8 | Project Manager 22 | On Hold | 7. Closure | Aug-2024 | NA | 0 | 0 | 0 | 0 | 0 |  | Closed
1000298 | Project 7 | Sub-Portfolio 4 | Project Manager 38 | Open/Active | 6. Implement | 25 Apr 25 | Yes | 56 | 0 | 0 | 0 | 56
1000299 | Project 8 | Sub-Portfolio 4 | Project Manager 36 | Completed | 6. Implement | 02 Aug 24 |  | 0 | 0 | 0 | 0 | 0 |  | Closure memo submitted and signed by Portfolio Director
1000300 | Project 9 | Sub-Portfolio 8 | Project Manager 12 | Prepare for Closure | 7. Closure | Sep-2024 | NA | 2 | 0 | 0 | 0 | 2 |  | Project has been delivered and completed
1000301 | Project 10 | Sub-Portfolio 7 | Project Manager 17 | Open/Active | 6. Implement | Apr-2025 | Yes | 6 | 0 | 0 | 0 | 6
1000302 | Project 11 | Sub-Portfolio 7 | Project Manager 17 | Open/Active | 6. Implement | Apr-2025 | Yes | 13 | 0 | 0 | 0 | 13
1000303 | Project 12 | Sub-Portfolio 4 | Project Manager 18 | Open/Active | 7. Closure | 01 Dec 23 | NA | 0 | 0 | 0 | 0 | 0 |  | Project has been delivered and completed
1000304 | Project 13 | Sub-Portfolio 8 | Project Manager 22 | Prepare for Closure | 7. Closure | Apr-2025 | NA | 6 | 0 | 0 | 0 | 6 |  | The post go-live support which is orginally planned until end of Jan'25 is extended until Apr'25. During this time, post go-live issues and existing BAU issues are being resolved with the help of the vendors (OpenText and HCL). All the outstanding issues are now resolved, and the post go-live support is now under closure Decommissioning of legacy stack in GovDC is initiated.
1000305 | Project 14 | Sub-Portfolio 8 | Project Manager 25 | Prepare for Closure | 7. Closure | Jun-2024 | NA | 0 | 0 | 0 | 0 | 0 |  | Project has been delivered and completed
1000306 | Project 15 | Sub-Portfolio 5 | Project Manager 26 | Completed | 7. Closure | Jun-2024 |  | 0 | 0 | 0 | 0 | 0 |  | Project has been delivered and completed
1000307 | Project 16 | Sub-Portfolio 7 | Project Manager 34 | Open/Active | 5. Build & Test | Apr-2025 | Yes | 27 | 0 | 0 | 0 | 27
1000308 | Project 17 | Sub-Portfolio 7 | Project Manager 4 | On Hold | 4. Analyse & Design | Apr-2025 | Yes | 14 | 0 | 0 | 0 | 14 |  | Project put on hold, resources reallocated.
1000309 | Project 18 | Sub-Portfolio 4 | Project Manager 3 | Completed | 7. Closure | 10 May 24 |  | 0 | 0 | 0 | 0 | 0 |  | Project has been delivered and completed
1000310 | Project 19 | Sub-Portfolio 8 | Project Manager 6 | Open/Active | 5. Build & Test | Apr-2025 | Yes | 27 | 0 | 0 | 0 | 27
1000311 | Project 20 | Sub-Portfolio 8 | Project Manager 31 | Prepare for Closure | 4. Analyse & Design | Aug-2024 | NA | 7 | 0 | 0 | 0 | 7 |  | completed in Oct 24
1000312 | Project 21 | Sub-Portfolio 7 | Project Manager 10 | Completed | 7. Closure | Jun-2024 |  | 0 | 1 | 0 | 0 | 1 |  | 0
1000313 | Project 22 | Sub-Portfolio 1 | Project Manager 32 | Prepare for Closure | 7. Closure | 0 | NA | 2 | 0 | 0 | 0 | 2 |  | Exception case - not for reporting
1000314 | Project 23 | Sub-Portfolio 7 | Project Manager 33 | Open/Active | 6. Implement | Apr-2025 | Yes | 19 | 0 | 0 | 0 | 19
1000315 | Project 24 | Sub-Portfolio 7 | Project Manager 35 | Open/Active | 2. Concept | Oct-2023 |  | 2 | 0 | 0 | 0 | 2 |  | Closed
1000316 | Project 25 | Sub-Portfolio 7 | Project Manager 38 | Completed | 7. Closure | May-2024 |  | 0 | 0 | 0 | 0 | 0 |  | 0
1000838 | Project 26 | Sub-Portfolio 7 |  | On Hold | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1000840 | Project 27 | Sub-Portfolio 7 | Project Manager 38 | Requested | 2. Concept | Apr-2024 |  | 15 | 0 | 0 | 0 | 15
1000841 | Project 28 | Sub-Portfolio 7 | Project Manager 38 | On Hold | 3. Evaluate | Feb-2024 | NA | 0 | 0 | 0 | 0 | 0 |  | Closed
1000869 | Project 29 | Sub-Portfolio 7 | Project Manager 17 | Open/Active | 4. Analyse & Design | Apr-2025 | Yes | 22 | 0 | 0 | 0 | 22
1000871 | Project 30 | Sub-Portfolio 8 | Project Manager 25 | On Hold | 4. Analyse & Design | Feb-2024 | NA | 0 | 0 | 0 | 0 | 0 |  | 2 new projects have been created
1000872 | Project 31 | Sub-Portfolio 8 | Project Manager 7 | Requested | 2. Concept | May-2024 |  | 5 | 0 | 0 | 1 | 6 |  | On Hold
1000884 | Project 32 | Sub-Portfolio 4 | Project Manager 18 | Cancelled | 2. Concept | 01 Dec 23 |  | 0 | 0 | 0 | 0 | 0 |  | Closed
1000918 | Project 33 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept | 01 Dec 23 |  | 0 | 0 | 0 | 0 | 0 |  | Will be closed
1000921 | Project 34 | Sub-Portfolio 4 | Project Manager 18 | Cancelled | 2. Concept | 01 Dec 23 |  | 0 | 0 | 0 | 0 | 0 |  | 0
1000924 | Project 36 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept | 01 Dec 23 |  | 0 | 0 | 0 | 0 | 0
1000927 | Project 39 | Sub-Portfolio 4 | Project Manager 18 | Cancelled | 2. Concept | 01 Dec 23 |  | 0 | 0 | 0 | 0 | 0 |  | 0
1000986 | Project 41 | Sub-Portfolio 7 | Project Manager 17 | Requested | 3. Evaluate | 05 Jul 24 | NA | 0 | 0 | 0 | 0 | 0 |  | Will be closed
1000987 | Project 42 | Sub-Portfolio 7 | Project Manager 29 | Open/Active | 4. Analyse & Design | Apr-2025 | Yes | 21 | 0 | 0 | 0 | 21
1000990 | Project 43 | Sub-Portfolio 8 | Project Manager 12 | Completed | 7. Closure | Jun-2024 |  | 0 | 0 | 0 | 0 | 0 |  | 0
1001122 | Project 45 | Sub-Portfolio 4 | Project Manager 38 | Prepare for Closure | 7. Closure | 07 Mar 25 | NA | 0 | 0 | 0 | 0 | 0 |  | not reportable, project closed
1001242 | Project 49 | Sub-Portfolio 7 |  | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001269 | Project 50 | Sub-Portfolio 7 | Project Manager 35 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001274 | Project 53 | Sub-Portfolio 4 | Project Manager 23 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001275 | Project 54 | Sub-Portfolio 4 | Project Manager 23 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001276 | Project 55 | Sub-Portfolio 4 | Project Manager 20 | Requested | 2. Concept | Apr-2025 |  | 0 | 0 | 0 | 0 | 0 |  | Project has been delivered and completed
1001277 | Project 56 | Sub-Portfolio 7 | Project Manager 27 | On Hold | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001279 | Project 57 | Sub-Portfolio 7 | Project Manager 1 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001280 | Project 58 | Sub-Portfolio 7 | Project Manager 27 | Cancelled | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Cancelled
1001282 | Project 59 | Sub-Portfolio 7 | Project Manager 14 | Open/Active | 3. Evaluate | Apr-2025 | Yes | 36 | 1 | 0 | 1 | 38
1001328 | Project 61 | Sub-Portfolio 8 | Project Manager 25 | Open/Active | 6. Implement | Apr-2025 | Yes | 55 | 0 | 0 | 0 | 55
1001347 | Project 62 | Sub-Portfolio 8 | Project Manager 16 | Open/Active | 3. Evaluate | 02 May 25 | Yes | 20 | 0 | 0 | 0 | 20 |  | 1/5: Followed up
1001349 | Project 63 | Sub-Portfolio 4 | Project Manager 18 | Open/Active | 3. Evaluate | 02 May 25 | Yes | 21 | 1 | 0 | 1 | 23 |  | 1/5: Followed up with PM
1001350 | Project 64 | Sub-Portfolio 8 | Project Manager 25 | Open/Active | 6. Implement | Feb-2025 | NA | 26 | 0 | 0 | 0 | 26 |  | Project closure will be approved in April. It is expected to be received in March 2025.
1001351 | Project 65 | Sub-Portfolio 8 | Project Manager 29 | Open/Active | 6. Implement | Apr-2025 | Yes | 18 | 1 | 0 | 0 | 19
1001353 | Project 66 | Sub-Portfolio 8 | Project Manager 12 | Open/Active | 3. Evaluate | 02 May 25 | Yes | 33 | 0 | 0 | 0 | 33 |  | 1/5: Updated today
1001354 | Project 67 | Sub-Portfolio 8 | Project Manager 2 | Cancelled | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
1001355 | Project 68 | Sub-Portfolio 8 | Project Manager 12 | Open/Active | 3. Evaluate | 02 May 25 | Yes | 27 | 1 | 0 | 1 | 29 |  | 1/5: Updated today
1001356 | Project 69 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001357 | Project 70 | Sub-Portfolio 1 | Project Manager 11 | On Hold | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001358 | Project 71 | Sub-Portfolio 8 | Project Manager 30 | Open/Active | 3. Evaluate | 02 May 25 | Yes | 29 | 2 | 0 | 0 | 31 |  | 1/5: PSR updated
1001359 | Project 72 | Sub-Portfolio 8 | Project Manager 21 | Open/Active | 3. Evaluate | 25 Apr 25 | Yes | 18 | 0 | 0 | 0 | 18 |  | 1/5: Updated today
1001360 | Project 73 | Sub-Portfolio 8 | Project Manager 21 | Open/Active | 4. Analyse & Design | 25 Apr 25 | Yes | 37 | 0 | 0 | 0 | 37 |  | 1/5: Updated today
1001361 | Project 74 | Sub-Portfolio 8 | Project Manager 28 | Open/Active | 3. Evaluate | Apr-2025 | Yes | 29 | 0 | 0 | 0 | 29
1001362 | Project 75 | Sub-Portfolio 4 | Project Manager 18 | Open/Active | 3. Evaluate | Apr-2025 | Yes | 21 | 0 | 0 | 0 | 21 |  | 1/5: Updated today
1001363 | Project 76 | Sub-Portfolio 4 | Project Manager 38 | Open/Active | 3. Evaluate | 25 Apr 25 | Yes | 41 | 0 | 0 | 0 | 41
1001364 | Project 77 | Sub-Portfolio 4 | Project Manager 38 | Open/Active | 3. Evaluate | May-2025 | Yes | 20 | 0 | 0 | 0 | 20
1001367 | Project 78 | Sub-Portfolio 4 | Project Manager 39 | Requested | 2. Concept | 26 Jul 24 |  | 0 | 0 | 0 | 0 | 0 |  | Cancelled
1001373 | Project 79 | Sub-Portfolio 7 | Project Manager 38 | Open/Active | 4. Analyse & Design | Apr-2025 | Yes | 10 | 1 | 0 | 0 | 11
1001374 | Project 80 | Sub-Portfolio 8 | Project Manager 25 | Requested | 2. Concept | Jun-2024 |  | 0 | 0 | 0 | 0 | 0 |  | Should be closed
1001375 | Project 81 | Sub-Portfolio 8 | Project Manager 25 | Requested | 2. Concept | Jun-2024 |  | 0 | 0 | 0 | 0 | 0 |  | On Hold
1001384 | Project 82 | Sub-Portfolio 8 | Project Manager 11 | On Hold | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001388 | Project 83 | Sub-Portfolio 8 | Project Manager 31 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Dummy
1001392 | Project 84 | Sub-Portfolio 7 | Project Manager 27 | On Hold | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001399 | Project 85 | Sub-Portfolio 4 | Project Manager 14 | Prepare for Closure | 7. Closure | 31 Jan 25 | NA | 34 | 0 | 0 | 0 | 34 |  | Project closedown on 31/01/2025
1001420 | Project 87 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0 |  | On Hold
1001430 | Project 91 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0 |  | May be closed
1001440 | Project 93 | Sub-Portfolio 8 | Project Manager 13 | Open/Active | 3. Evaluate | Apr-2025 | Yes | 20 | 0 | 0 | 0 | 20
1001493 | Project 101 | Sub-Portfolio 2 |  | On Hold | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001498 | Project 102 | Sub-Portfolio 7 | Project Manager 35 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0 |  | This is a Program
1001566 | Project 106 | Sub-Portfolio 7 | Project Manager 27 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001602 | Project 108 | Sub-Portfolio 7 | Project Manager 27 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001617 | Project 110 | Sub-Portfolio 8 | Project Manager 22 | Open/Active | 3. Evaluate | Apr-2025 | Yes | 6 | 0 | 0 | 0 | 6 |  | 1/5: Updated today
1001647 | Project 114 | Sub-Portfolio 4 | Project Manager 20 | Open/Active | 3. Evaluate | Apr-2025 | Yes | 0 | 0 | 0 | 0 | 0 |  | Changed from Minor Work to Project, its Stage Gate needs to be re-set from Implement to Concept
1001755 | Project 116 | Sub-Portfolio 4 | Project Manager 36 | Requested | 2. Concept | 0 |  | 1 | 0 | 0 | 0 | 1
1001774 | Project 119 | Sub-Portfolio 4 | Project Manager 4 | Requested | 2. Concept | Mar-2025 |  | 0 | 0 | 0 | 0 | 0
1001775 | Project 120 | Sub-Portfolio 4 | Project Manager 14 | Requested | 2. Concept | Apr-2025 |  | 26 | 0 | 0 | 0 | 26
1001776 | Project 121 | Sub-Portfolio 4 | Project Manager 14 | Requested | 2. Concept | Apr-2025 |  | 22 | 0 | 0 | 0 | 22
1001802 | Project 130 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001816 | Project 135 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Closed
1001817 | Project 136 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001818 | Project 137 | Sub-Portfolio 7 | Project Manager 7 | On Hold | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001821 | Project 140 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001822 | Project 141 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001825 | Project 143 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept | Apr-2025 |  | 0 | 0 | 0 | 0 | 0
1001829 | Project 144 | Sub-Portfolio 7 | Project Manager 35 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001834 | Project 145 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept | Apr-2025 |  | 0 | 0 | 0 | 0 | 0
1001857 | Project 146 | Sub-Portfolio 7 |  | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001860 | Project 147 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001861 | Project 148 | Sub-Portfolio 2 |  | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001863 | Project 149 | Sub-Portfolio 4 | Project Manager 3 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001866 | Project 150 | Sub-Portfolio 4 | Project Manager 3 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001870 | Project 152 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001871 | Project 153 | Sub-Portfolio 7 |  | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001872 | Project 154 | Sub-Portfolio 4 | Project Manager 20 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001875 | Project 156 | Sub-Portfolio 8 | Project Manager 25 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001876 | Project 157 | Sub-Portfolio 8 | Project Manager 25 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001877 | Project 158 | Sub-Portfolio 8 | Project Manager 25 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001878 | Project 159 | Sub-Portfolio 8 | Project Manager 16 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001879 | Project 160 | Sub-Portfolio 8 | Project Manager 31 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001880 | Project 161 | Sub-Portfolio 8 |  | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001881 | Project 162 | Sub-Portfolio 8 | Project Manager 12 | Cancelled | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0
1001882 | Project 163 | Sub-Portfolio 7 |  | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001891 | Project 164 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001896 | Project 166 | Sub-Portfolio 7 |  | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
1001898 | Project 167 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept | 0 |  | 0 | 0 | 0 | 0 | 0
Formulas:
PSR Date = XLOOKUP(TEXT(tbl_Data_Quality[[#This Row],[Work ID]],"0"),tbl_PV_Meta[Work ID '#],tbl_PV_Meta[PSR Date],,0)
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Status Review_ALL
114
Work ID | Work Name | Sub-Portfolio | PM | Work Status | Stage | PSR Date | OVERALL | SCOPE | COST | Budget | EAC | Var | SCHEDULE | Milestones Overdue | Milestones Delayed | Milestones Delay past FY25 | RESOURCE | BENEFIT | OCM | RISK | Active Inherent H & VH | Risks Due | Risks - Mitigation Action Plan Blank | ISSUE | Active H & VH | Issues Due
1000296 | Project 5 | Sub-Portfolio 7 | Project Manager 8 | Open/Active | 3. Evaluate | Apr-2025 | Red | Amber | Green | 3619244 | 3226487.38 | 392756.62 | Red | 15 | 8 |  | Green | Green | Green | Amber | 3 |  |  | Green | 1
1000307 | Project 16 | Sub-Portfolio 7 | Project Manager 34 | Open/Active | 5. Build & Test | Apr-2025 | Red | Green | Red |  |  |  | Amber | 27 | 16 | 2 | Amber | Green | Green | Amber | 1 |  |  | Amber
1000871 | Project 30 | Sub-Portfolio 8 | Project Manager 25 | On Hold | 4. Analyse & Design | Feb-2024 | Red | Amber | Red |  |  |  | Amber |  |  |  | Amber | Green | Green | Amber |  |  |  | Amber
1001282 | Project 59 | Sub-Portfolio 7 | Project Manager 14 | Open/Active | 3. Evaluate | Apr-2025 | Red | Amber | Amber | 887296.14 | 972999.66 | -85703.52 | Amber | 36 | 6 |  | Amber | Green | Green | Red |  | 1 |  | Amber | 1 | 1
1000310 | Project 19 | Sub-Portfolio 8 | Project Manager 6 | Open/Active | 5. Build & Test | Apr-2025 | Amber | Green | Amber |  |  |  | Amber | 27 | 18 |  | Green | Green | Green | Amber | 3 |  |  | Amber
1000313 | Project 22 | Sub-Portfolio 1 | Project Manager 32 | Prepare for Closure | 7. Closure | [8 empty] | 2
1000314 | Project 23 | Sub-Portfolio 7 | Project Manager 33 | Open/Active | 6. Implement | Apr-2025 | Amber | Green | Green | 2287821 | 2287735.29 | 85.71 | Amber | 19 | 2 |  | Amber | Green | Green | Amber |  |  |  | Amber
1000838 | Project 26 | Sub-Portfolio 7 |  | On Hold | 2. Concept
1001242 | Project 49 | Sub-Portfolio 7 |  | Requested | 2. Concept
1001269 | Project 50 | Sub-Portfolio 7 | Project Manager 35 | Requested | 2. Concept
1001274 | Project 53 | Sub-Portfolio 4 | Project Manager 23 | Requested | 2. Concept
1001275 | Project 54 | Sub-Portfolio 4 | Project Manager 23 | Requested | 2. Concept
1001276 | Project 55 | Sub-Portfolio 4 | Project Manager 20 | Requested | 2. Concept | Apr-2025 | Amber | Amber | Green |  |  |  | Amber |  |  |  | Green | Green | Green | Amber |  |  |  | Green
1001277 | Project 56 | Sub-Portfolio 7 | Project Manager 27 | On Hold | 2. Concept
1001279 | Project 57 | Sub-Portfolio 7 | Project Manager 1 | Requested | 2. Concept
1001280 | Project 58 | Sub-Portfolio 7 | Project Manager 27 | Cancelled | 2. Concept
1001349 | Project 63 | Sub-Portfolio 4 | Project Manager 18 | Open/Active | 3. Evaluate | 02 May 25 | Amber | Green | Amber | 1500000 | 1405080.08 | 94919.92 | Amber | 21 | 22 |  | Amber | Green | Green | Amber | 1 | 1 |  | Amber | 1 | 1
1001351 | Project 65 | Sub-Portfolio 8 | Project Manager 29 | Open/Active | 6. Implement | Apr-2025 | Amber | Green | Amber | 800000 | 655218.77 | 144781.23 | Amber | 18 |  |  | Green | Green | Green | Green | 1 | 1 |  | Green
1001354 | Project 67 | Sub-Portfolio 8 | Project Manager 2 | Cancelled | 2. Concept
1001356 | Project 69 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept
1001357 | Project 70 | Sub-Portfolio 1 | Project Manager 11 | On Hold | 2. Concept
1001358 | Project 71 | Sub-Portfolio 8 | Project Manager 30 | Open/Active | 3. Evaluate | 02 May 25 | Amber | Green | Amber | 220000 | 357014.67 | -137014.67 | Amber | 29 | 21 | 10 | Amber | Green | Green | Green | 1 | 2 |  | Green
1001359 | Project 72 | Sub-Portfolio 8 | Project Manager 21 | Open/Active | 3. Evaluate | 25 Apr 25 | Amber | Amber | Green | 350000 | 222629.68 | 127370.32 | Amber | 18 |  |  | Amber | Green | Green | Amber | 1 |  |  | Green
1001384 | Project 82 | Sub-Portfolio 8 | Project Manager 11 | On Hold | 2. Concept
1001388 | Project 83 | Sub-Portfolio 8 | Project Manager 31 | Requested | 2. Concept
1001392 | Project 84 | Sub-Portfolio 7 | Project Manager 27 | On Hold | 2. Concept
1001420 | Project 87 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept
1001430 | Project 91 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept
1001493 | Project 101 | Sub-Portfolio 2 |  | On Hold | 2. Concept
1001498 | Project 102 | Sub-Portfolio 7 | Project Manager 35 | Requested | 2. Concept
1001566 | Project 106 | Sub-Portfolio 7 | Project Manager 27 | Requested | 2. Concept
1001602 | Project 108 | Sub-Portfolio 7 | Project Manager 27 | Requested | 2. Concept
1001617 | Project 110 | Sub-Portfolio 8 | Project Manager 22 | Open/Active | 3. Evaluate | Apr-2025 | Amber | Green | Green | 4027260 | 3649370.39 | 377889.61 | Amber | 6 |  |  | Amber | Green | Green | Amber | 1 |  |  | Green
1001647 | Project 114 | Sub-Portfolio 4 | Project Manager 20 | Open/Active | 3. Evaluate | Apr-2025 | Amber | Amber | Green | 259814 | 152580.98 | 107233.02 | Amber |  |  |  | Green | Green | Green | Amber |  |  |  | Green
1001755 | Project 116 | Sub-Portfolio 4 | Project Manager 36 | Requested | 2. Concept | [8 empty] | 1 | [6 empty] | 1
1001802 | Project 130 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept
1001816 | Project 135 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept
1001817 | Project 136 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept
1001818 | Project 137 | Sub-Portfolio 7 | Project Manager 7 | On Hold | 2. Concept
1001821 | Project 140 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept
1001822 | Project 141 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept
1001829 | Project 144 | Sub-Portfolio 7 | Project Manager 35 | Requested | 2. Concept
1001857 | Project 146 | Sub-Portfolio 7 |  | Requested | 2. Concept
1001860 | Project 147 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept
1001861 | Project 148 | Sub-Portfolio 2 |  | Requested | 2. Concept
1001863 | Project 149 | Sub-Portfolio 4 | Project Manager 3 | Requested | 2. Concept
1001866 | Project 150 | Sub-Portfolio 4 | Project Manager 3 | Requested | 2. Concept
1001870 | Project 152 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept
1001871 | Project 153 | Sub-Portfolio 7 |  | Requested | 2. Concept
1001872 | Project 154 | Sub-Portfolio 4 | Project Manager 20 | Requested | 2. Concept
1001875 | Project 156 | Sub-Portfolio 8 | Project Manager 25 | Requested | 2. Concept
1001876 | Project 157 | Sub-Portfolio 8 | Project Manager 25 | Requested | 2. Concept
1001877 | Project 158 | Sub-Portfolio 8 | Project Manager 25 | Requested | 2. Concept
1001878 | Project 159 | Sub-Portfolio 8 | Project Manager 16 | Requested | 2. Concept
1001879 | Project 160 | Sub-Portfolio 8 | Project Manager 31 | Requested | 2. Concept
1001880 | Project 161 | Sub-Portfolio 8 |  | Requested | 2. Concept
1001881 | Project 162 | Sub-Portfolio 8 | Project Manager 12 | Cancelled | 2. Concept
1001882 | Project 163 | Sub-Portfolio 7 |  | Requested | 2. Concept
1001891 | Project 164 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept
1001896 | Project 166 | Sub-Portfolio 7 |  | Requested | 2. Concept
1001898 | Project 167 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept
1000292 | Project 1 | Sub-Portfolio 4 | Project Manager 3 | Prepare for Closure | 7. Closure | 11 Oct 24 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000293 | Project 2 | Sub-Portfolio 4 | Project Manager 18 | Prepare for Closure | 6. Implement | 19 Feb 24 - 01 Mar 24 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000294 | Project 3 | Sub-Portfolio 4 | Project Manager 4 | Open/Active | 3. Evaluate | 02 May 25 | Green | Green | Green |  |  |  | Green | 8 |  | 30 | Green | Green | Green | Amber | 1 |  |  | Green
1000297 | Project 6 | Sub-Portfolio 8 | Project Manager 22 | On Hold | 7. Closure | Aug-2024 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000298 | Project 7 | Sub-Portfolio 4 | Project Manager 38 | Open/Active | 6. Implement | 25 Apr 25 | Green | Green | Green | 400000 | 348920.99 | 51079.01 | Green | 56 | 6 | 4 | Green | Green | Green | Green |  |  |  | Green
1000299 | Project 8 | Sub-Portfolio 4 | Project Manager 36 | Completed | 6. Implement | 02 Aug 24 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000300 | Project 9 | Sub-Portfolio 8 | Project Manager 12 | Prepare for Closure | 7. Closure | Sep-2024 | Green | Green | Green |  |  |  | Green | 2 |  |  | Green | Green | Green | Green |  |  |  | Green
1000301 | Project 10 | Sub-Portfolio 7 | Project Manager 17 | Open/Active | 6. Implement | Apr-2025 | Green | Green | Green |  |  |  | Green | 6 |  |  | Green | Green | Green | Green |  |  |  | Green
1000302 | Project 11 | Sub-Portfolio 7 | Project Manager 17 | Open/Active | 6. Implement | Apr-2025 | Green | Green | Green | 505446 | 484120.18 | 21325.82 | Amber | 13 | 3 | 2 | Green | Green | Green | Green |  |  |  | Green
1000303 | Project 12 | Sub-Portfolio 4 | Project Manager 18 | Open/Active | 7. Closure | 01 Dec 23 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Amber |  |  |  | Green
1000304 | Project 13 | Sub-Portfolio 8 | Project Manager 22 | Prepare for Closure | 7. Closure | Apr-2025 | Green | Green | Green | 1520000 | 1030294.14 | 489705.86 | Green | 6 | 4 |  | Green | Green | Green | Green |  |  |  | Green
1000305 | Project 14 | Sub-Portfolio 8 | Project Manager 25 | Prepare for Closure | 7. Closure | Jun-2024 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000306 | Project 15 | Sub-Portfolio 5 | Project Manager 26 | Completed | 7. Closure | Jun-2024 | Green | Green | Green | [7 empty] | Green | Green |  | Green
1000308 | Project 17 | Sub-Portfolio 7 | Project Manager 4 | On Hold | 4. Analyse & Design | Apr-2025 | Green | Green | Green | 0 | 327688.57 | -327688.57 | Green | 14 |  |  | Green | Green | Green | Red |  |  |  | Red
1000309 | Project 18 | Sub-Portfolio 4 | Project Manager 3 | Completed | 7. Closure | 10 May 24 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000311 | Project 20 | Sub-Portfolio 8 | Project Manager 31 | Prepare for Closure | 4. Analyse & Design | Aug-2024 | Green | Green | Green |  |  |  | Green | 7 | 2 |  | Green | Green | Green | Green |  |  |  | Green
1000312 | Project 21 | Sub-Portfolio 7 | Project Manager 10 | Completed | 7. Closure | Jun-2024 | Green | Green | Green |  |  |  | Amber |  |  |  | Green | Green | Amber | Amber |  | 1 |  | Green
1000315 | Project 24 | Sub-Portfolio 7 | Project Manager 35 | Open/Active | 2. Concept | Oct-2023 | Green | Green | Green |  |  |  | Green | 2 |  |  | Green | Green | Green | Green |  |  |  | Green
1000316 | Project 25 | Sub-Portfolio 7 | Project Manager 38 | Completed | 7. Closure | May-2024 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000840 | Project 27 | Sub-Portfolio 7 | Project Manager 38 | Requested | 2. Concept | Apr-2024 | Green | Green | Green |  |  |  | Green | 15 |  |  | Green | Green | Green | Green |  |  |  | Green
1000841 | Project 28 | Sub-Portfolio 7 | Project Manager 38 | On Hold | 3. Evaluate | Feb-2024 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000869 | Project 29 | Sub-Portfolio 7 | Project Manager 17 | Open/Active | 4. Analyse & Design | Apr-2025 | Green | Green | Green | 632037.92 | 251129.28 | 380908.64 | Green | 22 |  |  | Green | Green | Green | Green |  |  |  | Green
1000872 | Project 31 | Sub-Portfolio 8 | Project Manager 7 | Requested | 2. Concept | May-2024 | Green | Green | Green |  |  |  | Amber | 5 |  |  | Green | Green | Green | Green |  |  |  | Green | 1 | 1
1000884 | Project 32 | Sub-Portfolio 4 | Project Manager 18 | Cancelled | 2. Concept | 01 Dec 23 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000918 | Project 33 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept | 01 Dec 23 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000921 | Project 34 | Sub-Portfolio 4 | Project Manager 18 | Cancelled | 2. Concept | 01 Dec 23 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000924 | Project 36 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept | 01 Dec 23 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Red |  |  |  | Green
1000927 | Project 39 | Sub-Portfolio 4 | Project Manager 18 | Cancelled | 2. Concept | 01 Dec 23 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000986 | Project 41 | Sub-Portfolio 7 | Project Manager 17 | Requested | 3. Evaluate | 05 Jul 24 | Green | Green | Amber |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1000987 | Project 42 | Sub-Portfolio 7 | Project Manager 29 | Open/Active | 4. Analyse & Design | Apr-2025 | Green | Green | Green |  |  |  | Amber | 21 | 5 | 4 | Green | Green | Green | Green | 1 |  |  | Green
1000990 | Project 43 | Sub-Portfolio 8 | Project Manager 12 | Completed | 7. Closure | Jun-2024 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1001122 | Project 45 | Sub-Portfolio 4 | Project Manager 38 | Prepare for Closure | 7. Closure | 07 Mar 25 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1001328 | Project 61 | Sub-Portfolio 8 | Project Manager 25 | Open/Active | 6. Implement | Apr-2025 | Green | Green | Green | 3210000 | 2503340.8 | 706659.2 | Green | 55 |  |  | Amber | Green | Green | Green | 2 |  |  | Green | 1
1001347 | Project 62 | Sub-Portfolio 8 | Project Manager 16 | Open/Active | 3. Evaluate | 02 May 25 | Green | Green | Green | 250000 | 249551.41 | 448.59 | Green | 20 | 4 |  | Green | Green | Green | Green |  |  |  | Green
1001350 | Project 64 | Sub-Portfolio 8 | Project Manager 25 | Open/Active | 6. Implement | Feb-2025 | Green | Green | Green | 2355000 | 1045813.04 | 1309186.96 | Green | 26 | 3 |  | Green | Green | Green | Green |  |  |  | Green
1001353 | Project 66 | Sub-Portfolio 8 | Project Manager 12 | Open/Active | 3. Evaluate | 02 May 25 | Green | Green | Green | 1336934 | 1195549.44 | 141384.56 | Green | 33 | 4 |  | Green | Green | Green | Green |  |  |  | Green
1001355 | Project 68 | Sub-Portfolio 8 | Project Manager 12 | Open/Active | 3. Evaluate | 02 May 25 | Green | Green | Green |  |  |  | Green | 27 | 3 |  | Amber | Green | Green | Amber |  | 1 |  | Green | 1 | 1
1001360 | Project 73 | Sub-Portfolio 8 | Project Manager 21 | Open/Active | 4. Analyse & Design | 25 Apr 25 | Green | Green | Green | 250000 | 183635.29 | 66364.71 | Amber | 37 |  |  | Green | Green | Green | Green |  |  |  | Green
1001361 | Project 74 | Sub-Portfolio 8 | Project Manager 28 | Open/Active | 3. Evaluate | Apr-2025 | Green | Green | Green | 435535 | 501049.11 | -65514.11 | Green | 29 | 1 |  | Green | Green | Green | Green | 1 |  |  | Green
1001362 | Project 75 | Sub-Portfolio 4 | Project Manager 18 | Open/Active | 3. Evaluate | Apr-2025 | Green | Green | Green | 1600000 | 1435401.63 | 164598.37 | Green | 21 | 22 |  | Green | Green | Green | Green |  |  |  | Green
1001363 | Project 76 | Sub-Portfolio 4 | Project Manager 38 | Open/Active | 3. Evaluate | 25 Apr 25 | Green | Green | Green | 339000 | 325032.26 | 13967.74 | Green | 41 |  |  | Green | Green | Green | Green |  |  |  | Green
1001364 | Project 77 | Sub-Portfolio 4 | Project Manager 38 | Open/Active | 3. Evaluate | May-2025 | Green | Green | Green | 751000 | 613476.13 | 137523.87 | Green | 20 | 8 |  | Green | Green | Green | Green |  |  |  | Green
1001367 | Project 78 | Sub-Portfolio 4 | Project Manager 39 | Requested | 2. Concept | 26 Jul 24 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1001373 | Project 79 | Sub-Portfolio 7 | Project Manager 38 | Open/Active | 4. Analyse & Design | Apr-2025 | Green | Green | Green | 208506.87 | 189116.56 | 19390.31 | Green | 10 |  |  | Green | Green | Green | Green | 3 | 1 |  | Green
1001374 | Project 80 | Sub-Portfolio 8 | Project Manager 25 | Requested | 2. Concept | Jun-2024 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1001375 | Project 81 | Sub-Portfolio 8 | Project Manager 25 | Requested | 2. Concept | Jun-2024 | Green | Green | Green |  |  |  | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
1001399 | Project 85 | Sub-Portfolio 4 | Project Manager 14 | Prepare for Closure | 7. Closure | 31 Jan 25 | Green | Green | Green | 0 | 0 | 0 | Green | 34 |  |  | Green | Green | Green | Green |  |  |  | Green
1001440 | Project 93 | Sub-Portfolio 8 | Project Manager 13 | Open/Active | 3. Evaluate | Apr-2025 | Green | Green | Green | 990000 | 1480046.87 | -490046.87 | Green | 20 | 2 |  | Amber | Green | Green | Green | 1 |  |  | Green
1001774 | Project 119 | Sub-Portfolio 4 | Project Manager 4 | Requested | 2. Concept | Mar-2025 | Green | Green | Green |  |  |  | Amber |  |  |  | Green | Green | Green | Green |  |  |  | Green
1001775 | Project 120 | Sub-Portfolio 4 | Project Manager 14 | Requested | 2. Concept | Apr-2025 | Green | Green | Green |  |  |  | Green | 26 |  |  | Green | Green | Green | Green |  |  |  | Green
1001776 | Project 121 | Sub-Portfolio 4 | Project Manager 14 | Requested | 2. Concept | Apr-2025 | Green | Green | Green |  |  |  | Green | 22 |  |  | Amber | Green | Green | Green |  |  |  | Amber
1001825 | Project 143 | Sub-Portfolio 4 | Project Manager 18 | Requested | 2. Concept | Apr-2025 | Green | Green | Green |  |  |  | Amber |  |  |  | Green | Green | Green | Green |  |  |  | Green
1001834 | Project 145 | Sub-Portfolio 7 | Project Manager 7 | Requested | 2. Concept | Apr-2025 | Green | Green | Green | 350000 | 207481.57 | 142518.43 | Green |  |  |  | Green | Green | Green | Green |  |  |  | Green
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
All updates to commentary should be made in Planview, and the data re-exported
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## PV_Meta
Metadata columnset from Planview
2025-05-07
Columnset: 00 Data Quality
Report Date
2025-05-01
167
Proj Name | PSR Date | Name | Work ID # | Work Type | Sub-Portfolio | Line of Business | Project Manager/Owner | Sponsor. | Business Priority | Methodology | Part Of Program? | Capitalization Flag | Work Status | Current Gate | Stage | Status Reporting Frequency | Reported - This Period (d) | Reporting Period | Reporting Period - Fortnightly | Reporting Period - Weekly | Overall Status Assessment | Scope Status Assessment | Cost Status Assessment | Schedule Status Assessment | Resourcing Status Assessment | Benefit Status Assessment | OCM Status Assessment | Quality Status Assessment | Risks Status Assessment | Issues Status Assessment | Baseline Start | Baseline Finish | Baseline Duration (d) | Duration at Complete (d) | Actual/Schedule Start | Actual/Schedule Finish | Schedule Start | Schedule Finish | Actual Start | Actual Finish | Late Finish | Percent Complete | Milestones, Total | Milestones,Completed | Milestones,Remain | Milestones, Scheduled | Milestones, Late | Milestones, Missed | Milestones, On Time | Changes, Active | Changes, Total | Risks, Active | Risks, Total | Issues, Active | Issues, Total
Project 1 | 11 Oct 24 | Project 1 | 1000292 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 3 | Sponsor 19 |  | Waterfall | No | Capital | Prepare for Closure | Gate 2 | 7. Closure | Weekly |  | Aug-2024 | 06 Jul 24 - 19 Jul 24 | 11 Oct 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2023-07-03 | 2024-04-26 08:00 | 199 | 390 | 2023-07-03 | 2025-02-05 17:00 | 2023-10-16 08:00 | 2025-02-05 17:00 | 2023-07-03 |  | 2024-03-26 17:00 | 13 | 10 | 10 |  | 10 | [6 empty] | 5 | 1 | 1
Project 2 | 19 Feb 24 - 01 Mar 24 | Project 2 | 1000293 | Project | Sub-Portfolio 4 | Line of Business 7 | Project Manager 18 | Sponsor 32 |  | Waterfall | No | Capital | Prepare for Closure | Gate 2 | 6. Implement | Fortnightly |  |  | 19 Feb 24 - 01 Mar 24 | 12 Jan 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2022-08-16 | 2024-02-29 17:00 | 385 | 467 | 2022-08-16 | 2024-06-28 17:00 | 2024-02-12 08:00 | 2024-06-28 17:00 | 2022-08-16 |  | 2024-03-15 17:00 | 80 | 11 | 11 |  | 11 | [6 empty] | 5 |  | 1
Project 3 | 02 May 25 | Project 3 | 1000294 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 4 | Sponsor 44 |  | Waterfall | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 02 May 25 | Green | Green | Green | Green | Green | Green | Green |  | Amber | Green | 2021-11-01 | 2026-02-05 17:00 | 1062 | 1228 | 2021-11-01 | 2026-09-30 17:00 | 2023-10-16 08:00 | 2026-09-30 17:00 | 2021-11-01 |  | 2025-12-19 17:00 | 79 | 91 | 38 | 53 | 83 | 36 | 46 | 4 |  |  | 6 | 7 | 1 | 1
Project 4 | 06 Dec 24 | Project 4 | 1000295 | Minor Work | Sub-Portfolio 4 | Line of Business 7 | Project Manager 15 | Sponsor 2 |  | Waterfall | No | Capital | Requested | Gate 1 | 6. Implement | Weekly |  |  |  | 06 Dec 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2022-08-29 | 2024-12-20 17:00 | 582 | 703 | 2022-08-29 | 2025-06-30 17:00 | 2024-05-01 09:00 | 2025-06-30 17:00 | 2022-08-29 |  | 2025-06-27 17:00 | 99 | 34 | 31 | 3 | 34 | 3 | 3 |  |  |  | 1 | 22 |  | 3
Project 5 | Apr-2025 | Project 5 | 1000296 | Project | Sub-Portfolio 7 | Line of Business 4 | Project Manager 8 | Sponsor 21 |  | Hybrid | Yes | Capex & Opex | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Apr-2025 |  |  | Red | Amber | Green | Red | Green | Green | Green |  | Amber | Green | 2019-07-01 | 2028-06-02 12:00 | 2262.5 | 2658 | 2019-07-01 | 2029-12-21 17:00 | 2019-10-18 08:00 | 2029-12-21 17:00 | 2019-07-01 |  | 2030-06-26 17:00 | 15 | 163 | 65 | 98 | 70 | 8 | 7 | 85 |  | 1 | 3 | 7 | 1 | 2
Project 6 | Aug-2024 | Project 6 | 1000297 | Project | Sub-Portfolio 8 | Line of Business 7 | Project Manager 22 | Sponsor 18 |  | Waterfall | Yes | Capital | On Hold | Gate 3 | 7. Closure | Monthly |  | Aug-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2020-07-01 | 2029-07-06 11:26 | 2276.4 | 2276.4 | 2020-07-01 | 2029-07-06 11:26 |  |  | 2020-07-01 |  |  | 100 | 29 | 29 |  | 29 | [6 empty] | 6 |  | 2
Project 7 | 25 Apr 25 | Project 7 | 1000298 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 38 | Sponsor 19 |  | Waterfall | No | Capital | Open/Active | Gate 3 | 6. Implement | Weekly |  |  |  | 25 Apr 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2022-08-16 | 2025-06-30 17:00 | 712 | 759 | 2022-08-16 | 2025-09-03 17:00 | 2022-11-24 08:00 | 2025-09-03 17:00 | 2022-08-16 |  | 2025-06-27 17:00 | 16 | 20 | 12 | 8 | 13 | 6 | 1 |  |  |  | 1 | 4 |  | 1
Project 8 | 02 Aug 24 | Project 8 | 1000299 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 36 | Sponsor 19 |  | Waterfall | Yes | Capital | Completed | Gate 3 | 6. Implement | Weekly |  |  | 27 May 24 - 07 Jun 24 | 02 Aug 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2022-11-15 | 2024-11-29 17:00 | 511 | 511 | 2022-11-15 | 2024-11-29 17:00 |  |  | 2022-11-15 | 2024-11-29 17:00 |  | 100 | 23 | 23 |  | 23 | [6 empty] | 3 |  | 5
Project 9 | Sep-2024 | Project 9 | 1000300 | Project | Sub-Portfolio 8 | Line of Business 7 | Project Manager 12 | Sponsor 18 |  | Waterfall | Yes | Capital | Prepare for Closure | Gate 2 | 7. Closure | Monthly |  | Sep-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2022-12-16 17:00 | 2024-10-31 17:00 | 466 | 481.8 | 2022-12-16 17:00 | 2024-11-22 15:00 | 2024-06-11 08:00 | 2024-11-22 15:00 | 2022-12-16 17:00 |  | 2024-11-01 17:00 | 93 | 64 | 64 |  | 64 | [6 empty] | 8 |  | 9
Project 10 | Apr-2025 | Project 10 | 1000301 | Project | Sub-Portfolio 7 | Line of Business 16 | Project Manager 17 | Sponsor 25 |  | Waterfall | No | Opex | Open/Active | Gate 1 | 6. Implement | Monthly |  | Apr-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2021-03-18 | 2025-10-31 17:00 | 1168 | 1168 | 2021-03-18 | 2025-10-31 17:00 | 2021-03-18 08:00 | 2025-10-31 17:00 | 2021-03-18 |  | 2025-06-02 17:00 | 40 | 74 | 64 | 10 | 64 |  |  | 10 |  |  | 2 | 2 | 1 | 4
Project 11 | Apr-2025 | Project 11 | 1000302 | Project | Sub-Portfolio 7 | Line of Business 7 | Project Manager 17 | Sponsor 23 |  | Hybrid | No | Opex | Open/Active | Gate 1 | 6. Implement | Monthly |  | Apr-2025 |  |  | Green | Green | Green | Amber | Green | Green | Green |  | Green | Green | 2019-04-09 | 2025-06-30 17:00 | 1587 | 1713 | 2019-04-09 | 2025-12-24 17:00 | 2019-04-09 08:00 | 2025-12-24 17:00 | 2019-04-09 |  | 2025-06-02 17:00 | 13 | 122 | 99 | 23 | 62 | 3 | 3 |  |  |  | 2 | 8 |  | 4
Project 12 | 01 Dec 23 | Project 12 | 1000303 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 18 | Sponsor 3 |  | Waterfall | No | Capital | Open/Active | Gate 3 | 7. Closure | Weekly |  |  |  | 01 Dec 23 | Green | Green | Green | Green | Green | Green | Green |  | Amber | Green | 2022-10-04 | 2025-10-01 17:00 | 744 | 744 | 2022-10-04 | 2025-10-01 17:00 |  |  | 2022-10-04 | 2025-10-01 17:00 |  | 100 | 19 | 19 |  | 19
Project 13 | Apr-2025 | Project 13 | 1000304 | Project | Sub-Portfolio 8 | Line of Business 7 | Project Manager 22 | Sponsor 18 |  | Hybrid | Yes | Capital | Prepare for Closure | Gate 2 | 7. Closure | Monthly |  | Apr-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2023-02-13 17:00 | 2025-02-14 17:00 | 492 | 554 | 2023-02-13 17:00 | 2025-05-16 17:00 | 2023-07-03 08:00 | 2025-05-16 17:00 | 2023-02-13 17:00 |  |  | 35 | 75 | 71 | 4 | 80 | 4 | 9 |  |  |  |  | 6 |  | 6
Project 14 | Jun-2024 | Project 14 | 1000305 | Project | Sub-Portfolio 8 | Line of Business 7 | Project Manager 25 | Sponsor 18 |  | Hybrid | Yes | Capital | Prepare for Closure | Gate 2 | 7. Closure | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2020-10-01 | 2024-04-10 17:00 | 900 | 1098 | 2020-10-01 | 2025-01-31 17:00 | 2024-01-08 09:00 | 2025-01-31 17:00 | 2020-10-01 |  | 2025-06-30 17:00 | 17 | 15 | 15 |  | 6 | [6 empty] | 3 |  | 2
Project 15 | Jun-2024 | Project 15 | 1000306 | Light Project | Sub-Portfolio 5 | Line of Business 7 | Project Manager 26 | Sponsor 43 |  | Hybrid | No | Opex | Completed | Gate 3 | 7. Closure | Monthly |  | Jun-2024 |  |  | Green | Green | Green |  | Green | Green |  |  | Green |  | 2018-01-01 08:00 | 2024-07-18 17:00 | 1687 | 1677 | 2018-01-12 17:00 | 2024-07-18 17:00 |  |  | 2018-01-12 17:00 | 2024-07-18 17:00 |  | 100 | 7 | 7 |  | 7
Project 16 | Apr-2025 | Project 16 | 1000307 | Project | Sub-Portfolio 7 | Line of Business 3 | Project Manager 34 | Sponsor 17 |  | Waterfall | Yes | Capex & Opex | Open/Active | Gate 1 | 5. Build & Test | Monthly |  | Apr-2025 |  |  | Red | Green | Red | Amber | Amber | Green | Green |  | Amber | Amber | 2019-06-04 08:00 | 2029-12-21 17:00 | 2677 | 2853.9 | 2018-09-28 09:00 | 2035-02-21 17:00 | 2018-09-28 09:00 | 2035-02-21 17:00 | 2021-06-14 17:00 |  | 2035-01-01 08:00 | 9 | 84 | 56 | 28 | 58 | 16 | 3 | 5 |  |  | 26 | 45 | 2 | 6
Project 17 | Apr-2025 | Project 17 | 1000308 | Project | Sub-Portfolio 7 | Line of Business 7 | Project Manager 4 | Sponsor 37 |  | Hybrid | No | Opex | On Hold | Gate 1 | 4. Analyse & Design | Monthly |  | Apr-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Red | Red | 2023-03-23 | 2024-11-07 08:00 | 404 | 729 | 2023-03-23 | 2026-03-17 17:00 | 2023-06-01 09:00 | 2026-03-17 17:00 | 2023-03-23 |  | 2026-03-18 08:00 | 6 | 71 | 28 | 43 | 31 | 23 | 23 |  |  |  |  | 23 |  | 7
Project 18 | 10 May 24 | Project 18 | 1000309 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 3 | Sponsor 19 |  | Waterfall | No | Capital | Completed | Gate 3 | 7. Closure | Weekly |  |  |  | 10 May 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2022-08-01 | 2024-11-06 17:00 | 570 | 570 | 2022-08-01 | 2024-11-06 17:00 |  |  | 2022-08-01 | 2024-11-06 17:00 |  | 100 | 17 | 17 |  | 17 | [6 empty] | 4 |  | 1
Project 19 | Apr-2025 | Project 19 | 1000310 | Project | Sub-Portfolio 8 | Line of Business 7 | Project Manager 6 | Sponsor 36 |  | Hybrid | No | Capex & Opex | Open/Active | Gate 1 | 5. Build & Test | Monthly |  | Apr-2025 |  | 14 Jun 24 | Amber | Green | Amber | Amber | Green | Green | Green |  | Amber | Amber | 2023-07-03 08:00 | 2029-12-21 17:00 | 1619 | 1619 | 2023-07-03 08:00 | 2029-12-21 17:00 | 2024-02-01 08:00 | 2029-12-21 17:00 | 2023-07-03 08:00 |  | 2026-05-08 11:08 | 21 | 203 | 104 | 99 | 173 | 18 | 70 | 81 |  |  | 21 | 28 | 3 | 5
Project 20 | Aug-2024 | Project 20 | 1000311 | Project | Sub-Portfolio 8 | Line of Business 7 | Project Manager 31 | Sponsor 18 |  | Agile | Yes | Capital | Prepare for Closure | Gate 2 | 4. Analyse & Design | Monthly |  | Aug-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2023-07-17 | 2024-02-16 17:00 | 143 | 437 | 2023-07-17 | 2025-05-01 08:00 | 2024-01-15 08:00 | 2025-05-01 08:00 | 2023-07-17 |  | 2024-09-25 08:00 | 58 | 35 | 33 | 2 | 22 | 2 | 2
Project 21 | Jun-2024 | Project 21 | 1000312 | Project | Sub-Portfolio 7 | Line of Business 3 | Project Manager 10 | Sponsor 17 |  | Agile | Yes | Capital | Completed | Gate 3 | 7. Closure | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Amber | Green | Green | Amber |  | Amber | Green | 2021-07-12 | 2024-11-25 17:00 | 858 | 858 | 2021-07-12 | 2024-11-25 17:00 |  |  | 2021-07-12 | 2024-11-25 17:00 |  | 100 | 27 | 27 |  | 27 | [5 empty] | 1 | 11 |  | 4
Project 22 | 0 | Project 22 | 1000313 | Project | Sub-Portfolio 1 | Line of Business 7 | Project Manager 32 | Sponsor 13 |  | Waterfall | No | Opex | Prepare for Closure | Gate 2 | 7. Closure | Monthly | [14 empty] | 2023-08-01 | 2024-05-30 17:00 | 203 | 203 | 2023-08-01 | 2024-05-30 17:00 | 2023-08-01 08:00 | 2024-05-30 17:00 | 2023-08-01 |  |  | 10 | 3 | 3 |  | 3
Project 23 | Apr-2025 | Project 23 | 1000314 | Project | Sub-Portfolio 7 | Line of Business 7 | Project Manager 33 | Sponsor 14 |  | Hybrid | Yes | Capital | Open/Active | Gate 1 | 6. Implement | Monthly |  | Apr-2025 |  |  | Amber | Green | Green | Amber | Amber | Green | Green |  | Amber | Amber | 2023-03-22 | 2025-08-11 17:00 | 588 | 588 | 2023-03-22 | 2025-08-11 17:00 | 2023-09-11 08:00 | 2025-08-11 17:00 | 2023-03-22 |  | 2025-06-30 17:00 | 26 | 85 | 66 | 19 | 66 | 2 | 1 | 17 |  |  |  | 1
Project 24 | Oct-2023 | Project 24 | 1000315 | Project | Sub-Portfolio 7 | Line of Business 7 | Project Manager 35 | Sponsor 24 |  | Waterfall |  |  | Open/Active |  | 2. Concept | Monthly |  | Oct-2023 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 1593 | 2021-04-19 | 2027-08-27 17:00 | 2023-10-03 09:00 | 2027-08-27 17:00 | 2021-04-19 |  | 2027-06-21 17:00 | 10 | 4 | 4
Project 25 | May-2024 | Project 25 | 1000316 | Project | Sub-Portfolio 7 | Line of Business 17 | Project Manager 38 | Sponsor 4 |  | Agile | No | Capital | Completed | Gate 3 | 7. Closure | Monthly |  | May-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2021-06-30 | 2024-05-31 17:00 | 742 | 742 | 2021-06-30 | 2024-05-31 17:00 |  |  | 2021-06-30 | 2024-05-31 17:00 |  | 100 | 19 | 19 |  | 19 | [6 empty] | 2 |  | 1
Project 26 | 0 | Project 26 | 1000838 | Project | Sub-Portfolio 7 | Line of Business 14 |  |  |  |  | No | Capital | On Hold |  | 2. Concept | Monthly | [17 empty] | 365 | 2025-07-01 08:00 | 2026-12-17 17:00 | 2025-07-01 08:00 | 2026-12-17 17:00 |  |  |  | 0
Project 27 | Apr-2024 | Project 27 | 1000840 | Project | Sub-Portfolio 7 | Line of Business 18 | Project Manager 38 | Sponsor 22 |  | Hybrid | No | Capital | Requested | Gate 0 | 2. Concept | Monthly |  | Apr-2024 |  | 01 Mar 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2023-02-01 08:00 | 2025-06-30 17:00 | 593 | 837 | 2023-02-01 08:00 | 2026-06-30 17:00 | 2023-02-01 08:00 | 2026-06-30 17:00 | 2024-07-09 17:00 |  | 2025-06-02 17:00 | 0 | 42 | 19 | 23 | 27 |  | 8 |  |  |  |  | 2 |  | 4
Project 28 | Feb-2024 | Project 28 | 1000841 | Project | Sub-Portfolio 7 | Line of Business 18 | Project Manager 38 |  |  |  | No | Opex | On Hold | Gate 0 | 3. Evaluate | Monthly |  | Feb-2024 |  | 26 Jan 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 115 | 2024-01-15 08:00 | 2024-06-28 17:00 | 2024-01-15 08:00 | 2024-06-28 17:00 |  |  |  | 0 | [10 empty] | 2 |  | 1
Project 29 | Apr-2025 | Project 29 | 1000869 | Project | Sub-Portfolio 7 |  | Project Manager 17 | Sponsor 50 |  | Hybrid | No | Capital | Open/Active | Gate 1 | 4. Analyse & Design | Monthly |  | Apr-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2021-07-01 17:00 | 2026-07-31 17:00 | 1271 | 1271 | 2021-07-01 17:00 | 2026-07-31 17:00 | 2023-11-01 08:00 | 2026-07-31 17:00 | 2021-07-01 17:00 |  | 2025-06-27 17:00 | 11 | 51 | 20 | 31 | 20 |  |  | 31 |  |  |  | 3 | 1 | 6
Project 30 | Feb-2024 | Project 30 | 1000871 | Project | Sub-Portfolio 8 |  | Project Manager 25 | Sponsor 18 |  |  | No | Capital | On Hold |  | 4. Analyse & Design | Monthly |  | Feb-2024 |  |  | Red | Amber | Red | Amber | Amber | Green | Green |  | Amber | Amber |  |  |  | 213 | 2023-11-13 08:00 | 2024-09-25 17:00 | 2023-11-13 08:00 | 2024-09-25 17:00 |  |  |  | 0 | [9 empty] | 5 | 5
Project 31 | May-2024 | Project 31 | 1000872 | Project | Sub-Portfolio 8 |  | Project Manager 7 |  |  |  | No | Opex | Requested |  | 2. Concept | Monthly |  | May-2024 |  |  | Green | Green | Green | Amber | Green | Green | Green |  | Green | Green |  |  |  | 450 | 2024-03-04 08:00 | 2025-12-22 17:00 | 2024-03-07 08:00 | 2025-12-22 17:00 | 2024-03-04 08:00 |  | 2025-06-02 17:00 | 40 | 72 | 68 | 4 | [8 empty] | 1 | 1
Project 32 | 01 Dec 23 | Project 32 | 1000884 | Light Project | Sub-Portfolio 4 | Line of Business 7 | Project Manager 18 | Sponsor 30 |  |  | No | Opex | Cancelled |  | 2. Concept | Weekly |  |  |  | 01 Dec 23 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 136 | 2023-09-11 08:00 | 2024-04-05 17:00 |  |  | 2023-09-11 08:00 |  |  | 100 | [7 empty] | 1 | 1
Project 33 | 01 Dec 23 | Project 33 | 1000918 | Project | Sub-Portfolio 4 | Line of Business 7 | Project Manager 18 |  |  |  | No | Capex & Opex | Requested |  | 2. Concept | Weekly |  |  |  | 01 Dec 23 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 160 | 2023-10-30 08:00 | 2024-06-28 17:00 | 2023-10-30 08:00 | 2024-06-28 17:00 |  |  |  | 0
Project 34 | 01 Dec 23 | Project 34 | 1000921 | Project | Sub-Portfolio 4 | Line of Business 7 | Project Manager 18 |  |  |  | No | Capex & Opex | Cancelled |  | 2. Concept | Weekly |  |  |  | 01 Dec 23 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 223 | 2023-08-01 08:00 | 2024-06-28 17:00 |  |  | 2023-08-01 08:00 | 2024-06-28 17:00 |  | 100
Project 35 |  | Project 35 | 1000923 | Application Support | Sub-Portfolio 5 |  | Project Manager 37 | [5 empty] | Open/Active | [20 empty] | 174.6 | 2023-11-01 09:00 | 2024-07-23 15:00 | 2023-11-01 09:00 | 2024-07-23 15:00 |  |  |  | 0
Project 36 | 01 Dec 23 | Project 36 | 1000924 | Project | Sub-Portfolio 4 | Line of Business 7 | Project Manager 18 |  |  |  | No | Opex | Requested |  | 2. Concept | Weekly |  |  |  | 01 Dec 23 | Green | Green | Green | Green | Green | Green | Green |  | Red | Green |  |  |  | 158 | 2023-09-01 08:00 | 2024-04-30 17:00 | 2023-09-01 08:00 | 2024-04-30 17:00 |  |  |  | 0
Project 37 | 0 | Project 37 | 1000925 | Application Support | Sub-Portfolio 5 |  | Project Manager 26 | [5 empty] | Open/Active |  |  | Weekly | [17 empty] | 139.9 | 2023-11-27 09:00 | 2024-06-28 17:00 | 2023-11-27 09:00 | 2024-06-28 17:00 |  |  |  | 0
Project 38 | 28 Feb 25 | Project 38 | 1000926 | Service | Sub-Portfolio 4 | Line of Business 8 | Project Manager 18 |  | Important |  |  | Capex & Opex | Requested |  |  | Weekly |  |  |  | 28 Feb 25 | Green | Amber | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 199 | 2024-10-01 08:00 | 2025-07-28 17:00 | 2024-10-01 08:00 | 2025-07-28 17:00 |  |  |  | 0
Project 39 | 01 Dec 23 | Project 39 | 1000927 | Project | Sub-Portfolio 4 | Line of Business 7 | Project Manager 18 |  |  |  | No | Capex & Opex | Cancelled |  | 2. Concept | Weekly |  |  |  | 01 Dec 23 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 200 | 2023-09-01 08:00 | 2024-06-28 17:00 |  |  | 2023-09-01 08:00 | 2024-06-28 17:00 |  | 100
Project 40 | Mar-2024 | Project 40 | 1000962 | Minor Work | Sub-Portfolio 7 | Line of Business 15 | Project Manager 27 | Sponsor 29 |  | Hybrid |  |  | Prepare for Closure |  | 2. Concept | Monthly |  | Mar-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 161.9 | 2024-01-11 09:00 | 2024-08-30 17:00 | 2024-01-11 09:00 | 2024-08-30 17:00 | 2024-03-14 08:00 |  |  | 36
Project 41 | 05 Jul 24 | Project 41 | 1000986 | Project | Sub-Portfolio 7 | Line of Business 10 | Project Manager 17 |  |  |  | No | Opex | Requested |  | 3. Evaluate | Weekly |  |  |  | 05 Jul 24 | Green | Green | Amber | Green | Green | Green | Green |  | Green | Green |  |  |  | 234 | 2023-12-18 08:00 | 2024-11-29 17:00 | 2023-12-18 08:00 | 2024-11-29 17:00 |  |  |  | 0
Project 42 | Apr-2025 | Project 42 | 1000987 | Project | Sub-Portfolio 7 | Line of Business 22 | Project Manager 29 | Sponsor 51 |  | Hybrid | No | Capex & Opex | Open/Active | Gate 1 | 4. Analyse & Design | Monthly |  | Apr-2025 |  |  | Green | Green | Green | Amber | Green | Green | Green |  | Green | Green | 2024-04-19 17:00 | 2027-02-26 17:00 | 698 | 698 | 2024-04-19 17:00 | 2027-02-26 17:00 | 2024-07-01 09:00 | 2027-02-26 17:00 | 2024-04-19 17:00 |  | 2025-06-02 17:00 | 31 | 69 | 42 | 27 | 49 | 5 | 7 | 22 |  |  | 2 | 7 |  | 2
Project 43 | Jun-2024 | Project 43 | 1000990 | Project | Sub-Portfolio 8 | Line of Business 17 | Project Manager 12 | Sponsor 18 |  | Waterfall | No | Capex & Opex | Completed | Gate 3 | 7. Closure | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2023-12-18 08:00 | 2024-05-15 12:00 | 93.5 | 93.5 | 2023-12-18 08:00 | 2024-05-15 12:00 |  |  | 2023-12-18 08:00 | 2024-05-15 12:00 |  | 100 | [10 empty] | 1 |  | 2
Project 44 | May-2024 | Project 44 | 1001051 | Minor Work | Sub-Portfolio 1 | Line of Business 21 | Project Manager 7 | Sponsor 34 | High |  |  | Capital | Requested |  |  | Monthly |  | May-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 121.1 | 2024-02-01 09:00 | 2024-07-25 09:53 | 2024-02-01 09:00 | 2024-07-25 09:53 | 2024-02-01 09:00 |  |  | 51 | 5 | 5 | [8 empty] | 1 |  | 3
Project 45 | 07 Mar 25 | Project 45 | 1001122 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 38 | Sponsor 1 |  | Waterfall | No | Capital | Prepare for Closure | Gate 2 | 7. Closure | Weekly |  |  |  | 07 Mar 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2023-12-12 08:00 | 2025-03-10 17:00 | 298 | 292 | 2023-12-12 08:00 | 2025-02-28 17:00 | 2023-12-12 08:00 | 2025-02-28 17:00 | 2024-03-22 17:00 |  | 2025-06-02 17:00 | 57 | 75 | 74 | 1 | 75 |  | 1 | 1 |  |  |  | 4 |  | 2
Project 46 | 0 | Project 46 | 1001138 | Application Support | Sub-Portfolio 5 |  |  |  | High |  |  |  | Requested |  |  | Weekly | [17 empty] | 115 | 2024-01-15 08:00 | 2024-06-28 17:00 | 2024-01-15 08:00 | 2024-06-28 17:00 |  |  |  | 0
Project 47 | 0 | Project 47 | 1001171 | Minor Work | Sub-Portfolio 4 | Line of Business 6 | Project Manager 18 | Sponsor 38 | Important |  | No | Capital | Requested |  | 2. Concept | Weekly | [17 empty] | 85.9 | 2024-02-26 09:00 | 2024-06-28 17:00 | 2024-02-26 09:00 | 2024-06-28 17:00 |  |  |  | 0
Project 48 | 0 | Project 48 | 1001239 | Minor Work | Sub-Portfolio 3 |  | Project Manager 13 |  | Low | Waterfall | No | Capital | Completed | Gate 3 | 7. Closure | Weekly | [14 empty] | 2024-04-02 08:00 | 2024-07-29 17:00 | 83 | 83 | 2024-04-02 08:00 | 2024-07-29 17:00 |  |  | 2024-04-02 08:00 | 2024-07-29 17:00 |  | 100 | 9 | 9 |  | 9 | [7 empty] | 1 | 1
Project 49 | 0 | Project 49 | 1001242 | Project | Sub-Portfolio 7 | [7 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 442 | 2024-03-18 08:00 | 2025-12-24 17:00 | 2024-03-18 08:00 | 2025-12-24 17:00 |  |  |  | 0
Project 50 | 0 | Project 50 | 1001269 | Project | Sub-Portfolio 7 | Line of Business 2 | Project Manager 35 | Sponsor 14 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 86 | 2024-03-25 08:00 | 2024-07-26 17:00 | 2024-03-25 08:00 | 2024-07-26 17:00 |  |  |  | 0
Project 51 | 0 | Project 51 | 1001271 | Minor Work | Sub-Portfolio 4 | Line of Business 12 | Project Manager 23 |  | High |  |  |  | Requested |  |  | Monthly | [25 empty] | 0
Project 52 | 0 | Project 52 | 1001273 | Minor Work | Sub-Portfolio 4 | Line of Business 12 | Project Manager 23 |  | Medium |  |  |  | Requested |  |  | Monthly | [25 empty] | 0
Project 53 | 0 | Project 53 | 1001274 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 23 | [5 empty] | Requested |  | 2. Concept | Monthly | [25 empty] | 0
Project 54 | 0 | Project 54 | 1001275 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 23 | [5 empty] | Requested |  | 2. Concept | Monthly | [25 empty] | 0
Project 55 | Apr-2025 | Project 55 | 1001276 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 20 | Sponsor 6 |  |  | No | Capital | Requested |  | 2. Concept | Monthly |  | Apr-2025 |  |  | Amber | Amber | Green | Amber | Green | Green | Green |  | Amber | Green |  |  |  | 179 | 2024-10-01 08:00 | 2025-06-30 17:00 | 2024-10-01 08:00 | 2025-06-30 17:00 |  |  | 2025-06-03 08:00 | 0 | 31 |  | 31 | [6 empty] | 1 | 1
Project 56 | 0 | Project 56 | 1001277 | Project | Sub-Portfolio 7 | Line of Business 13 | Project Manager 27 |  |  |  | No | Capital | On Hold |  | 2. Concept | Monthly | [17 empty] | 993.9 | 2024-08-14 09:00 | 2028-08-07 17:00 | 2024-08-14 09:00 | 2028-08-07 17:00 |  |  |  | 0
Project 57 | 0 | Project 57 | 1001279 | Project | Sub-Portfolio 7 | Line of Business 13 | Project Manager 1 |  |  |  |  | Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 200 | 2024-03-11 08:00 | 2024-12-20 17:00 | 2024-03-11 08:00 | 2024-12-20 17:00 |  |  |  | 0
Project 58 | 0 | Project 58 | 1001280 | Light Project | Sub-Portfolio 7 | Line of Business 20 | Project Manager 27 | [5 empty] | Cancelled |  | 2. Concept | Monthly | [17 empty] | 76 | 2024-03-11 08:00 | 2024-06-28 17:00 |  |  | 2024-03-11 08:00 | 2024-06-28 17:00 |  | 100
Project 59 | Apr-2025 | Project 59 | 1001282 | Project | Sub-Portfolio 7 |  | Project Manager 14 | Sponsor 7 |  | Agile | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Apr-2025 |  |  | Red | Amber | Amber | Amber | Amber | Green | Green |  | Red | Amber | 2024-04-24 17:00 | 2026-02-16 16:00 | 440.9 | 440.9 | 2024-04-24 17:00 | 2026-02-16 16:00 | 2024-09-02 08:00 | 2026-02-16 16:00 | 2024-04-24 17:00 |  | 2025-06-02 17:00 | 25 | 59 | 44 | 15 | 48 | 6 | 4 | 9 |  |  | 3 | 12 | 2 | 9
Project 60 | Jun-2024 | Project 60 | 1001299 | Minor Work | Sub-Portfolio 7 | Line of Business 20 | Project Manager 38 |  |  |  | No | Capital | Requested |  | 2. Concept | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 116 | 2024-03-18 08:00 | 2024-08-30 17:00 | 2024-03-18 08:00 | 2024-08-30 17:00 | 2024-03-18 08:00 |  |  | 29
Project 61 | Apr-2025 | Project 61 | 1001328 | Project | Sub-Portfolio 8 | Line of Business 24 | Project Manager 25 | Sponsor 18 |  | Agile | No | Capital | Open/Active | Gate 1 | 6. Implement | Monthly |  | Apr-2025 |  |  | Green | Green | Green | Green | Amber | Green | Green |  | Green | Green | 2024-03-13 17:00 | 2025-11-03 17:00 | 407 | 407 | 2024-03-13 17:00 | 2025-11-03 17:00 | 2024-03-25 08:00 | 2025-11-03 17:00 | 2024-03-13 17:00 |  | 2025-06-02 17:00 | 10 | 94 | 77 | 17 | 77 |  |  | 17 | 1 | 1 | 2 | 7 | 2 | 4
Project 62 | 02 May 25 | Project 62 | 1001347 | Project | Sub-Portfolio 8 | Line of Business 7 | Project Manager 16 | Sponsor 18 |  | Agile | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 02 May 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-09-02 17:00 | 2025-06-25 17:00 | 196 | 198 | 2024-09-02 17:00 | 2025-06-27 17:00 | 2025-01-24 17:00 | 2025-06-27 17:00 | 2024-09-02 17:00 |  | 2026-06-30 17:00 | 8 | 30 | 6 | 24 | 30 | 4 | 24 | 20 |  |  |  | 3
Project 63 | 02 May 25 | Project 63 | 1001349 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 18 | Sponsor 19 |  | Agile | No | Capex & Opex | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 02 May 25 | Amber | Green | Amber | Amber | Amber | Green | Green |  | Amber | Amber | 2024-03-26 17:00 | 2025-08-01 08:00 | 332 | 332 | 2024-03-26 17:00 | 2025-08-01 08:00 | 2024-07-01 08:00 | 2025-08-01 08:00 | 2024-03-26 17:00 |  | 2025-06-27 17:00 | 15 | 54 | 19 | 35 | 43 | 22 | 24 | 12 |  |  | 3 | 5 | 1 | 1
Project 64 | Feb-2025 | Project 64 | 1001350 | Project | Sub-Portfolio 8 | Line of Business 13 | Project Manager 25 | Sponsor 18 |  | Agile | No | Capital | Open/Active | Gate 1 | 6. Implement | Monthly |  | Feb-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-07-01 08:00 | 2025-04-17 17:00 | 197 | 204 | 2024-07-01 08:00 | 2025-05-01 17:00 | 2024-07-01 08:00 | 2025-05-01 17:00 | 2024-09-06 17:00 |  | 2025-06-02 17:00 | 2 | 49 | 46 | 3 | 49 | 3 | 3 |  |  | 1 |  | 10 |  | 3
Project 65 | Apr-2025 | Project 65 | 1001351 | Project | Sub-Portfolio 8 | Line of Business 19 | Project Manager 29 | Sponsor 10 |  | Hybrid | No | Capital | Open/Active | Gate 1 | 6. Implement | Monthly |  | Apr-2025 |  |  | Amber | Green | Amber | Amber | Green | Green | Green |  | Green | Green | 2024-08-01 17:00 | 2025-06-30 17:00 | 221 | 221 | 2024-08-01 17:00 | 2025-06-30 17:00 | 2024-08-26 08:00 | 2025-06-30 17:00 | 2024-08-01 17:00 |  | 2025-06-02 17:00 | 34 | 72 | 60 | 12 | 61 |  | 4 | 11 |  |  | 2 | 7 |  | 1
Project 66 | 02 May 25 | Project 66 | 1001353 | Project | Sub-Portfolio 8 |  | Project Manager 12 |  |  | Waterfall | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 02 May 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-05-10 17:00 | 2025-08-29 17:00 | 323 | 323 | 2024-05-10 17:00 | 2025-08-29 17:00 | 2024-07-01 08:00 | 2025-08-29 17:00 | 2024-05-10 17:00 |  | 2025-06-30 08:00 | 27 | 66 | 46 | 20 | 50 | 4 | 4 | 16 |  |  | 3 | 8
Project 67 | 0 | Project 67 | 1001354 | Project | Sub-Portfolio 8 |  | Project Manager 2 | Sponsor 18 |  |  | No | Opex | Cancelled |  | 2. Concept | Weekly | [25 empty] | 0
Project 68 | 02 May 25 | Project 68 | 1001355 | Project | Sub-Portfolio 8 |  | Project Manager 12 |  |  | Hybrid | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 02 May 25 | Green | Green | Green | Green | Amber | Green | Green |  | Amber | Green | 2024-07-01 09:00 | 2025-10-31 17:00 | 332.9 | 332.9 | 2024-07-01 09:00 | 2025-10-31 17:00 | 2024-07-01 09:00 | 2025-10-31 17:00 | 2024-08-30 17:00 |  | 2025-06-02 17:00 | 6 | 115 | 41 | 74 | 44 | 3 | 3 | 71 |  |  | 1 | 4 | 1 | 1
Project 69 | 0 | Project 69 | 1001356 | Project | Sub-Portfolio 4 | Line of Business 7 | Project Manager 18 |  |  |  | No | Capital | Requested |  | 2. Concept | Weekly | [17 empty] | 1.1 | 2024-12-19 09:00 | 2024-12-20 10:00 | 2024-12-19 09:00 | 2024-12-20 10:00 |  |  |  | 0
Project 70 | 0 | Project 70 | 1001357 | Project | Sub-Portfolio 1 |  | Project Manager 11 |  |  |  | No | Capital | On Hold |  | 2. Concept | Weekly | [25 empty] | 0
Project 71 | 02 May 25 | Project 71 | 1001358 | Project | Sub-Portfolio 8 |  | Project Manager 30 | Sponsor 7 |  | Hybrid | No | Capex & Opex | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 02 May 25 | Amber | Green | Amber | Amber | Amber | Green | Green |  | Green | Green | 2024-07-31 17:00 | 2025-09-22 16:00 | 281.9 | 340.9 | 2024-07-31 17:00 | 2025-12-15 16:00 | 2024-12-13 17:00 | 2025-12-15 16:00 | 2024-07-31 17:00 |  | 2025-07-01 08:00 | 19 | 72 | 31 | 41 | 46 | 23 | 16 |  |  |  | 5 | 5
Project 72 | 25 Apr 25 | Project 72 | 1001359 | Project | Sub-Portfolio 8 |  | Project Manager 21 | Sponsor 18 |  | Waterfall | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 25 Apr 25 | Amber | Amber | Green | Amber | Amber | Green | Green |  | Amber | Green | 2024-03-26 17:00 | 2025-10-31 17:00 | 397 | 397 | 2024-03-26 17:00 | 2025-10-31 17:00 | 2025-01-06 08:00 | 2025-10-31 17:00 | 2024-03-26 17:00 |  | 2025-06-02 17:00 | 45 | 53 | 11 | 42 | 12 | 1 | 1 |  |  |  | 9 | 10
Project 73 | 25 Apr 25 | Project 73 | 1001360 | Project | Sub-Portfolio 8 |  | Project Manager 21 | Sponsor 18 |  | Hybrid | No | Capital | Open/Active | Gate 1 | 4. Analyse & Design | Weekly |  |  |  | 25 Apr 25 | Green | Green | Green | Amber | Green | Green | Green |  | Green | Green | 2024-03-26 17:00 | 2025-10-31 17:00 | 397 | 397 | 2024-03-26 17:00 | 2025-10-31 17:00 | 2025-01-06 08:00 | 2025-10-31 17:00 | 2024-03-26 17:00 |  | 2025-06-30 17:00 | 49 | 46 | 24 | 22 | 28 |  | 4 | 22 |  |  | 2 | 4
Project 74 | Apr-2025 | Project 74 | 1001361 | Project | Sub-Portfolio 8 |  | Project Manager 28 | Sponsor 18 |  | Agile | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Apr-2025 |  | 11 Oct 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-09-30 08:00 | 2025-10-31 17:00 | 268 | 268 | 2024-09-30 08:00 | 2025-10-31 17:00 | 2024-09-30 08:00 | 2025-10-31 17:00 | 2024-10-30 17:00 |  | 2025-06-27 17:00 | 0 | 44 | 14 | 30 | 15 | 1 | 1 | 29 |  |  | 6 | 7 |  | 4
Project 75 | Apr-2025 | Project 75 | 1001362 | Project | Sub-Portfolio 4 | Line of Business 7 | Project Manager 18 | Sponsor 49 |  | Waterfall | No | Capex & Opex | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Apr-2025 |  | 24 Jan 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-07-29 17:00 | 2025-07-01 09:00 | 224.1 | 284 | 2024-07-08 08:00 | 2025-08-29 17:00 | 2024-07-08 08:00 | 2025-08-29 17:00 | 2024-07-29 17:00 |  | 2025-06-02 17:00 | 18 | 54 | 30 | 24 | 60 | 22 | 31 | 2 |  |  | 10 | 10 | 1 | 1
Project 76 | 25 Apr 25 | Project 76 | 1001363 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 38 | Sponsor 19 |  | Agile | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Weekly |  |  |  | 25 Apr 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-03-26 17:00 | 2025-07-31 17:00 | 332 | 332 | 2024-03-26 17:00 | 2025-07-31 17:00 | 2024-07-01 09:00 | 2025-07-31 17:00 | 2024-03-26 17:00 |  | 2025-06-02 17:00 | 44 | 45 | 29 | 16 | 30 |  | 1 | 16 |  |  | 2 | 2
Project 77 | May-2025 | Project 77 | 1001364 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 38 | Sponsor 19 |  |  | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | May-2025 |  | 07 Mar 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-07-01 08:00 | 2025-07-31 08:00 | 267 | 374 | 2024-07-01 08:00 | 2026-01-14 17:00 | 2024-07-01 08:00 | 2026-01-14 17:00 | 2024-09-24 17:00 |  | 2025-06-02 17:00 | 1 | 22 | 13 | 9 | 16 | 8 | 6 | 1 |  |  | 6 | 6
Project 78 | 26 Jul 24 | Project 78 | 1001367 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 39 |  |  |  |  | Capex & Opex | Requested |  | 2. Concept | Weekly |  |  |  | 26 Jul 24 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 87.1 | 2024-02-22 09:00 | 2024-06-28 10:00 | 2024-02-22 09:00 | 2024-06-28 10:00 |  |  |  | 0 | [10 empty] | 9
Project 79 | Apr-2025 | Project 79 | 1001373 | Project | Sub-Portfolio 7 | Line of Business 20 | Project Manager 38 | Sponsor 31 |  | Agile | No | Capital | Open/Active | Gate 1 | 4. Analyse & Design | Monthly |  | Apr-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-03-18 09:00 | 2025-06-30 17:00 | 315.9 | 423.9 | 2024-03-18 09:00 | 2025-11-28 17:00 | 2024-03-18 09:00 | 2025-11-28 17:00 | 2024-04-09 08:00 |  | 2025-06-27 17:00 | 15 | 38 | 27 | 11 | 27 | [5 empty] | 3 | 5
Project 80 | Jun-2024 | Project 80 | 1001374 | Project | Sub-Portfolio 8 | Line of Business 8 | Project Manager 25 |  |  |  |  | Capital | Requested |  | 2. Concept | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 93.8 | 2024-03-01 08:00 | 2024-07-16 15:00 | 2024-03-01 08:00 | 2024-07-16 15:00 |  |  |  | 0 | [9 empty] | 1 | 1 | 1 | 1
Project 81 | Jun-2024 | Project 81 | 1001375 | Project | Sub-Portfolio 8 | Line of Business 8 | Project Manager 25 |  |  |  |  | Capital | Requested |  | 2. Concept | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 93.8 | 2024-03-01 08:00 | 2024-07-16 15:00 | 2024-03-01 08:00 | 2024-07-16 15:00 |  |  |  | 0 | [9 empty] | 1 | 2 |  | 1
Project 82 | 0 | Project 82 | 1001384 | Project | Sub-Portfolio 8 |  | Project Manager 11 |  |  |  | No | Capital | On Hold |  | 2. Concept | Weekly | [25 empty] | 0
Project 83 | 0 | Project 83 | 1001388 | Project | Sub-Portfolio 8 | Line of Business 1 | Project Manager 31 |  |  |  |  | Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 70.1 | 2024-03-18 09:00 | 2024-06-28 10:00 | 2024-03-18 09:00 | 2024-06-28 10:00 |  |  |  | 0
Project 84 | 0 | Project 84 | 1001392 | Project | Sub-Portfolio 7 | Line of Business 13 | Project Manager 27 |  |  |  |  | Capital | On Hold |  | 2. Concept | Monthly | [17 empty] | 62 | 2024-04-02 08:00 | 2024-06-28 17:00 | 2024-04-02 08:00 | 2024-06-28 17:00 |  |  |  | 0
Project 85 | 31 Jan 25 | Project 85 | 1001399 | Project | Sub-Portfolio 4 | Line of Business 7 | Project Manager 14 |  | Important | Agile | No | Capital | Prepare for Closure | Gate 2 | 7. Closure | Weekly |  |  |  | 31 Jan 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-03-28 17:00 | 2025-02-03 09:00 | 205.1 | 205.1 | 2024-03-28 17:00 | 2025-02-03 09:00 | 2024-07-01 08:00 | 2025-01-31 17:00 | 2024-03-28 17:00 |  | 2025-06-02 17:00 | 100 | 53 | 53 |  | 53 | [6 empty] | 2
Project 86 | Jun-2024 | Project 86 | 1001413 | Minor Work | Sub-Portfolio 7 | Line of Business 23 | Project Manager 38 |  |  |  | No | Capital | Requested |  | 2. Concept | Monthly |  | Jun-2024 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 57.9 | 2024-04-08 09:00 | 2024-06-28 17:00 | 2024-04-08 09:00 | 2024-06-28 17:00 |  |  |  | 0
Project 87 | 0 | Project 87 | 1001420 | Light Project | Sub-Portfolio 4 | Line of Business 7 | Project Manager 18 | Sponsor 48 | Medium |  | No | Capital | Requested |  | 2. Concept | Weekly | [17 empty] | 140.9 | 2024-04-15 09:00 | 2024-10-31 17:00 | 2024-04-15 09:00 | 2024-10-31 17:00 |  |  |  | 0
Project 88 | 0 | Project 88 | 1001422 | Minor Work | Sub-Portfolio 4 | Line of Business 7 | Project Manager 19 |  | Medium |  | No | Capital | Requested |  | 2. Concept | Weekly | [17 empty] | 70 | 2024-04-15 08:00 | 2024-07-23 17:00 | 2024-04-15 08:00 | 2024-07-23 17:00 |  |  |  | 0
Project 89 | 0 | Project 89 | 1001428 | Minor Work | Sub-Portfolio 7 |  | Project Manager 13 |  | High |  |  |  | Requested |  |  | Monthly | [17 empty] | 103 | 2024-02-01 08:00 | 2024-06-28 17:00 | 2024-02-01 08:00 | 2024-06-28 17:00 |  |  |  | 0
Project 90 | 0 | Project 90 | 1001429 | Program (admin) | Sub-Portfolio 4 |  |  |  | Important |  |  |  | Requested |  |  | Monthly | [17 empty] | 863.9 | 2022-07-27 09:00 | 2026-01-28 17:00 | 2022-07-27 09:00 | 2026-01-28 17:00 |  |  |  | 0
Project 91 | 0 | Project 91 | 1001430 | Project | Sub-Portfolio 7 | Line of Business 20 | Project Manager 7 |  |  |  | No | Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 52.9 | 2024-04-15 09:00 | 2024-06-28 17:00 | 2024-04-15 09:00 | 2024-06-28 17:00 | 2024-05-20 08:00 |  |  | 26
Project 92 | 0 | Project 92 | 1001437 | Minor Work | Sub-Portfolio 7 | Line of Business 13 | Project Manager 27 | Sponsor 42 |  |  |  | Capital | Requested |  | 2. Concept | Monthly | [17 empty] | 113.9 | 2024-04-22 09:00 | 2024-09-30 17:00 | 2024-04-22 09:00 | 2024-09-30 17:00 | 2024-04-29 08:00 |  |  | 18
Project 93 | Apr-2025 | Project 93 | 1001440 | Project | Sub-Portfolio 8 | Line of Business 24 | Project Manager 13 |  |  | Agile | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Apr-2025 |  |  | Green | Green | Green | Green | Amber | Green | Green |  | Green | Green | 2024-05-10 17:00 | 2026-06-04 17:00 | 506 | 506 | 2024-05-10 17:00 | 2026-06-04 17:00 | 2024-07-01 08:00 | 2026-06-04 17:00 | 2024-05-10 17:00 |  | 2025-06-02 17:00 | 5 | 67 | 34 | 33 | 53 | 2 | 24 | 25 |  |  | 5 | 5 | 1 | 2
Project 94 | 0 | Project 94 | 1001444 | Epic | Sub-Portfolio 7 | Line of Business 9 | Project Manager 13 | [5 empty] | Requested |  | 2. Concept | Monthly | [25 empty] | 0
Project 95 | 0 | Project 95 | 1001449 | Program (admin) | Sub-Portfolio 4 |  |  |  | Important |  |  |  | Requested |  |  | Weekly | [17 empty] | 162.9 | 2024-05-06 09:00 | 2024-12-20 17:00 | 2024-05-06 09:00 | 2024-12-20 17:00 |  |  |  | 0
Project 96 | 0 | Project 96 | 1001458 | Minor Work | Sub-Portfolio 7 |  | Project Manager 27 |  |  |  |  | Opex | On Hold |  | 2. Concept | Monthly | [17 empty] | 61.1 | 2024-05-06 09:00 | 2024-07-31 10:00 | 2024-05-06 09:00 | 2024-07-31 10:00 |  |  |  | 0
Project 97 | 0 | Project 97 | 1001459 | Minor Work | Sub-Portfolio 7 | Line of Business 5 | Project Manager 35 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 38.9 | 2024-05-06 09:00 | 2024-06-28 17:00 | 2024-05-06 09:00 | 2024-06-28 17:00 |  |  |  | 0
Project 98 | 0 | Project 98 | 1001460 | Epic | Sub-Portfolio 7 | Line of Business 5 | Project Manager 35 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 41.9 | 2024-05-01 09:00 | 2024-06-28 17:00 | 2024-05-01 09:00 | 2024-06-28 17:00 |  |  |  | 0
Project 99 | 0 | Project 99 | 1001483 | Minor Work | Sub-Portfolio 4 | Line of Business 12 | Project Manager 19 |  | Important |  |  | Capital | Requested |  |  | Weekly | [17 empty] | 88.9 | 2024-04-29 09:00 | 2024-08-30 17:00 | 2024-04-29 09:00 | 2024-08-30 17:00 |  |  |  | 0
Project 100 | 0 | Project 100 | 1001486 | Application Support | Sub-Portfolio 7 | Line of Business 13 | Project Manager 7 |  | High |  |  | Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 110.1 | 2024-05-27 09:00 | 2024-10-30 10:00 | 2024-05-27 09:00 | 2024-10-30 10:00 |  |  |  | 0
Project 101 | 0 | Project 101 | 1001493 | Project | Sub-Portfolio 2 |  |  |  |  | Agile | No | Opex | On Hold | Gate 0 | 2. Concept | Weekly | [14 empty] | 2022-08-01 08:00 | 2025-07-11 08:00 | 731 | 822 | 2022-08-01 08:00 | 2025-11-17 17:00 | 2025-01-17 17:00 | 2025-11-17 17:00 | 2022-08-01 08:00 |  | 2025-11-13 17:00 | 5 | 83 |  | 83 | 55 | 51 | 55 | 22 |  |  | 1 | 1
Project 102 | 0 | Project 102 | 1001498 | Project | Sub-Portfolio 7 |  | Project Manager 35 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 24.1 | 2024-05-24 09:00 | 2024-06-28 10:00 | 2024-05-24 09:00 | 2024-06-28 10:00 |  |  |  | 0
Project 103 | 0 | Project 103 | 1001504 | Application Support | Sub-Portfolio 7 | Line of Business 13 | Project Manager 7 |  | High |  |  | Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 106.1 | 2024-06-03 09:00 | 2024-10-31 10:00 | 2024-06-03 09:00 | 2024-10-31 10:00 |  |  |  | 0
Project 104 | 0 | Project 104 | 1001524 | Minor Work | Sub-Portfolio 7 |  | Project Manager 7 | [5 empty] | Requested |  | 2. Concept | Weekly | [17 empty] | 282 | 2024-08-09 08:00 | 2025-09-30 17:00 | 2024-08-09 08:00 | 2025-09-30 17:00 | 2024-08-09 08:00 |  |  | 42 | [9 empty] | 1 | 1
Project 105 | 0 | Project 105 | 1001548 | Minor Work | Sub-Portfolio 7 |  | Project Manager 13 |  | Low |  |  | Opex | Requested |  |  | Monthly | [17 empty] | 66 | 2024-07-01 08:00 | 2024-09-30 17:00 | 2024-07-01 08:00 | 2024-09-30 17:00 |  |  |  | 0
Project 106 | 0 | Project 106 | 1001566 | Project | Sub-Portfolio 7 |  | Project Manager 27 |  |  |  | No | Capex & Opex | Requested |  | 2. Concept | Weekly | [17 empty] | 225 | 2024-07-29 08:00 | 2025-06-30 17:00 | 2024-07-29 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 107 | 0 | Project 107 | 1001579 | Minor Work | Sub-Portfolio 7 |  | Project Manager 27 |  |  |  | No | Opex | Requested |  | 2. Concept | Weekly | [25 empty] | 0
Project 108 | 0 | Project 108 | 1001602 | Project | Sub-Portfolio 7 |  | Project Manager 27 |  |  |  | No | Capital | Requested |  | 2. Concept | Weekly | [17 empty] | 325.9 | 2024-09-02 09:00 | 2025-12-24 17:00 | 2024-09-02 09:00 | 2025-12-24 17:00 |  |  |  | 0
Project 109 | 21 Mar 25 | Project 109 | 1001608 | Minor Work | Sub-Portfolio 4 | Line of Business 12 | Project Manager 5 |  | High |  | No | Capex & Opex | Open/Active |  | 6. Implement | Weekly |  |  |  | 21 Mar 25 | Green | Green | Amber | Green | Green | Green | Green |  | Amber | Green |  |  |  | 178.9 | 2024-10-01 09:00 | 2025-06-30 17:00 | 2024-10-01 09:00 | 2025-06-30 17:00 |  |  | 2025-06-27 17:00 | 0 | 14 |  | 14
Project 110 | Apr-2025 | Project 110 | 1001617 | Project | Sub-Portfolio 8 | Line of Business 7 | Project Manager 22 | Sponsor 18 |  |  | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Apr-2025 |  |  | Amber | Green | Green | Amber | Amber | Green | Green |  | Amber | Green |  |  |  | 442 | 2024-07-05 17:00 | 2026-04-30 17:00 | 2024-11-05 08:00 | 2026-04-30 17:00 | 2024-07-05 17:00 |  | 2025-11-13 17:00 | 0 | 74 | 23 | 51 | [6 empty] | 2 | 3
Project 111 | 25 Apr 25 | Project 111 | 1001618 | Minor Work | Sub-Portfolio 4 |  | Project Manager 36 | Sponsor 11 | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly |  | Jan-2025 |  | 25 Apr 25 | Amber | Green | Amber | Amber | Green | Green | Green |  | Amber | Green |  |  |  | 294 | 2024-09-11 08:00 | 2025-11-19 17:00 | 2024-09-11 08:00 | 2025-11-19 17:00 | 2024-09-30 17:00 |  | 2025-04-08 17:00 | 13 | 12 | 10 | 2 | [6 empty] | 3 | 4 | 1 | 2
Project 112 | 0 | Project 112 | 1001626 | Minor Work | Sub-Portfolio 7 | Line of Business 7 | Project Manager 13 |  | High |  |  |  | Requested |  | 6. Implement | Monthly | [17 empty] | 159 | 2024-10-01 08:00 | 2025-05-30 17:00 | 2024-10-01 08:00 | 2025-05-30 17:00 |  |  |  | 0
Project 113 | 0 | Project 113 | 1001643 | Minor Work | Sub-Portfolio 7 |  | Project Manager 27 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Monthly | [17 empty] | 160 | 2024-09-30 08:00 | 2025-05-30 17:00 | 2024-09-30 08:00 | 2025-05-30 17:00 |  |  |  | 0
Project 114 | Apr-2025 | Project 114 | 1001647 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 20 | Sponsor 19 | Medium | Waterfall | No | Capital | Open/Active | Gate 0 | 3. Evaluate | Monthly |  | Apr-2025 |  |  | Amber | Amber | Green | Amber | Green | Green | Green |  | Amber | Green | 2024-10-08 09:00 | 2026-06-30 09:00 | 418 | 418.9 | 2024-10-08 09:00 | 2026-06-30 17:00 | 2024-10-08 09:00 | 2026-06-30 17:00 | 2024-11-19 17:00 |  | 2025-06-03 08:00 | 10 | 31 | 5 | 26 | 5 | [5 empty] | 2 | 2
Project 115 | 0 | Project 115 | 1001650 | Minor Work | Sub-Portfolio 7 |  | Project Manager 7 |  | Important |  |  |  | Open/Active |  | 6. Implement | Weekly | [17 empty] | 240.9 | 2024-10-08 09:00 | 2025-09-30 17:00 | 2024-10-08 09:00 | 2025-09-30 17:00 | 2024-11-22 08:00 |  |  | 1
Project 116 | 0 | Project 116 | 1001755 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 36 | Sponsor 8 |  |  | No | Capex & Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 114.9 | 2025-02-17 09:00 | 2025-07-31 17:00 | 2025-02-17 09:00 | 2025-07-31 17:00 |  |  |  | 0 | 5 |  | 5 | [6 empty] | 4 | 4
Project 117 | 0 | Project 117 | 1001765 | Minor Work | Sub-Portfolio 7 |  | Project Manager 7 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly | [17 empty] | 429.8 | 2024-10-21 09:00 | 2026-07-28 16:00 | 2024-10-21 09:00 | 2026-07-28 16:00 | 2024-10-21 09:00 |  |  | 3
Project 118 | 0 | Project 118 | 1001768 | Minor Work | Sub-Portfolio 7 |  | Project Manager 35 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly | [17 empty] | 1.1 | 2024-10-21 09:00 | 2024-10-22 10:00 | 2024-10-21 09:00 | 2024-10-22 10:00 |  |  |  | 0
Project 119 | Mar-2025 | Project 119 | 1001774 | Project | Sub-Portfolio 4 |  | Project Manager 4 | Sponsor 19 |  |  |  |  | Requested |  | 2. Concept | Monthly |  | Mar-2025 |  | 21 Feb 25 | Green | Green | Green | Amber | Green | Green | Green |  | Green | Green |  |  |  | 380 | 2024-11-01 08:00 | 2026-05-29 17:00 | 2024-12-02 08:00 | 2026-05-29 17:00 | 2024-11-01 08:00 |  | 2025-04-08 17:00 | 24 | 6 | 1 | 5
Project 120 | Apr-2025 | Project 120 | 1001775 | Light Project | Sub-Portfolio 4 |  | Project Manager 14 | Sponsor 19 |  |  | No | Capital | Requested |  | 2. Concept | Monthly |  | Apr-2025 |  | 21 Feb 25 | Green | Green | Green | Green | Green | Green | Green |  | Green | Green | 2024-11-01 08:00 | 2025-06-30 17:00 | 157 | 157 | 2024-11-01 08:00 | 2025-06-30 17:00 | 2024-11-01 08:00 | 2025-06-30 17:00 | 2025-03-14 17:00 |  | 2025-06-02 17:00 | 0 | 7 | 2 | 5
Project 121 | Apr-2025 | Project 121 | 1001776 | Light Project | Sub-Portfolio 4 |  | Project Manager 14 | Sponsor 19 |  |  | No | Capital | Requested |  | 2. Concept | Monthly |  | Apr-2025 |  | 21 Feb 25 | Green | Green | Green | Green | Amber | Green | Green |  | Green | Amber | 2024-11-01 08:00 | 2026-06-30 17:00 | 401 | 282.9 | 2024-11-01 09:00 | 2025-12-24 17:00 | 2024-11-01 09:00 | 2025-12-24 17:00 | 2025-03-14 17:00 |  | 2025-06-02 17:00 | 0 | 12 | 2 | 10
Project 122 | Apr-2025 | Project 122 | 1001777 | Minor Work | Sub-Portfolio 4 |  | Project Manager 14 | Sponsor 19 | Medium |  |  |  | Requested |  | 2. Concept | Monthly |  | Apr-2025 |  | 21 Feb 25 | Green | Green | Green | Amber | Green | Green | Green |  | Amber | Green | 2024-11-01 08:00 | 2025-12-19 17:00 | 280 | 283 | 2024-11-01 08:00 | 2025-12-24 17:00 | 2024-11-01 08:00 | 2025-12-24 17:00 | 2024-11-01 08:00 |  |  | 9 | 8 | 1 | 7 | 8 | 7 | 7
Project 123 | 0 | Project 123 | 1001784 | Application Support | Sub-Portfolio 1 |  | Project Manager 13 |  | High |  |  | Opex | Requested |  | 6. Implement | Monthly | [17 empty] | 311 | 2024-07-01 08:00 | 2025-09-30 17:00 | 2024-07-01 08:00 | 2025-09-30 17:00 |  |  |  | 0
Project 124 | 0 | Project 124 | 1001785 | Application Support | Sub-Portfolio 2 |  | Project Manager 9 |  | High |  |  | Opex | Requested |  |  | Monthly | [17 empty] | 245 | 2024-07-01 08:00 | 2025-06-30 17:00 | 2024-07-01 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 125 | 0 | Project 125 | 1001786 | Application Support | Sub-Portfolio 4 |  |  |  | High |  |  | Opex | Requested |  | 6. Implement | Monthly | [17 empty] | 245 | 2024-07-01 08:00 | 2025-06-30 17:00 | 2024-07-01 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 126 | 0 | Project 126 | 1001787 | Application Support | Sub-Portfolio 7 |  |  |  | High |  |  | Opex | Requested |  | 6. Implement | Monthly | [17 empty] | 245 | 2024-07-01 08:00 | 2025-06-30 17:00 | 2024-07-01 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 127 | 0 | Project 127 | 1001788 | Application Support | Sub-Portfolio 5 |  |  |  | High |  |  | Opex | Requested |  | 6. Implement | Monthly | [17 empty] | 245 | 2024-07-01 08:00 | 2025-06-30 17:00 | 2024-07-01 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 128 | 0 | Project 128 | 1001789 | Application Support | Sub-Portfolio 6 |  |  |  | High |  |  | Opex | Requested |  | 6. Implement | Monthly | [17 empty] | 245 | 2024-07-01 08:00 | 2025-06-30 17:00 | 2024-07-01 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 129 | 0 | Project 129 | 1001790 | Application Support | Sub-Portfolio 8 |  |  |  | High |  |  | Opex | Requested |  | 6. Implement | Monthly | [17 empty] | 245 | 2024-07-01 08:00 | 2025-06-30 17:00 | 2024-07-01 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 130 | 0 | Project 130 | 1001802 | Project | Sub-Portfolio 7 | Line of Business 22 | Project Manager 7 | Sponsor 15 |  |  |  |  | Requested |  | 2. Concept | Weekly | [17 empty] | 25 | 2024-12-09 08:00 | 2025-01-24 17:00 | 2024-12-09 08:00 | 2025-01-24 17:00 |  |  |  | 0
Project 131 | 0 | Project 131 | 1001803 | Minor Work | Sub-Portfolio 7 |  | Project Manager 35 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly | [25 empty] | 0
Project 132 | 0 | Project 132 | 1001804 | Minor Work | Sub-Portfolio 7 |  | Project Manager 35 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly | [25 empty] | 0
Project 133 | 0 | Project 133 | 1001805 | Minor Work | Sub-Portfolio 7 |  | Project Manager 35 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly | [25 empty] | 0
Project 134 | 0 | Project 134 | 1001806 | Minor Work | Sub-Portfolio 7 |  | Project Manager 35 |  | Medium |  |  |  | Open/Active |  | 6. Implement | Weekly | [25 empty] | 0
Project 135 | 0 | Project 135 | 1001816 | Project | Sub-Portfolio 7 |  | Project Manager 7 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 131 | 2024-12-09 08:00 | 2025-06-30 17:00 | 2024-12-09 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 136 | 0 | Project 136 | 1001817 | Project | Sub-Portfolio 7 |  | Project Manager 7 | Sponsor 12 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 306 | 2024-12-09 08:00 | 2026-03-20 17:00 | 2024-12-09 08:00 | 2026-03-20 17:00 | 2025-02-10 08:00 |  |  | 6
Project 137 | 0 | Project 137 | 1001818 | Project | Sub-Portfolio 7 |  | Project Manager 7 | Sponsor 41 |  |  |  |  | On Hold |  | 2. Concept | Monthly | [17 empty] | 163.2 | 2024-12-09 08:00 | 2025-08-14 09:18 | 2024-12-09 08:00 | 2025-08-14 09:18 | 2024-12-09 08:00 |  |  | 22
Project 138 | 0 | Project 138 | 1001819 | Minor Work | Sub-Portfolio 7 |  | Project Manager 24 | Sponsor 9 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 130.9 | 2025-03-24 09:00 | 2025-09-26 17:00 | 2025-03-24 09:00 | 2025-09-26 17:00 |  |  |  | 0
Project 139 | 0 | Project 139 | 1001820 | Minor Work | Sub-Portfolio 7 |  | Project Manager 35 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 127 | 2024-12-13 08:00 | 2025-06-30 17:00 | 2024-12-13 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 140 | 0 | Project 140 | 1001821 | Project | Sub-Portfolio 4 |  | Project Manager 18 | Sponsor 11 |  |  |  |  | Requested |  | 2. Concept | Weekly | [17 empty] | 137 | 2025-03-31 08:00 | 2025-10-14 17:00 | 2025-03-31 08:00 | 2025-10-14 17:00 |  |  |  | 0
Project 141 | 0 | Project 141 | 1001822 | Project | Sub-Portfolio 7 |  | Project Manager 7 | [5 empty] | Requested |  | 2. Concept | Monthly | [17 empty] | 185 | 2025-01-06 08:00 | 2025-09-26 17:00 | 2025-01-06 08:00 | 2025-09-26 17:00 |  |  |  | 0
Project 142 | 0 | Project 142 | 1001823 | Minor Work | Sub-Portfolio 3 | Line of Business 12 | Project Manager 3 |  | High |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 126 | 2024-12-16 08:00 | 2025-06-30 17:00 | 2024-12-16 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 143 | Apr-2025 | Project 143 | 1001825 | Project | Sub-Portfolio 4 |  | Project Manager 18 | Sponsor 28 |  |  |  |  | Requested |  | 2. Concept | Monthly |  | Apr-2025 |  |  | Green | Green | Green | Amber | Green | Green | Green |  | Green | Green |  |  |  | 369 | 2024-09-19 08:00 | 2026-03-31 17:00 | 2024-09-19 08:00 | 2026-03-31 17:00 |  |  |  | 0
Project 144 | 0 | Project 144 | 1001829 | Project | Sub-Portfolio 7 |  | Project Manager 35 | Sponsor 40 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 106 | 2025-01-28 08:00 | 2025-06-30 17:00 | 2025-01-28 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 145 | Apr-2025 | Project 145 | 1001834 | Light Project | Sub-Portfolio 7 |  | Project Manager 7 | Sponsor 33 |  |  | No | Capital | Requested |  | 2. Concept | Monthly |  | Apr-2025 |  |  | Green | Green | Green | Green | Green | Green | Green |  | Green | Green |  |  |  | 141 | 2025-02-10 08:00 | 2025-08-29 17:00 | 2025-02-17 08:00 | 2025-08-29 17:00 | 2025-02-10 08:00 |  |  | 22 | [9 empty] | 3 | 3 |  | 2
Project 146 | 0 | Project 146 | 1001857 | Project | Sub-Portfolio 7 |  |  | Sponsor 46 |  |  |  |  | Requested |  | 2. Concept | Monthly | [25 empty] | 0
Project 147 | 0 | Project 147 | 1001860 | Project | Sub-Portfolio 7 |  | Project Manager 7 | Sponsor 27 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 62 | 2025-03-03 08:00 | 2025-05-30 17:00 | 2025-03-03 08:00 | 2025-05-30 17:00 |  |  |  | 0
Project 148 | 0 | Project 148 | 1001861 | Project | Sub-Portfolio 2 |  |  | Sponsor 35 |  |  |  | Capex & Opex | Requested |  | 2. Concept | Weekly | [17 empty] | 60 | 2025-07-01 08:00 | 2025-09-22 17:00 | 2025-07-01 08:00 | 2025-09-22 17:00 |  |  |  | 0
Project 149 | 0 | Project 149 | 1001863 | Light Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 3 | Sponsor 26 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 84 | 2025-02-27 08:00 | 2025-06-30 17:00 | 2025-02-27 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 150 | 0 | Project 150 | 1001866 | Light Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 3 | Sponsor 16 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 84 | 2025-02-27 08:00 | 2025-06-30 17:00 | 2025-02-27 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 151 | 0 | Project 151 | 1001869 | Minor Work | Sub-Portfolio 3 | [7 empty] | Requested |  | 2. Concept | Weekly | [25 empty] | 0
Project 152 | 0 | Project 152 | 1001870 | Project | Sub-Portfolio 4 |  | Project Manager 18 | Sponsor 43 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 82 | 2025-03-03 08:00 | 2025-06-30 17:00 | 2025-03-03 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 153 | 0 | Project 153 | 1001871 | Project | Sub-Portfolio 7 |  |  | Sponsor 45 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 82 | 2025-03-03 08:00 | 2025-06-30 17:00 | 2025-03-03 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 154 | 0 | Project 154 | 1001872 | Project | Sub-Portfolio 4 | Line of Business 12 | Project Manager 20 | Sponsor 8 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 82 | 2025-03-03 08:00 | 2025-06-30 17:00 | 2025-03-03 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 155 | 0 | Project 155 | 1001873 | Minor Work | Sub-Portfolio 7 |  | Project Manager 7 | Sponsor 36 | Low |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 82 | 2025-03-03 08:00 | 2025-06-30 17:00 | 2025-03-03 08:00 | 2025-06-30 17:00 |  |  |  | 0 | [9 empty] | 1 | 1
Project 156 | 0 | Project 156 | 1001875 | Project | Sub-Portfolio 8 | Line of Business 24 | Project Manager 25 | Sponsor 18 |  |  | No | Capex & Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 307 | 2025-03-06 08:00 | 2026-06-05 17:00 | 2025-03-06 08:00 | 2026-06-05 17:00 |  |  |  | 0
Project 157 | 0 | Project 157 | 1001876 | Project | Sub-Portfolio 8 | Line of Business 24 | Project Manager 25 | Sponsor 18 |  |  | No | Capex & Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 323 | 2025-03-25 08:00 | 2026-07-17 17:00 | 2025-03-25 08:00 | 2026-07-17 17:00 |  |  |  | 0
Project 158 | 0 | Project 158 | 1001877 | Project | Sub-Portfolio 8 | Line of Business 24 | Project Manager 25 | Sponsor 18 |  |  | No | Capex & Opex | Requested |  | 2. Concept | Monthly | [17 empty] | 50.3 | 2025-03-25 08:00 | 2025-06-06 10:29 | 2025-03-25 08:00 | 2025-06-06 10:29 |  |  |  | 0
Project 159 | 0 | Project 159 | 1001878 | Project | Sub-Portfolio 8 |  | Project Manager 16 | Sponsor 18 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 323 | 2025-03-06 08:00 | 2026-06-30 17:00 | 2025-03-06 08:00 | 2026-06-30 17:00 |  |  |  | 0
Project 160 | 0 | Project 160 | 1001879 | Project | Sub-Portfolio 8 |  | Project Manager 31 | Sponsor 18 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 323 | 2025-03-06 08:00 | 2026-06-30 17:00 | 2025-03-06 08:00 | 2026-06-30 17:00 |  |  |  | 0
Project 161 | 0 | Project 161 | 1001880 | Project | Sub-Portfolio 8 |  |  | Sponsor 18 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 525 | 2024-03-07 08:00 | 2026-04-30 17:00 | 2024-03-07 08:00 | 2026-04-30 17:00 |  |  |  | 0
Project 162 | 0 | Project 162 | 1001881 | Project | Sub-Portfolio 8 | Line of Business 11 | Project Manager 12 | Sponsor 18 |  |  | Yes | Capital | Cancelled |  | 2. Concept | Monthly | [17 empty] | 118 | 2025-01-09 08:00 | 2025-06-30 17:00 |  |  | 2025-01-09 08:00 | 2025-06-30 17:00 |  | 100
Project 163 | 0 | Project 163 | 1001882 | Project | Sub-Portfolio 7 |  |  | Sponsor 20 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 77 | 2025-03-10 08:00 | 2025-06-30 17:00 | 2025-03-10 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 164 | 0 | Project 164 | 1001891 | Project | Sub-Portfolio 7 |  | Project Manager 7 | Sponsor 47 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 26 | 2025-04-22 08:00 | 2025-05-28 17:00 | 2025-04-22 08:00 | 2025-05-28 17:00 |  |  |  | 0
Project 165 | 0 | Project 165 | 1001895 | Minor Work | Sub-Portfolio 7 |  | Project Manager 7 | Sponsor 39 | High |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 63 | 2025-03-28 08:00 | 2025-06-30 17:00 | 2025-03-28 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 166 | 0 | Project 166 | 1001896 | Project | Sub-Portfolio 7 |  |  | Sponsor 5 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 62 | 2025-03-31 08:00 | 2025-06-30 17:00 | 2025-03-31 08:00 | 2025-06-30 17:00 |  |  |  | 0
Project 167 | 0 | Project 167 | 1001898 | Project | Sub-Portfolio 7 |  | Project Manager 7 | Sponsor 36 |  |  |  |  | Requested |  | 2. Concept | Monthly | [17 empty] | 81 | 2025-04-04 08:00 | 2025-07-31 17:00 | 2025-04-04 08:00 | 2025-07-31 17:00 |  |  |  | 0
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## PV_Milestones
[14 empty] | WRK15 | [7 empty] | BL Delivery Ratio Full Year |  |  |  | BL Delivery Ratio YTD
[22 empty] | 50.73% |  |  |  | 54.62%
[23 empty] | 85.09% | 43.16% |  | 54.62% | 69.09% | 13.28% | 4.111% | KPIs against Planned YTD
[10 empty] | Last Extracted | 2025-05-06 | [11 empty] | 85.09% | 43.16% | 35.52% | 19.4% | 24.54% | 4.718% | 1.46% | KPIs against Total Milestones
[16 empty] | 3561 | [6 empty] | 3030 | 1537 | 1265 | 691 | 874 | 168 | 52
Project Status | Schedule Variance | Project Description | Milestone Description | Milestone Type | Milestone Indentifier | Project Status2 | Stage | Work ID | Work Description | Work Notes: | Actual/Schedule Finish | Baseline Date | Variance (d) | Variance (%) | UID | Duplicate Milestone | Sub-Portfolio | BL FY | Finish FY | Complete | To be Baselined | Planned WoL | Actual WoL | Planned YTD | Actual YTD | Overdue | Delayed | Delayed past FY25 | PM
Requested | 0% | Project 5 | Release 1.1 Go-Live | Deliverable | Go-Live | Requested | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Requested | 0% | Project 5 | Release 1.2 Go-Live | Deliverable | Go-Live | Requested | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-04-01 17:00 | 2026-04-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Requested | 0% | Project 5 | Release 1.3 Go-Live | Deliverable | Go-Live | Requested | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-09-04 17:00 | 2026-09-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Requested | 0% | Project 68 | 4.09 Test Plan Sign Off Phase 2 | Deliverable | Unassigned | Requested | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Requested | 0% | Project 68 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Requested | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Requested | -25% to -10% | Project 75 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -0.15672 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Requested | -25% to -10% | Project 75 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -0.15672 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Requested | N/A | Project 31 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Requested | 2. Concept | 1000872 |  | Delay reason known here | 2025-12-12 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Requested | N/A | Project 31 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Requested | 2. Concept | 1000872 |  | Delay reason known here | 2025-12-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Requested | N/A | Project 31 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Requested | 2. Concept | 1000872 |  | Delay reason known here | 2025-12-17 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Requested | N/A | Project 31 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Requested | 2. Concept | 1000872 |  | Delay reason known here | 2025-12-22 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Requested | -10% to -5% | Project 63 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Requested | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-03-17 08:00 | -32 | -0.096386 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Requested | -25% to -10% | Project 4 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Requested | 6. Implement | 1000295 |  | Delay reason known here | 2025-05-01 17:00 | 2024-12-20 17:00 | -80 | -0.1138 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 15
Requested | -25% to -10% | Project 4 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Requested | 6. Implement | 1000295 |  | Delay reason known here | 2025-05-01 17:00 | 2024-12-20 17:00 | -80 | -0.1138 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 15
Requested | -25% to -10% | Project 4 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Requested | 6. Implement | 1000295 |  | Delay reason known here | 2025-05-01 17:00 | 2024-12-20 17:00 | -80 | -0.1138 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 15
Requested | N/A | Project 110 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | System Architect Replacement | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-09-09 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | Microfocus to TOSCA migration for Automation suite | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-09-02 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-20 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-20 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-20 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-20 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-20 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-20 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-20 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | GO LIVE | Deliverable | Go-Live | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-23 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-07-18 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-20 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2026-03-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-09-12 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-09-12 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-09-12 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-09-12 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-09-12 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-09-12 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-09-12 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-09-12 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | N/A | Project 110 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Requested | 0% | Project 5 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Requested | 3. Evaluate | 1000296 |  | Delay reason known here | 2027-01-11 17:00 | 2027-01-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Requested | N/A | Project 27 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-07-07 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-07-07 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-22 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-08-29 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-07-21 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2025-07-21 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2026-06-05 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2026-06-12 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2026-06-19 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 27 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Requested | 2. Concept | 1000840 |  | Delay reason known here | 2026-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 7 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Requested | 6. Implement | 1000298 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Requested | N/A | Project 119 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | 1001774 |  | Delay reason known here | 2025-06-26 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Requested | N/A | Project 119 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Requested | 2. Concept | 1001774 |  | Delay reason known here | 2025-06-26 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Requested | N/A | Project 119 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Requested | 2. Concept | 1001774 |  | Delay reason known here | 2025-06-26 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Requested | N/A | Project 119 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Requested | 2. Concept | 1001774 |  | Delay reason known here | 2025-06-26 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Requested | N/A | Project 119 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Requested | 2. Concept | 1001774 |  | Delay reason known here | 2025-06-26 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Requested | N/A | Project 120 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | 1001775 |  | Delay reason known here | 2025-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Requested | N/A | Project 120 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Requested | 2. Concept | 1001775 |  | Delay reason known here | 2025-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Requested | N/A | Project 120 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Requested | N/A | Project 120 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Requested | 2. Concept | 1001775 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Requested | N/A | Project 120 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Requested | 2. Concept | 1001775 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Requested | N/A | Project 120 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Requested | 2. Concept | 1001775 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Requested | N/A | Project 121 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | 1001776 |  | Delay reason known here | 2025-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Requested | N/A | Project 121 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Requested | 2. Concept | 1001776 |  | Delay reason known here | 2025-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Requested | N/A | Project 121 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Requested | 2. Concept | 1001776 |  | Delay reason known here | 2025-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Requested | N/A | Project 121 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | 1001776 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Requested | N/A | Project 121 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | 1001776 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Requested | N/A | Project 121 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Requested | 2. Concept | 1001776 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Requested | N/A | Project 121 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Requested | 2. Concept | 1001776 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Requested | N/A | Project 121 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | 1001776 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Requested | N/A | Project 121 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Requested | 2. Concept | 1001776 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Requested | N/A | Project 121 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Requested | 2. Concept | 1001776 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Requested | -10% to -5% | Project 122 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | 1001777 |  | Delay reason known here | 2025-04-30 17:00 | 2025-03-31 17:00 | -19 | -0.067138 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Requested | -10% to -5% | Project 122 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Requested | 2. Concept | 1001777 |  | Delay reason known here | 2025-04-30 17:00 | 2025-03-31 17:00 | -19 | -0.067138 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Requested | -10% to -5% | Project 122 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | 1001777 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-17 17:00 | -28 | -0.09894 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 14
Requested | -25% to -10% | Project 122 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Requested | 2. Concept | 1001777 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-14 17:00 | -31 | -0.10954 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 14
Requested | -25% to -10% | Project 122 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Requested | 2. Concept | 1001777 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-14 17:00 | -31 | -0.10954 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 14
Requested | -10% to -5% | Project 122 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | 1001777 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-17 17:00 | -28 | -0.09894 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 14
Requested | -10% to -5% | Project 122 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Requested | 2. Concept | 1001777 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-30 17:00 | -22 | -0.077739 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 14
Requested | -10% to -5% | Project 93 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Requested | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-05-12 17:00 | 2025-02-28 17:00 | -48 | -0.094862 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 13
Requested | N/A | Project 116 | Closure Phase | Deliverable | Unassigned | Requested | 2. Concept | 1001755 |  | Delay reason known here | 2025-07-04 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Requested | N/A | Project 116 | Documentation Deliverables (SAD,BRD,Test Plan) | Deliverable | Unassigned | Requested | 2. Concept | 1001755 |  | Delay reason known here | 2025-05-16 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Requested | N/A | Project 116 | Analysis and Design Phase Completed | Deliverable | Unassigned | Requested | 2. Concept | 1001755 |  | Delay reason known here | 2025-05-16 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Requested | N/A | Project 116 | Procurement phase completed | Deliverable | Unassigned | Requested | 2. Concept | 1001755 |  | Delay reason known here | 2025-04-24 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 36
Requested | N/A | Project 116 | Build and test completed | Deliverable | Unassigned | Requested | 2. Concept | 1001755 |  | Delay reason known here | 2025-06-02 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Requested | N/A | Project 55 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Requested | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Requested | N/A | Project 55 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Requested | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Requested | N/A | Project 55 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Requested | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Requested | N/A | Project 55 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Requested | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Requested | N/A | Project 55 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Requested | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Requested | N/A | Project 110 | Performance Test suite Migration | Deliverable | Unassigned | Requested | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-08-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Open/Active | <-25% | Project 11 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-12-24 17:00 | 2024-03-01 17:00 | -452 | -0.26386 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2026 | No | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 17
Open/Active | -5% to 0% | Project 19 | CIS Applications Migration Build & Test Complete | Governance | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-01 17:00 | 2025-03-31 17:00 | -20 | -0.012353 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | CIS Applications Mig'n Implementation & GO LIVE | Governance | Go-Live | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-19 17:00 | 2025-05-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 5 | PROJECT CLOSED (GATE 3): Stage 1 | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2027-03-05 17:00 | 2027-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Implement Archiving Solution | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-12-24 08:00 | 2026-12-24 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 16 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2026-08-31 17:00 | 2026-08-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Open/Active | 0% | Project 23 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-07-01 17:00 | 2025-07-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% | Project 23 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-07-02 17:00 | 2025-07-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% | Project 23 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-07-02 17:00 | 2025-07-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | -5% to 0% | Project 23 | ANALYSIS & DESIGN PHASE 3 COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-05-27 17:00 | 2025-05-19 17:00 | -6 | -0.010204 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 33
Open/Active | 0% | Project 23 | BUILD & TEST PHASE 3 COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-06-18 17:00 | 2025-06-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% | Project 23 | IMPLEMENT PHASE 3 COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-07-01 17:00 | 2025-07-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% | Project 10 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 6. Implement | 1000301 |  | Delay reason known here | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 10 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 6. Implement | 1000301 |  | Delay reason known here | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 10 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1000301 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 10 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1000301 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | GR5.07 Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-09-01 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-09-01 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-09-19 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 5.03 Release Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-09-12 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-09-19 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-09-01 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-09-22 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-09-30 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | GR6.07 Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-10-01 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-11-03 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-11-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-12-01 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | HYB6.04 Release Retrospective Complete | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-11-03 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-11-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-12-05 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | BUSINESS GO LIVE (R4 Dates to be Built in) | Deliverable | Go-Live | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-12-24 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-12-24 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-12-24 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-12-24 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 11 | 7.03 Closure Checklist & Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-12-24 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 5 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2027-02-10 17:00 | 2027-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2027-01-13 17:00 | 2027-01-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2027-03-03 17:00 | 2027-03-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | -5% to 0% | Project 5 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-05-15 17:00 | 2025-02-26 17:00 | -53 | -0.01994 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 8
Open/Active | 0% | Project 29 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Open/Active | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 61 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 42 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2027-02-05 17:00 | 2027-02-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2027-02-12 17:00 | 2027-02-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2027-02-19 17:00 | 2027-02-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2027-02-26 17:00 | 2027-02-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | -25% to -10% | Project 42 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-07-31 17:00 | 2025-02-14 17:00 | -115 | -0.16476 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | Project Manager 29
Open/Active | <-25% | Project 42 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-10-31 17:00 | 2025-02-21 17:00 | -175 | -0.25072 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | Project Manager 29
Open/Active | <-25% | Project 42 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-11-28 17:00 | 2025-02-13 17:00 | -201 | -0.28797 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | Project Manager 29
Open/Active | <-25% | Project 42 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-11-14 17:00 | 2025-02-14 17:00 | -190 | -0.27221 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | Project Manager 29
Open/Active | -10% to -5% | Project 42 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-05-09 17:00 | 2025-02-28 17:00 | -47 | -0.067335 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-10-13 17:00 | 2025-10-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-11-03 17:00 | 2025-11-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-11-21 17:00 | 2025-11-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-10-13 17:00 | 2025-10-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-10-01 17:00 | 2025-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-11-03 17:00 | 2025-11-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-11-14 17:00 | 2025-11-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-11-12 17:00 | 2025-11-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-11-28 17:00 | 2025-11-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | GO LIVE | Deliverable | Go-Live | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 42 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2026-12-18 17:00 | 2026-12-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 16 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2026-08-14 17:00 | 2026-08-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Open/Active | 0% | Project 16 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2026-08-21 17:00 | 2026-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Open/Active | 0% | Project 16 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2026-08-28 17:00 | 2026-08-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Open/Active | 0% | Project 19 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2027-06-18 17:00 | 2027-06-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2027-06-11 17:00 | 2027-06-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2027-06-25 17:00 | 2027-06-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2027-06-30 17:00 | 2027-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | -25% to -10% | Project 77 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-05-16 17:00 | 2025-01-31 08:00 | -73 | -0.23397 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 38
Open/Active | <-25% | Project 77 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-06-30 17:00 | 2025-02-14 08:00 | -93 | -0.29808 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 38
Open/Active | <-25% | Project 77 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-05-30 17:00 | 2025-01-31 08:00 | -83 | -0.26603 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 38
Open/Active | <-25% | Project 77 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-06-30 17:00 | 2025-02-14 08:00 | -93 | -0.29808 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 38
Open/Active | -5% to 0% | Project 77 | MARITIME S/W OP INCIDENT MGT VENDOR SELECTED | Governance | Unassigned | Open/Active | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-07-11 17:00 | 2025-07-11 08:00 | -1 | -0.0032051 | #REF! | Duplicate | Sub-Portfolio 4 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 38
Open/Active | 0% | Project 93 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-06-20 17:00 | 2025-06-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Open/Active | 0% | Project 93 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Open/Active | -10% to -5% | Project 93 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-05-09 17:00 | 2025-02-28 17:00 | -47 | -0.092885 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 13
Open/Active | -5% to 0% | Project 75 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-06-23 17:00 | 2025-06-06 17:00 | -10 | -0.037313 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 75 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-06-23 17:00 | 2025-06-20 17:00 | -1 | -0.0037313 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | 0% | Project 75 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-06-27 17:00 | 2025-06-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | 0% | Project 75 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | 0% | Project 76 | 3.14 Project Management Plan Sign Off (use SoW) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | 3.00 EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | 7.00 PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 59 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-07-15 08:00 | 2025-07-15 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Open/Active | 0% | Project 59 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-07-15 08:00 | 2025-07-15 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Open/Active | 0% | Project 59 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-07-16 08:00 | 2025-07-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Open/Active | 0% | Project 59 | 7.00 PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-07-16 08:00 | 2025-07-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Open/Active | -25% to -10% | Project 59 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-05-30 17:00 | 2024-12-20 17:00 | -101 | -0.22909 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 14
Open/Active | -25% to -10% | Project 59 | 3.00 EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-05-30 17:00 | 2024-12-20 17:00 | -101 | -0.22909 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 14
Open/Active | -5% to 0% | Project 68 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-05-15 17:00 | 2025-04-30 17:00 | -11 | -0.038194 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 12
Open/Active | -10% to -5% | Project 68 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-30 17:00 | -22 | -0.076389 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 12
Open/Active | -10% to -5% | Project 68 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-30 17:00 | -22 | -0.076389 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-08 17:00 | 2025-10-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-08 17:00 | 2025-10-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-10 17:00 | 2025-10-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-08 17:00 | 2025-10-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-10 17:00 | 2025-10-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | TRANCHE 3 GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-08 17:00 | 2025-10-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-17 17:00 | 2025-10-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | -25% to -10% | Project 66 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-05-01 17:00 | 2024-12-20 17:00 | -80 | -0.24768 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 12
Open/Active | -10% to -5% | Project 66 | 4.01 Sol'n Architecture Design (SAD) Sign Off LLID | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-05-05 17:00 | 2025-04-04 17:00 | -18 | -0.055728 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 12
Open/Active | -10% to -5% | Project 66 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-05-05 17:00 | 2025-04-04 17:00 | -18 | -0.055728 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 12
Open/Active | -10% to -5% | Project 66 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-05-16 17:00 | 2025-04-04 17:00 | -27 | -0.083591 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-08-08 17:00 | 2025-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-08-15 17:00 | 2025-08-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-08-08 17:00 | 2025-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-07-28 17:00 | 2025-07-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-08-14 17:00 | 2025-08-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | GO LIVE Production | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-08-15 17:00 | 2025-08-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-08-18 17:00 | 2025-08-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | -25% to -10% | Project 75 | 4.11 Security Risk Assessment (SRA) Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -0.15672 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -25% to -10% | Project 75 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-02 17:00 | 2025-02-25 17:00 | -45 | -0.16791 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -25% to -10% | Project 75 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -0.15672 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 75 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-16 17:00 | 2025-04-29 17:00 | -13 | -0.048507 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 75 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-09 17:00 | 2025-04-17 17:00 | -13 | -0.048507 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 75 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-09 17:00 | 2025-04-17 17:00 | -13 | -0.048507 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 75 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-09 17:00 | 2025-04-28 17:00 | -9 | -0.033582 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 75 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-29 17:00 | -23 | -0.085821 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 75 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-30 17:00 | -22 | -0.08209 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 75 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-06-13 17:00 | 2025-05-12 17:00 | -23 | -0.085821 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 75 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-06-13 17:00 | 2025-05-09 17:00 | -24 | -0.089552 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 75 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-06-13 17:00 | 2025-05-16 17:00 | -19 | -0.070896 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 75 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-06-06 17:00 | 2025-05-05 17:00 | -24 | -0.089552 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 75 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-06-13 17:00 | 2025-05-20 17:00 | -17 | -0.063433 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 75 | GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-06-20 17:00 | 2025-05-21 17:00 | -21 | -0.078358 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 75 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-06-20 17:00 | 2025-05-30 17:00 | -14 | -0.052239 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | <-25% | Project 71 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-01 08:00 | 2024-11-22 17:00 | -99 | -0.29043 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 30
Open/Active | -10% to -5% | Project 71 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-24 17:00 | -25 | -0.073341 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 30
Open/Active | -10% to -5% | Project 71 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-30 17:00 | -22 | -0.06454 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 30
Open/Active | -10% to -5% | Project 71 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-17 17:00 | -28 | -0.082142 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 30
Open/Active | -10% to -5% | Project 71 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-17 17:00 | -28 | -0.082142 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 30
Open/Active | -10% to -5% | Project 71 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-11 17:00 | -32 | -0.093876 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 30
Open/Active | -25% to -10% | Project 71 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-30 17:00 | 2025-03-14 17:00 | -52 | -0.15255 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 30
Open/Active | -10% to -5% | Project 71 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-29 17:00 | -23 | -0.067473 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 30
Open/Active | -10% to -5% | Project 71 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-28 17:00 | -24 | -0.070407 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 30
Open/Active | -10% to -5% | Project 71 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-29 17:00 | -23 | -0.067473 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 30
Open/Active | -10% to -5% | Project 71 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-30 17:00 | -22 | -0.06454 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 30
Open/Active | -25% to -10% | Project 71 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-07-31 17:00 | 2025-03-28 17:00 | -85 | -0.24936 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | Project Manager 30
Open/Active | -25% to -10% | Project 71 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-07-31 17:00 | 2025-03-28 17:00 | -85 | -0.24936 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | Project Manager 30
Open/Active | -25% to -10% | Project 71 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-07-31 17:00 | 2025-04-23 17:00 | -69 | -0.20242 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | Project Manager 30
Open/Active | -25% to -10% | Project 71 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-08-29 17:00 | 2025-05-09 17:00 | -79 | -0.23176 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Project Manager 30
Open/Active | -25% to -10% | Project 71 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-08-29 17:00 | 2025-05-23 17:00 | -69 | -0.20242 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Project Manager 30
Open/Active | -25% to -10% | Project 71 | GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-08-29 17:00 | 2025-05-30 17:00 | -64 | -0.18775 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Project Manager 30
Open/Active | -25% to -10% | Project 71 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-08-29 17:00 | 2025-06-06 17:00 | -59 | -0.17308 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Project Manager 30
Open/Active | -25% to -10% | Project 71 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-09-30 17:00 | 2025-06-13 17:00 | -77 | -0.22589 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Project Manager 30
Open/Active | -25% to -10% | Project 71 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-09-30 17:00 | 2025-06-25 17:00 | -69 | -0.20242 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Project Manager 30
Open/Active | -25% to -10% | Project 71 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-09-30 17:00 | 2025-06-30 08:00 | -67 | -0.19655 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Project Manager 30
Open/Active | -5% to 0% | Project 64 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1001350 |  | Delay reason known here | 2025-05-01 17:00 | 2025-04-17 17:00 | -7 | -0.045455 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 25
Open/Active | -5% to 0% | Project 64 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1001350 |  | Delay reason known here | 2025-05-01 17:00 | 2025-04-17 17:00 | -7 | -0.045455 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 25
Open/Active | -5% to 0% | Project 64 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | 1001350 |  | Delay reason known here | 2025-05-01 17:00 | 2025-04-17 17:00 | -7 | -0.045455 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 25
Open/Active | -25% to -10% | Project 77 | RFP DOCUMENTATION COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-04 08:00 | -38 | -0.12179 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 38
Open/Active | -10% to -5% | Project 77 | CLOSED RFP LAUNCHED (w/ 10 Selected Vendors) | Governance | Unassigned | Open/Active | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-06-13 17:00 | 2025-05-02 08:00 | -30 | -0.096154 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 38
Open/Active | -5% to 0% | Project 77 | PROPOSAL REVIEW COMPLETE | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-06-13 17:00 | 2025-06-13 08:00 | -1 | -0.0032051 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 38
Open/Active | 0% | Project 61 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | GO LIVE Oracle Solaris: DOCUMENTUM | Deliverable | Go-Live | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | GO LIVE Oracle Solaris: RailTable Suite of Apps | Deliverable | Go-Live | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | DEP OUT - GO LIVE Oracle Solaris: TPS | Deliverable | Go-Live | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-06-02 17:00 | 2025-06-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | BUILD & TEST PHASE COMPLETE (DOCUMENTUM) | Governance | Unassigned | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-07-18 17:00 | 2025-07-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 61 | 5.00 ICT Release Board Approval (CAB) for TPS | Deliverable | Unassigned | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-06-20 17:00 | 2025-06-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 65 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 6. Implement | 1001351 |  | Delay reason known here | 2025-05-02 17:00 | 2025-05-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 65 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | 1001351 |  | Delay reason known here | 2025-05-02 17:00 | 2025-05-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 65 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 6. Implement | 1001351 |  | Delay reason known here | 2025-05-02 17:00 | 2025-05-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 65 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 6. Implement | 1001351 |  | Delay reason known here | 2025-05-02 17:00 | 2025-05-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 65 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 6. Implement | 1001351 |  | Delay reason known here | 2025-05-23 17:00 | 2025-05-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% to 5% | Project 65 | SQUIZ - SMS GO LIVE | Deliverable | Go-Live | Open/Active | 6. Implement | 1001351 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-30 17:00 | 10 | 0.045249 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 65 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 6. Implement | 1001351 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 65 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1001351 |  | Delay reason known here | 2025-06-06 17:00 | 2025-06-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 65 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1001351 |  | Delay reason known here | 2025-06-13 17:00 | 2025-06-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 65 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1001351 |  | Delay reason known here | 2025-06-20 17:00 | 2025-06-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 65 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | 1001351 |  | Delay reason known here | 2025-06-20 17:00 | 2025-06-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | 0% | Project 5 | 4.01 Sol'n Architecture Design (SAD) Sign Off 1.3 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-01-13 17:00 | 2026-01-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-01-13 17:00 | 2026-01-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-01-13 17:00 | 2026-01-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 4.09 Test Plan Sign Off 1.3 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | -10% to -5% | Project 59 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-05-01 17:00 | 2025-02-28 17:00 | -41 | -0.092997 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 14
Open/Active | -10% to -5% | Project 59 | 4.00 ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-05-01 17:00 | 2025-02-28 17:00 | -41 | -0.092997 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 14
Open/Active | 0% | Project 59 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Open/Active | 0% | Project 59 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-05-14 08:00 | 2025-05-14 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Open/Active | 0% | Project 59 | 5.00 BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-05-16 08:00 | 2025-05-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Open/Active | 0% | Project 59 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-05-14 08:00 | 2025-05-14 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Open/Active | 0% | Project 59 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-05-16 08:00 | 2025-05-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Open/Active | -5% to 0% | Project 59 | 6.00 GO LIVE PHASE 1 | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-06-20 17:00 | 2025-05-27 08:00 | -18 | -0.040828 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 14
Open/Active | -5% to 0% | Project 59 | 6.00 IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-06-23 17:00 | 2025-05-28 17:00 | -17 | -0.03856 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 14
Open/Active | 0% | Project 93 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-05-02 17:00 | 2025-05-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Open/Active | 0% | Project 93 | GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-05-06 17:00 | 2025-05-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Open/Active | 0% | Project 93 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-05-07 17:00 | 2025-05-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Open/Active | -10% to -5% | Project 16 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-10-01 17:00 | 2025-04-02 08:00 | -127 | -0.059152 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | Project Manager 34
Open/Active | -10% to -5% | Project 16 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-10-01 17:00 | 2025-04-11 08:00 | -120 | -0.055892 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-10-24 17:00 | 2025-08-15 08:00 | -50 | -0.023288 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-10-31 17:00 | 2025-08-01 08:00 | -65 | -0.030275 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-10-13 17:00 | 2025-08-08 08:00 | -46 | -0.021425 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-10-31 17:00 | 2025-08-15 08:00 | -55 | -0.025617 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-10-31 17:00 | 2025-08-22 08:00 | -50 | -0.023288 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-10-31 17:00 | 2025-08-29 17:00 | -44 | -0.020494 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-08-25 17:00 | 2025-08-25 08:00 | -1 | -0.00046577 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-08-27 17:00 | 2025-08-27 08:00 | -1 | -0.00046577 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-09-12 17:00 | 2025-09-12 08:00 | -1 | -0.00046577 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-09-19 17:00 | 2025-09-19 08:00 | -1 | -0.00046577 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-09-24 17:00 | 2025-09-24 08:00 | -1 | -0.00046577 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-09-25 17:00 | 2025-09-25 08:00 | -1 | -0.00046577 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | GO LIVE TCOPS PHASE 1 | Deliverable | Go-Live | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-11-14 17:00 | 2025-09-29 08:00 | -34 | -0.015836 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -5% to 0% | Project 16 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-11-17 17:00 | 2025-09-30 08:00 | -34 | -0.015836 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 34
Open/Active | -25% to -10% | Project 63 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -0.12651 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 63 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-03-31 08:00 | -22 | -0.066265 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 63 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-03-31 08:00 | -22 | -0.066265 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -25% to -10% | Project 63 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-02-21 17:00 | -47 | -0.14157 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 63 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -0.033133 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 63 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-04-22 08:00 | -8 | -0.024096 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 63 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-04-14 08:00 | -12 | -0.036145 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 63 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-03-28 08:00 | -23 | -0.069277 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -25% to -10% | Project 63 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -0.12651 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -25% to -10% | Project 63 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-02-28 17:00 | -42 | -0.12651 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 63 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-03-17 08:00 | -32 | -0.096386 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 63 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-03-31 08:00 | -22 | -0.066265 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -10% to -5% | Project 63 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-03-17 08:00 | -32 | -0.096386 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 63 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-04-30 17:00 | -2 | -0.0060241 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | 0% | Project 63 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-06-13 08:00 | 2025-06-13 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 63 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -0.033133 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | 0% | Project 63 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-06-13 08:00 | 2025-06-13 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 63 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -0.033133 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | 0% | Project 63 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-06-02 17:00 | 2025-06-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | 0% | Project 63 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-06-13 17:00 | 2025-06-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 63 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-04-30 17:00 | -2 | -0.0060241 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 63 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -0.033133 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 63 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -0.033133 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | 0% | Project 63 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-06-13 08:00 | 2025-06-13 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | 0% | Project 63 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-12 17:00 | 2025-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | 0% | Project 63 | GO LIVE: First 8-10 Vessels/Vehicles Ready | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-06-17 08:00 | 2025-06-17 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | 0% | Project 63 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-06-18 08:00 | 2025-06-18 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | 0% | Project 63 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-06-30 08:00 | 2025-06-30 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | 0% | Project 63 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-08-01 08:00 | 2025-08-01 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | 0% | Project 63 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-08-01 08:00 | 2025-08-01 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 63 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -0.033133 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | -5% to 0% | Project 63 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 | 2025-04-15 08:00 | -11 | -0.033133 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | 0% | Project 76 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-06-06 17:00 | 2025-06-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | 5.00 BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-06-06 17:00 | 2025-06-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 76 | 6.00 IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 23 | GO LIVE - OT-IT Ph3 | Deliverable | Go-Live | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-06-25 17:00 | 2025-06-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% | Project 23 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-06-18 17:00 | 2025-06-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | -5% to 0% | Project 23 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-05-27 17:00 | 2025-04-17 17:00 | -25 | -0.042517 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 33
Open/Active | -5% to 0% | Project 19 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-01 17:00 | 2025-03-31 17:00 | -20 | -0.012353 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | 5.00 Service Continuity Runbook Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-01 17:00 | 2025-03-31 17:00 | -20 | -0.012353 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 6.02 Implementation Plan Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 6.00 Application Handover Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 5.00 Service Continuity Runbook Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-30 08:00 | 2025-05-30 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 6.02 Implementation Plan Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-30 08:00 | 2025-05-30 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-12 17:00 | 2025-06-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | 6.00 Application Handover Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-13 17:00 | 2025-06-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 29 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 29 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 29 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 29 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 5 | 5.01 Test Cases Sign Off 1.3 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | 5.02 Test Summary Report/Cert Sign Off 1.3 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | N/A | Project 110 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Open/Active | N/A | Project 110 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Open/Active | N/A | Project 110 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Open/Active | N/A | Project 110 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Open/Active | N/A | Project 110 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Open/Active | N/A | Project 110 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Open/Active | N/A | Project 110 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Open/Active | N/A | Project 110 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Open/Active | N/A | Project 110 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Open/Active | <-25% | Project 75 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-01 17:00 | 2024-12-04 17:00 | -92 | -0.34328 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | <-25% | Project 75 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-01 17:00 | 2024-12-04 17:00 | -92 | -0.34328 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 18
Open/Active | 0% to 5% | Project 23 | OT-IT PH3 End of Build | Deliverable | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-05-23 17:00 | 2025-06-04 17:00 | 8 | 0.013605 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | -5% to 0% | Project 19 | 5.06 Release Requested - Blocksheets | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-02 17:00 | 2025-02-28 17:00 | -63 | -0.038913 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-06 17:00 | 2025-02-28 17:00 | -67 | -0.041384 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | 6.02 Implementation Plan Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-02 17:00 | 2025-03-31 17:00 | -42 | -0.025942 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-20 17:00 | 2025-03-31 17:00 | -55 | -0.033972 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | BlockSheets GO LIVE | Deliverable | Go-Live | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-30 17:00 | 2025-04-07 17:00 | -56 | -0.034589 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-30 17:00 | 2025-03-31 17:00 | -41 | -0.025324 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | 5.06 Release Requested - SSTS | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-02 17:00 | 2025-04-17 17:00 | -29 | -0.017912 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | 5.00 Service Continuity Runbook Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-30 17:00 | 2025-03-31 17:00 | -41 | -0.025324 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-02 17:00 | 2025-03-31 17:00 | -42 | -0.025942 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | SSTS BUILD & TEST PHASE COMPLETE | Governance | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-30 17:00 | 2025-03-31 17:00 | -41 | -0.025324 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-02 17:00 | 2025-04-29 17:00 | -24 | -0.014824 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | 6.02 Implementation Plan Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-02 17:00 | 2025-04-29 17:00 | -24 | -0.014824 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-02 17:00 | 2025-04-29 17:00 | -24 | -0.014824 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | 6.00 Application Handover Checklist Complete | Deliverable | Yes | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-02 17:00 | 2025-04-29 17:00 | -24 | -0.014824 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 19 | SSTS GO LIVE | Deliverable | Go-Live | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-30 17:00 | 2025-04-30 17:00 | -42 | -0.025942 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 6
Open/Active | N/A | Project 7 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | 1000298 |  | Delay reason known here | 2025-05-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | -5% to 0% | Project 7 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | 1000298 |  | Delay reason known here | 2025-06-06 17:00 | 2025-04-30 17:00 | -27 | -0.035573 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 38
Open/Active | -5% to 0% | Project 7 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 6. Implement | 1000298 |  | Delay reason known here | 2025-06-30 17:00 | 2025-05-30 17:00 | -20 | -0.02635 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 38
Open/Active | -5% to 0% | Project 7 | GO LIVE (NSW BOSN) | Deliverable | Go-Live | Open/Active | 6. Implement | 1000298 |  | Delay reason known here | 2025-07-31 17:00 | 2025-06-16 17:00 | -33 | -0.043478 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Project Manager 38
Open/Active | -10% to -5% | Project 7 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1000298 |  | Delay reason known here | 2025-09-03 17:00 | 2025-06-30 17:00 | -47 | -0.061924 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Project Manager 38
Open/Active | -10% to -5% | Project 7 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1000298 |  | Delay reason known here | 2025-09-03 17:00 | 2025-06-30 17:00 | -47 | -0.061924 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Project Manager 38
Open/Active | -10% to -5% | Project 7 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | 1000298 |  | Delay reason known here | 2025-09-03 17:00 | 2025-06-30 17:00 | -47 | -0.061924 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Project Manager 38
Open/Active | <-25% | Project 62 | 3.06 HL Business Requirements Document Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-05-16 17:00 | 2025-01-31 17:00 | -72 | -0.36364 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 16
Open/Active | <-25% | Project 62 | 3.11 Prelim Sol'n Options Roadmap Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-05-16 17:00 | 2025-01-31 17:00 | -72 | -0.36364 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 16
Open/Active | <-25% | Project 62 | 3.21 Final Business Case Approved (Light Touch) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-06-12 17:00 | 2025-01-31 17:00 | -90 | -0.45455 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 16
Open/Active | <-25% | Project 62 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-06-19 17:00 | 2025-01-31 17:00 | -95 | -0.4798 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 16
Open/Active | -5% to 0% | Project 74 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-05-07 17:00 | 2025-04-30 17:00 | -5 | -0.020325 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-06-16 08:00 | 2025-06-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-06-16 08:00 | 2025-06-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-06-16 08:00 | 2025-06-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-06-16 08:00 | 2025-06-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-07-04 17:00 | 2025-07-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | GO LIVE - LEGACY SHAREPOINT MIGRATION (GOV DC) | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | 0% | Project 74 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | N/A | Project 109 | GO LIVE | Deliverable | Go-Live | Open/Active | 6. Implement | 1001608 |  | Delay reason known here | 2025-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 5
Open/Active | N/A | Project 109 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 6. Implement | 1001608 |  | Delay reason known here | 2025-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 5
Open/Active | N/A | Project 109 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1001608 |  | Delay reason known here | 2025-05-07 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 5
Open/Active | N/A | Project 109 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1001608 |  | Delay reason known here | 2025-05-09 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 5
Open/Active | N/A | Project 109 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1001608 |  | Delay reason known here | 2025-05-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 5
Open/Active | N/A | Project 109 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | 1001608 |  | Delay reason known here | 2025-05-16 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 5
Open/Active | 0% | Project 23 | 6.03 Go Live Readiness Complete | Deliverable | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-06-23 17:00 | 2025-06-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% | Project 23 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-06-25 17:00 | 2025-06-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% | Project 23 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-06-24 17:00 | 2025-06-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% | Project 23 | 6.05 Service Design & Definition Complete (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-06-20 17:00 | 2025-06-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% | Project 23 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-06-23 17:00 | 2025-06-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% to 5% | Project 23 | OT-IT PH3 End of SIT | Deliverable | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-05-30 17:00 | 2025-06-18 17:00 | 12 | 0.020408 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% to 5% | Project 23 | OT-IT PH3 End of UAT | Deliverable | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-06-06 17:00 | 2025-06-18 17:00 | 7 | 0.011905 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% | Project 23 | HDI>>SAA Req't (Ph1 Jun'25, Ph2 Sep'25) | External | Unassigned | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-05-27 17:00 | 2025-05-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | N/A | Project 111 | UAT Signed Off | Deliverable | Unassigned | Open/Active | 6. Implement | 1001618 |  | Delay reason known here | 2025-05-05 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Open/Active | N/A | Project 111 | Deploy into GSIT Prod completion/final signoff | Deliverable | Go-Live | Open/Active | 6. Implement | 1001618 |  | Delay reason known here | 2025-05-30 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Open/Active | 0% | Project 77 | VENDOR CONTRACT SIGNED (PHASE 2 END) | Governance | Unassigned | Open/Active | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-07-31 08:00 | 2025-07-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 10 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 6. Implement | 1000301 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 63 | Training Documentation Ready | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-06-13 08:00 | 2025-06-13 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | -25% to -10% | Project 11 | TMS R4 Go-live (TBC) | Deliverable | Go-Live | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-12-24 17:00 | 2025-01-01 17:00 | -247 | -0.14419 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | Project Manager 17
Open/Active | -10% to -5% | Project 11 | TMS R4 UAT Interface & Testing Support Complete | Deliverable | Yes | Open/Active | 6. Implement | 1000302 |  | Delay reason known here | 2025-09-30 17:00 | 2025-03-17 17:00 | -137 | -0.079977 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | Project Manager 17
Open/Active | 0% | Project 10 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 6. Implement | 1000301 |  | Delay reason known here | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 23 | PROJECT CLOSED (GATE 3) Phase 2 | Governance | Gate 3 Approval | Open/Active | 6. Implement | 1000314 |  | Delay reason known here | 2025-07-02 17:00 | 2025-07-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Open/Active | 0% | Project 10 | Business GO LIVE | Deliverable | Go-Live | Open/Active | 6. Implement | 1000301 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 10 | Technical Deployment | Deliverable | Unassigned | Open/Active | 6. Implement | 1000301 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 10 | IMPLEMENT PHASE COMPLETE | Governance | Unassigned | Open/Active | 6. Implement | 1000301 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 10 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 6. Implement | 1000301 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 72 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-05 17:00 | 2025-05-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 61 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Gate 3 Approval | Open/Active | 6. Implement | 1001328 |  | Delay reason known here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Open/Active | 0% | Project 19 | TRIMS (VIZIRAIL) GO LIVE (CONFIRMED FY26) | Deliverable | Go-Live | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2026-06-30 17:00 | 2026-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 10% to 25% | Project 19 | FMCS GO LIVE - Minor Release targeting 31/7 | Deliverable | Go-Live | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-07-31 17:00 | 2026-06-30 17:00 | 221 | 0.1365 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | -5% to 0% | Project 5 | TPS.Plan SIT environment readiness | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-05-19 17:00 | 2025-04-14 17:00 | -22 | -0.0082769 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | TPS.Plan PROD&DR environment readiness | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-06-26 17:00 | 2025-06-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | TPS.Plan DEV03 environment readiness | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-07-17 17:00 | 2025-07-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Integration PSAD endorse by GSIT PDA | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-12-09 17:00 | 2025-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | -5% to 0% | Project 5 | Contract execution | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-05-23 17:00 | 2025-03-31 17:00 | -36 | -0.013544 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 8
Open/Active | -5% to 0% | Project 5 | SOW for TPS.Plan installation and configuration | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-05-16 17:00 | 2025-04-30 17:00 | -12 | -0.0045147 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 8
Open/Active | -5% to 0% | Project 5 | SOW Review & Sign-Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-05-23 17:00 | 2025-05-07 17:00 | -12 | -0.0045147 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Define Application Managed Support Services (AMSS) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-06-04 17:00 | 2025-06-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | -5% to 0% | Project 5 | Service Design Workshops & Define Support Model | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-06-30 17:00 | 2025-04-04 17:00 | -57 | -0.021445 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 8
Open/Active | -5% to 0% | Project 5 | Document the Support Process | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-04 17:00 | -17 | -0.0063958 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Business & IT Stakeholder Socialization | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-07-30 17:00 | 2025-07-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Service Design Sign-Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-08-13 17:00 | 2025-08-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | -5% to 0% | Project 5 | Test Plan & Test Cases readiness | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-05-19 17:00 | 2025-04-11 17:00 | -23 | -0.0086531 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | SIT Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-07-01 17:00 | 2025-07-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | UAT Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-08-14 17:00 | 2025-08-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | NFR Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-08-14 17:00 | 2025-08-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | End of warranty support | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-09-17 17:00 | 2025-09-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Go-Live Business Approval | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-08-15 17:00 | 2025-08-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Decommission TPAC Rail Suite (RailNet & RailTable) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-11-12 17:00 | 2026-11-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Decommission other GSIT Managed Apps Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-11-12 17:00 | 2026-11-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | PSAD (R1.3 entire solution) endorse by GSIT PDA | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-11-03 17:00 | 2025-11-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Integration & Application SAD sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-12-15 17:00 | 2025-12-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Interface control document sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-12-22 17:00 | 2025-12-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Integration solution build | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-04-22 17:00 | 2026-04-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Application solution build | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-04-23 17:00 | 2026-04-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Report SAD sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-01-13 17:00 | 2026-01-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Report solution build | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-03 17:00 | 2026-03-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Test Plan & Test Cases Readiness | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-05 17:00 | 2026-03-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | SIT Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-06-12 17:00 | 2026-06-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | UAT Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-07-24 17:00 | 2026-07-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Regression Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-08-14 17:00 | 2026-08-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | NFR Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Update BAU Documents & Sign-Off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-04 17:00 | 2026-03-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Go-Live Business Approval | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-09-02 17:00 | 2026-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | End of warranty support | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-09-30 17:00 | 2026-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | SOE design | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-08-20 17:00 | 2025-08-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Installation and SOE package rollout | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-11-13 17:00 | 2025-11-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Monitor and hardware procurement | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-09-17 17:00 | 2025-09-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | PSAD (R1.2 entire solution) endorse by GSIT PDA | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-06-25 17:00 | 2025-06-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Integration & Application SAD sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-08-13 17:00 | 2025-08-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Interface control document sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-07-30 17:00 | 2025-07-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Integration solution build | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-08-20 17:00 | 2025-08-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Application solution build | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-09-03 17:00 | 2025-09-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Report SAD sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-08-04 17:00 | 2025-08-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Report solution build | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-09-15 17:00 | 2025-09-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Test Plan & Test Cases readiness | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-11-05 17:00 | 2025-11-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | SIT Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-12-09 17:00 | 2025-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | UAT Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-04 17:00 | 2026-03-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | NFR Test Summary Report | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-26 17:00 | 2026-03-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Update BAU documents and sign-off | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-11-20 17:00 | 2025-11-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | Go-Live Business Approval | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-31 17:00 | 2026-03-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 5 | End of warranty support | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-04-30 17:00 | 2026-04-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 66 | InfoArchive Build Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-05-23 17:00 | 2025-05-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 66 | Data Migration Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-07-25 17:00 | 2025-07-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | TRANCHE 1 GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-06-27 17:00 | 2025-06-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | TRANCHE 2 GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-08-07 17:00 | 2025-08-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | N/A | Project 5 | 5.02 Test Summary Report/Cert Sign Off (R1.1) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-08-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | N/A | Project 5 | 5.02 Test Summary Report/Cert Sign Off (R1.2) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-03-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | N/A | Project 5 | 4.01 Sol'n Architecture Design (SAD) Sign Off 1.3 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-08-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | N/A | Project 5 | 4.01 Sol'n Architecture Design (SAD) Sign Off 1.2 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-08-04 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | N/A | Project 5 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-05-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Open/Active | 0% | Project 73 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-05-09 17:00 | 2025-05-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-06-13 17:00 | 2025-06-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-06-17 17:00 | 2025-06-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | End of Sprint 3 | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-05-06 17:00 | 2025-05-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | End of Sprint 5 | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-06-03 17:00 | 2025-06-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | End of Sprint 4 | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-05-20 17:00 | 2025-05-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 29 | Procurement Decision: How to Engage Vendor | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | 0% | Project 29 | Statement of Work Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Open/Active | N/A | Project 65 | SQUIZ - SECURE LIBRARY GO LIVE | Deliverable | Go-Live | Open/Active | 6. Implement | 1001351 |  | Delay reason known here | 2025-05-02 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Open/Active | N/A | Project 3 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | N/A | Project 3 | 7.02 PIR Sign Off (done for Phase 2 Only) | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | N/A | Project 3 | 7.03 Closure Memo Sign Off for Phase 3 | Deliverable | Gate 3 Approval | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | N/A | Project 3 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | N/A | Project 3 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-18 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | N/A | Project 3 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-18 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | N/A | Project 3 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-18 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | N/A | Project 3 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-18 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | N/A | Project 3 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-18 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | N/A | Project 3 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-18 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | N/A | Project 3 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-18 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | N/A | Project 3 | GO LIVE | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-18 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | N/A | Project 3 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-09-18 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2027 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Open/Active | 0% | Project 68 | End of Sprint 5 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-05-13 17:00 | 2025-05-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | End of Sprint 6 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-05-27 17:00 | 2025-05-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | End of Sprint 7 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-06-10 17:00 | 2025-06-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | End of Sprint 8 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-06-24 17:00 | 2025-06-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | End of Sprint 9 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-07-08 17:00 | 2025-07-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | End of Sprint 10 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-07-22 17:00 | 2025-07-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | End of Sprint 11 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-08-05 17:00 | 2025-08-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | End of Sprint 12 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-08-19 17:00 | 2025-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | End of Sprint 13 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-02 17:00 | 2025-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | End of Sprint 14 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-16 17:00 | 2025-09-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | End of Sprint 15 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | End of Sprint 16 | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | N/A | Project 93 | Task Assigner Development Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-08-29 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Open/Active | N/A | Project 93 | eSCD Development Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-10-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Open/Active | N/A | Project 93 | Task Assigner UAT Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-12-24 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Open/Active | N/A | Project 93 | TCSS Prod Deployment | Deliverable | Go-Live | Open/Active | 3. Evaluate | 1001440 |  | Delay reason known here | 2026-01-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Open/Active | N/A | Project 93 | MyRoster Development Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-08-29 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Open/Active | N/A | Project 93 | CAS Development Complete | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-10-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Open/Active | 0% | Project 72 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 6.01 Training Docs & App H'over Checklist Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | GO LIVE | Deliverable | Go-Live | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 72 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | Sprint Plan | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-05-06 17:00 | 2025-05-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | Sprint Review | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-05-06 17:00 | 2025-05-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-05-06 17:00 | 2025-05-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | Sprint Plan | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-05-20 17:00 | 2025-05-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | Sprint Review | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-05-20 17:00 | 2025-05-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-05-20 17:00 | 2025-05-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | Sprint Plan | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-06-03 17:00 | 2025-06-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | Sprint Review | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-06-03 17:00 | 2025-06-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 73 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-06-03 17:00 | 2025-06-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Open/Active | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-05-13 17:00 | 2025-05-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-05-13 17:00 | 2025-05-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-05-13 17:00 | 2025-05-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-05-27 17:00 | 2025-05-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-05-27 17:00 | 2025-05-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-05-27 17:00 | 2025-05-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-06-10 17:00 | 2025-06-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-06-10 17:00 | 2025-06-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-06-10 17:00 | 2025-06-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-06-24 17:00 | 2025-06-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-06-24 17:00 | 2025-06-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-06-24 17:00 | 2025-06-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-07-08 17:00 | 2025-07-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-07-08 17:00 | 2025-07-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-07-08 17:00 | 2025-07-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-07-22 17:00 | 2025-07-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-07-22 17:00 | 2025-07-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-07-22 17:00 | 2025-07-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-08-05 17:00 | 2025-08-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-08-05 17:00 | 2025-08-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-08-05 17:00 | 2025-08-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-08-19 17:00 | 2025-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-08-19 17:00 | 2025-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-08-19 17:00 | 2025-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-02 17:00 | 2025-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-02 17:00 | 2025-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-02 17:00 | 2025-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-16 17:00 | 2025-09-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-16 17:00 | 2025-09-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-16 17:00 | 2025-09-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-10-14 17:00 | 2025-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Open/Active | N/A | Project 79 | Production Deployment Phase 1 | Deliverable | Go-Live | Open/Active | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2025-08-18 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | N/A | Project 79 | Production Deployment Phase 2 | Deliverable | Go-Live | Open/Active | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2025-11-10 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 74 | Site Locking - Banners - Server Stop - Decomm End | Deliverable | Unassigned | Open/Active | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-09-30 17:00 | 2025-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 28
Open/Active | N/A | Project 63 | RFP Finalisation | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-05-02 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Open/Active | N/A | Project 114 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 114 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Open/Active | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
Open/Active | N/A | Project 79 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Open/Active | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2025-10-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | N/A | Project 79 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2025-11-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | N/A | Project 79 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2025-11-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | N/A | Project 79 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Open/Active | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2025-11-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | N/A | Project 79 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Open/Active | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2025-11-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | N/A | Project 79 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2025-10-24 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | N/A | Project 79 | 5.02 Test Summary Ph2 Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2025-10-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | N/A | Project 79 | 5.01 System Integration Test Cases Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2025-07-11 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | N/A | Project 79 | 5.02 Test Summary Ph1 Report/Cert Sign Off | Deliverable | Unassigned | Open/Active | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2025-07-11 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Open/Active | 0% | Project 19 | Ph1 - GovDC uplift Migration Implementation | Governance | Go-Live | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-16 08:00 | 2025-06-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Open/Active | 0% | Project 19 | Ph1 - GovDC Migration Build and Test Complete | Governance | Unassigned | Open/Active | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-16 17:00 | 2025-05-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | TCSS Mig'n Scratch & Design Complete | Governance | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-12-18 17:00 | 2024-12-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 6 | ICFMS DB migration plan as a subset of BC | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2023-12-21 17:00 | 2023-12-21 17:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | -25% to -10% | Project 101 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-30 17:00 | 2024-08-30 17:00 | -97 | -0.118 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-30 17:00 | 2024-08-30 17:00 | -97 | -0.118 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-30 17:00 | 2024-08-30 17:00 | -97 | -0.118 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-30 17:00 | 2024-08-30 17:00 | -97 | -0.118 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -10% to -5% | Project 101 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-27 17:00 | 2024-10-21 17:00 | -82 | -0.099757 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-19 17:00 | 2024-09-27 17:00 | -91 | -0.11071 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -10% to -5% | Project 101 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-27 17:00 | 2024-10-21 17:00 | -82 | -0.099757 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -10% to -5% | Project 101 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-27 17:00 | 2024-10-21 17:00 | -82 | -0.099757 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -10% to -5% | Project 101 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-03 17:00 | 2024-11-04 17:00 | -74 | -0.090024 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -10% to -5% | Project 101 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-05 17:00 | 2024-11-11 17:00 | -71 | -0.086375 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -10% to -5% | Project 101 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-27 17:00 | 2024-10-21 17:00 | -82 | -0.099757 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -10% to -5% | Project 101 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-05 17:00 | 2024-11-11 17:00 | -71 | -0.086375 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-31 17:00 | 2025-02-18 17:00 | -29 | -0.03528 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-11 17:00 | 2025-02-18 17:00 | -15 | -0.018248 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-21 17:00 | 2025-02-18 17:00 | -23 | -0.027981 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-26 17:00 | 2025-02-18 17:00 | -26 | -0.03163 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-05 17:00 | 2025-02-18 17:00 | -11 | -0.013382 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-10 17:00 | 2025-02-18 17:00 | -14 | -0.017032 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-13 17:00 | 2025-02-18 17:00 | -17 | -0.020681 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-21 17:00 | 2025-02-18 17:00 | -23 | -0.027981 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-04-04 17:00 | 2025-02-18 17:00 | -33 | -0.040146 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | 0% to 5% | Project 101 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-03-18 17:00 | 41 | 0.049878 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | 5% to 10% | Project 101 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-03 17:00 | 2025-05-02 17:00 | 61 | 0.074209 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 5% to 10% | Project 101 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-05-09 17:00 | 76 | 0.092457 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 5% to 10% | Project 101 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-03 17:00 | 2025-05-09 17:00 | 66 | 0.080292 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 5% to 10% | Project 101 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-03 17:00 | 2025-05-09 17:00 | 66 | 0.080292 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 10% to 25% | Project 101 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-05-23 17:00 | 86 | 0.10462 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 5% to 10% | Project 101 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-03 17:00 | 2025-05-30 17:00 | 81 | 0.09854 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 10% to 25% | Project 101 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-06-06 17:00 | 96 | 0.11679 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 10% to 25% | Project 101 | GO LIVE | Deliverable | Go-Live | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-03 17:00 | 2025-06-12 17:00 | 89 | 0.10827 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 10% to 25% | Project 101 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-06-12 17:00 | 99 | 0.12044 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 10% to 25% | Project 101 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-24 17:00 | 2025-06-20 08:00 | 99 | 0.12044 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 10% to 25% | Project 101 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-03 17:00 | 2025-06-27 08:00 | 99 | 0.12044 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 10% to 25% | Project 101 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-10 17:00 | 2025-07-04 08:00 | 99 | 0.12044 | #REF! | Duplicate | Sub-Portfolio 2 | 2026 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 0% to 5% | Project 101 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-06-27 17:00 | 2025-07-11 08:00 | 9 | 0.010949 | #REF! | Duplicate | Sub-Portfolio 2 | 2026 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-27 17:00 | -87 | -0.10584 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-20 17:00 | 2024-10-04 17:00 | -87 | -0.10584 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-27 17:00 | 2024-10-14 17:00 | -87 | -0.10584 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-06 17:00 | 2024-09-20 17:00 | -107 | -0.13017 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-05 17:00 | 2025-02-18 17:00 | -11 | -0.013382 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-07 17:00 | 2025-02-18 17:00 | -13 | -0.015815 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | 0% to 5% | Project 101 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-02-25 17:00 | 26 | 0.03163 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | 5% to 10% | Project 101 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-05-16 17:00 | 81 | 0.09854 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 5% to 10% | Project 101 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-05-16 17:00 | 81 | 0.09854 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 0% to 5% | Project 101 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-02-25 17:00 | 26 | 0.03163 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-18 17:00 | 2025-02-18 17:00 | -20 | -0.024331 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.04 HYB Definition of Done | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-25 17:00 | 2025-02-18 17:00 | -25 | -0.030414 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | N/A | Project 17 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 5.04 Training Management Plan Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2025-01-20 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-12-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 101 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-30 17:00 | 2024-08-30 17:00 | -97 | -0.118 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-05 17:00 | 2025-02-18 17:00 | -11 | -0.013382 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | 5% to 10% | Project 101 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-05-09 17:00 | 76 | 0.092457 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | N/A | Project 17 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2025-01-22 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 5.03 Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-11 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-11 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-11 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-11 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-04 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 3.08 Release Plan | Deliverable | Project Kickoff | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-04 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-09-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-04 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 17 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-09-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -5% to 0% | Project 101 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-03 17:00 | 2025-02-18 17:00 | -9 | -0.010949 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-06 17:00 | 2025-02-18 17:00 | -12 | -0.014599 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-04-04 17:00 | 2025-02-18 17:00 | -33 | -0.040146 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-04-01 17:00 | 2025-02-18 17:00 | -30 | -0.036496 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | 10% to 25% | Project 101 | 6.01 Training Docs & App H'over Checklist Complete | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-06-06 17:00 | 96 | 0.11679 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | N/A | Project 17 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-12-10 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 10% to 25% | Project 101 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-06-06 17:00 | 96 | 0.11679 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 5% to 10% | Project 101 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2025-05-09 17:00 | 76 | 0.092457 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | -5% to 0% | Project 101 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-18 17:00 | 2025-02-18 17:00 | -20 | -0.024331 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | N/A | Project 17 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-11 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 0% | Project 6 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | -25% to -10% | Project 101 | DEP IN: Inbound Dependency | External | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-17 17:00 | 2024-08-02 17:00 | -109 | -0.1326 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | N/A | Project 17 | HDO>>EPS Program UAT Commencement 30/9 | External | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-09-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 101 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 101 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-13 17:00 | 2024-09-20 17:00 | -92 | -0.11192 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -10% to -5% | Project 101 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-27 17:00 | 2024-10-21 17:00 | -82 | -0.099757 | #REF! | Duplicate | Sub-Portfolio 2 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0
On Hold | -25% to -10% | Project 3 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-08-28 17:00 | 2025-06-13 17:00 | -298 | -0.24267 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | 0% | Project 93 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-10-17 17:00 | 2024-10-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | -5% to 0% | Project 3 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-02-07 17:00 | 2024-11-04 17:00 | -58 | -0.047231 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -5% to 0% | Project 3 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-02-14 17:00 | 2024-12-02 17:00 | -43 | -0.035016 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-06-13 17:00 | 2024-11-22 17:00 | -130 | -0.10586 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -5% to 0% | Project 3 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-02-14 17:00 | 2024-11-21 17:00 | -50 | -0.040717 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 3 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here |  | 2024-11-04 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-06-13 17:00 | 2024-12-02 17:00 | -124 | -0.10098 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 3 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here |  | 2024-12-06 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -10% to -5% | Project 3 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-04-17 17:00 | 2024-12-02 17:00 | -87 | -0.070847 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 3 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here |  | 2024-12-06 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 3 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here |  | 2024-11-15 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -5% to 0% | Project 3 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-02-14 17:00 | 2024-11-15 17:00 | -54 | -0.043974 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 3 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here |  | 2024-11-04 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-11-28 17:00 | 2024-11-20 17:00 | -251 | -0.2044 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -5% to 0% | Project 3 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-12 17:00 | -13 | -0.010586 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 0% to 5% | Project 3 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-09-27 17:00 | 2024-11-01 17:00 | 24 | 0.019544 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 0% to 5% | Project 3 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-09-27 17:00 | 2024-11-14 17:00 | 33 | 0.026873 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 0% | Project 3 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -5% to 0% | Project 3 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-02-07 17:00 | 2024-11-04 17:00 | -58 | -0.047231 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -5% to 0% | Project 3 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-02-07 17:00 | 2024-11-11 17:00 | -53 | -0.04316 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -5% to 0% | Project 3 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-02-07 17:00 | 2024-11-18 17:00 | -48 | -0.039088 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-06-13 17:00 | 2024-11-25 17:00 | -129 | -0.10505 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 0% | Project 93 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-24 17:00 | 2025-02-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-25 17:00 | 2025-02-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-17 17:00 | 2025-02-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-04 17:00 | 2025-02-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-07 17:00 | 2025-02-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-06 17:00 | 2025-02-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-13 17:00 | 2024-12-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-01-07 17:00 | 2025-01-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-01-10 17:00 | 2025-01-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | 0% | Project 93 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-19 17:00 | 2024-12-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 13
On Hold | -25% to -10% | Project 3 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-08-29 17:00 | 2025-01-23 17:00 | -151 | -0.12296 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-08-29 17:00 | 2024-12-20 17:00 | -165 | -0.13436 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | N/A | Project 3 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here |  | 2025-01-10 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 3 | 4.04 HYB Definition of Done | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here |  | 2025-01-17 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-08-29 17:00 | 2025-01-24 17:00 | -150 | -0.12215 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | N/A | Project 3 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here |  | 2025-01-30 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-08-29 17:00 | 2024-11-22 17:00 | -185 | -0.15065 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-08-29 17:00 | 2025-01-20 17:00 | -154 | -0.12541 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-08-29 17:00 | 2024-12-20 17:00 | -165 | -0.13436 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -10% to -5% | Project 3 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-04-24 17:00 | 2025-01-08 17:00 | -73 | -0.059446 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-08-29 17:00 | 2025-01-13 17:00 | -159 | -0.12948 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-11-28 17:00 | 2025-01-16 17:00 | -220 | -0.17915 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-12-12 17:00 | 2025-01-21 17:00 | -227 | -0.18485 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-12-12 17:00 | 2024-12-20 17:00 | -239 | -0.19463 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-12-12 17:00 | 2025-01-08 17:00 | -236 | -0.19218 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-09-26 17:00 | 2025-01-07 17:00 | -183 | -0.14902 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-12-12 17:00 | 2025-01-30 17:00 | -221 | -0.17997 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-09-05 17:00 | 2025-02-20 17:00 | -137 | -0.11156 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-11-28 17:00 | 2025-03-06 17:00 | -186 | -0.15147 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-11-28 17:00 | 2025-03-20 17:00 | -176 | -0.14332 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | N/A | Project 3 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here |  | 2025-02-20 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-11-28 17:00 | 2025-04-03 17:00 | -166 | -0.13518 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-11-28 17:00 | 2025-04-03 17:00 | -166 | -0.13518 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-11-28 17:00 | 2025-04-03 17:00 | -166 | -0.13518 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-11-28 17:00 | 2025-04-03 17:00 | -166 | -0.13518 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -25% to -10% | Project 3 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-11-28 17:00 | 2025-04-03 17:00 | -166 | -0.13518 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2026 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | <-25% | Project 3 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-08-28 17:00 | 2025-04-09 17:00 | -341 | -0.27769 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2027 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | <-25% | Project 3 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-08-28 17:00 | 2025-04-15 17:00 | -337 | -0.27443 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2027 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | <-25% | Project 3 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-08-28 17:00 | 2025-04-23 17:00 | -333 | -0.27117 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2027 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | 0% | Project 3 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 3 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here |  | 2025-04-09 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | <-25% | Project 3 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-08-28 17:00 | 2025-05-06 17:00 | -325 | -0.26466 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | <-25% | Project 3 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-08-28 17:00 | 2025-05-12 17:00 | -321 | -0.2614 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | <-25% | Project 3 | GO LIVE | Deliverable | Go-Live | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-08-28 17:00 | 2025-05-16 17:00 | -317 | -0.25814 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | <-25% | Project 3 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2026-08-28 17:00 | 2025-05-30 08:00 | -308 | -0.25081 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Project Manager 4
On Hold | -5% to 0% | Project 3 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-02-07 17:00 | 2024-12-03 17:00 | -37 | -0.03013 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -5% to 0% | Project 3 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-02-07 17:00 | 2024-12-05 17:00 | -35 | -0.028502 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 0% | Project 19 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.03 HYB Team Charter (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.04 HYB Definition of Done | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-11-01 17:00 | 2024-11-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-11-13 17:00 | 2024-11-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.09 Test Plan Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.10 Traceability Matrix Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-12-10 17:00 | 2024-12-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-12-13 17:00 | 2024-12-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-12-18 17:00 | 2024-12-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-10 17:00 | 2024-10-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-11-25 17:00 | 2024-11-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.00 P80 Cost Estimate Ready | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-01-08 17:00 | 2025-01-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.01 Test Cases Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-01-15 17:00 | 2025-01-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-01-22 17:00 | 2025-01-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-01-08 17:00 | 2025-01-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.06 Release Requested (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.00 Service Continuity Runbook Complete | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-03-25 17:00 | 2025-03-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-04-04 17:00 | 2025-04-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.02 Implementation Plan Complete | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-04-08 17:00 | 2025-04-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-04-24 17:00 | 2025-04-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.04 HYB Release Retrospective Complete | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-03-21 17:00 | 2025-03-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-07 17:00 | 2025-05-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.00 Application Handover Checklist Complete | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-19 17:00 | 2025-05-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-14 17:00 | 2024-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-16 17:00 | 2024-10-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-10 17:00 | 2024-10-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-21 17:00 | 2024-10-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-11-26 17:00 | 2024-11-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-11-27 17:00 | 2024-11-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-11-25 17:00 | 2024-11-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 29 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-08-29 17:00 | 2025-08-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2026-07-31 17:00 | 2026-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-05-07 17:00 | 2025-05-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-05-21 17:00 | 2025-05-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-04 17:00 | 2025-06-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-04 17:00 | 2025-06-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-19 17:00 | 2025-06-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-19 17:00 | 2025-06-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-19 17:00 | 2025-06-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-19 17:00 | 2025-06-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-19 17:00 | 2025-06-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-25 17:00 | 2025-06-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-07-01 17:00 | 2025-07-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-07-07 17:00 | 2025-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-07-11 17:00 | 2025-07-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-06-25 17:00 | 2025-06-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-07-17 17:00 | 2025-07-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-07-23 17:00 | 2025-07-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | GO LIVE | Deliverable | Go-Live | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-07-29 17:00 | 2025-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2026-06-30 17:00 | 2026-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2026-06-30 17:00 | 2026-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2026-06-30 17:00 | 2026-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 29 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | On Hold | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2026-06-30 17:00 | 2026-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
On Hold | 0% | Project 5 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-09-01 17:00 | 2026-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | 0% | Project 5 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | On Hold | 3. Evaluate | 1000296 |  | Delay reason known here | 2026-12-24 17:00 | 2026-12-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2027 | 2027 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
On Hold | -25% to -10% | Project 17 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2025-01-17 17:00 | 2024-08-28 08:00 | -92 | -0.1262 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 17 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-12-11 17:00 | 2024-08-28 08:00 | -75 | -0.10288 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 0% | Project 6 | Procurement Strategy | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2022-12-23 | 2022-12-23 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | Identify the upstream and down stream Apps | Unassigned | Yes | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2023-09-28 17:00 | 2023-09-28 17:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | <-25% | Project 17 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 17:00 | 2023-09-28 08:00 | -269 | -0.369 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 0% | Project 6 | Investment Brief signed off | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2022-10-14 | 2022-10-14 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | SAD Approved and Signed off | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2020-07-03 | 2020-07-03 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2021 | 2021 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 19 | Ph2 (Cloud) Migration Discovery Complete | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | Ph2 (Cloud) Migration Analysis Complete | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-30 17:00 | 2025-06-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | TCSS Mig'n Build & Test Complete | Governance | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | TCSS Mig'n Implementation & Go Live | Deliverable | Go-Live | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-05-30 17:00 | 2025-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 6 | PCR#1 Approval | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2023-08-31 | 2023-08-31 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | Obtain Sign off to the options | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2020-07-06 | 2020-07-06 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2021 | 2021 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 19 | Ph2 (Cloud) Migration Scratch & Design Complet | Governance | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-07-31 17:00 | 2025-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 6 | Obtain Sign off on PACT | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2022-09-29 | 2022-09-29 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 19 | Ph2 (Cloud) Migration Build and Test Complete | Governance | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-10-31 17:00 | 2025-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | Ph2 (Cloud) Migration Implementation & go-live | Governance | Go-Live | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-12-12 17:00 | 2025-12-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 6 | Concept Phase Complete | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2022-09-30 | 2022-09-30 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | -25% to -10% | Project 17 | Build Complete | Unassigned | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 08:00 | 2024-04-10 08:00 | -143 | -0.19616 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | <-25% | Project 17 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-11 08:00 | 2023-10-06 08:00 | -249 | -0.34156 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -10% to -5% | Project 17 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2025-02-28 17:00 | 2024-11-07 08:00 | -71 | -0.097394 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | <-25% | Project 17 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-11-29 17:00 | 2023-12-01 17:00 | -244 | -0.33471 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -10% to -5% | Project 17 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 08:00 | 2024-08-02 17:00 | -62 | -0.085048 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 17 | BUILD & TEST PHASE COMPLETE | Governance | Yes | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-12-20 17:00 | 2024-08-09 17:00 | -94 | -0.12894 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 0% | Project 6 | Detailed Design Document Sign-off | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2022-10-06 | 2022-10-06 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | -25% to -10% | Project 17 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-12-09 17:00 | 2024-08-23 17:00 | -75 | -0.10288 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -10% to -5% | Project 17 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2025-01-31 17:00 | 2024-10-15 08:00 | -68 | -0.093278 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -10% to -5% | Project 17 | 7.03 Closure Checklist & Memo Sign Off | Deliverable | Gate 3 Approval | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2025-02-24 17:00 | 2024-10-31 17:00 | -71 | -0.097394 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 0% | Project 6 | Business Case for Phase 2 Complete | Deliverable | Project Kickoff | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2024-06-21 17:00 | 2024-06-21 17:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | Prod environment for HCL DX Platform | Unassigned | Yes | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2024-05-13 08:00 | 2024-05-13 08:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 19 | Ramsys & Trackware Migrt. Build & Test Complete | Governance | Unassigned | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 19 | Ramsys & Trackware Migrt. Implementation & Go Live | Governance | Go-Live | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-12-16 08:00 | 2024-12-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
On Hold | 0% | Project 6 | Completion of Post-Production Support & Handover | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | WebSphere UI Migration Complete | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | -25% to -10% | Project 17 | GO LIVE | Deliverable | Go-Live | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2025-01-31 17:00 | 2024-08-30 17:00 | -98 | -0.13443 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | <-25% | Project 17 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Yes | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 08:00 | 2023-09-27 17:00 | -268 | -0.36763 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | <-25% | Project 17 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 08:00 | 2023-09-27 17:00 | -268 | -0.36763 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | <-25% | Project 17 | Data Risk Assessment Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 | This is the milestone for GSIT decision to use GIS dataset for ePAS. | Delay reason known here | 2024-10-11 08:00 | 2023-10-20 17:00 | -238 | -0.32647 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 17 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 08:00 | 2024-04-24 17:00 | -132 | -0.18107 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 17 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2025-02-14 17:00 | 2024-08-23 17:00 | -113 | -0.15501 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 17 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2025-02-21 17:00 | 2024-10-14 17:00 | -83 | -0.11385 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -10% to -5% | Project 17 | UAT Complete | Unassigned | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 08:00 | 2024-07-26 17:00 | -67 | -0.091907 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | -25% to -10% | Project 17 | SIT Complete | Unassigned | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-31 08:00 | 2024-06-21 17:00 | -92 | -0.1262 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | N/A | Project 101 | Release to Pre-Prod | Unassigned | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-03-11 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 2 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | N/A | Project 101 | Release Scope Close | Unassigned | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-01-24 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 2 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | N/A | Project 101 | Release to SIT | Unassigned | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-02-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 2 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | N/A | Project 101 | UAT Exit Q-Gate | Unassigned | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-04-10 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 2 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | N/A | Project 101 | Regression Exit Q-Gate | Unassigned | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-05-14 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 2 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | N/A | Project 101 | Release Scope Close | Unassigned | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-07-28 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 2 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | N/A | Project 101 | Release to SIT | Unassigned | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-08-21 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 2 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | N/A | Project 101 | Release to Pre-Prod | Unassigned | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-09-12 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 2 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | N/A | Project 101 | UAT Exit Q-Gate | Unassigned | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-10-14 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 2 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | N/A | Project 101 | Regression Exit Q-Gate | Unassigned | Unassigned | On Hold | 2. Concept | 1001493 |  | Delay reason known here | 2025-11-12 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 2 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
On Hold | 0% | Project 6 | Production Go-live | Unassigned | Go-Live | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2024-05-20 08:00 | 2024-05-20 08:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | <-25% | Project 17 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-09-13 17:00 | 2023-10-16 17:00 | -224 | -0.30727 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 0% | Project 6 | Architecting Cloud landing zones approvals for Pha | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2023-04-06 | 2023-04-06 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | The HCL contact drafts for WPS upgrade & DB upgard | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2023-03-10 | 2023-03-10 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | Resource re-alignment post Cloud PDA approvals | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2023-04-17 | 2023-04-17 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | Re-baseline the project by excemption | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2023-05-12 | 2023-05-12 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | Investment Brief Signed off | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2022-12-23 | 2022-12-23 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | Concept SGR Completed | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2022-12-23 | 2022-12-23 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | Project Management Plan | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2023-08-31 | 2023-08-31 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | Evaluate SGR Completed | Unassigned | Unassigned | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2023-08-31 | 2023-08-31 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | <-25% | Project 17 | 4.14 Detailed Service design & Defn Onboard pk | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-11 08:00 | 2023-11-10 17:00 | -223 | -0.3059 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
On Hold | 0% | Project 6 | Migration approach document post application disco | Unassigned | Yes | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2023-09-27 17:00 | 2023-09-27 17:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | 0% | Project 6 | SIT environment for HCL DX Platform | Unassigned | Yes | On Hold | 7. Closure | 1000297 |  | Delay reason known here | 2023-12-18 17:00 | 2023-12-18 17:00 | 0 |  | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
On Hold | N/A | Project 73 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 73 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 73 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 73 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 73 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 73 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 73 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 73 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 73 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 73 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 73 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 73 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 73 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | 0% | Project 73 | End of Sprint 6 | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-06-17 17:00 | 2025-06-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | 0% | Project 73 | Sprint Plan | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-06-17 17:00 | 2025-06-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | 0% | Project 73 | Sprint Review | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-06-17 17:00 | 2025-06-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | 0% | Project 73 | Sprint Retrospective | Deliverable | Unassigned | On Hold | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-06-17 17:00 | 2025-06-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
On Hold | N/A | Project 55 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | N/A | Project 55 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | On Hold | 2. Concept | 1001276 |  | Delay reason known here | 2025-06-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 20
On Hold | 0% | Project 19 | Ph2 (Cloud) Migration Establishment | Deliverable | Yes | On Hold | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Oracle Apex - GSU Migration Build and Test | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-02-19 17:00 | 2024-02-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Oracle Apex - GSU Migration Scratch and Design | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-02-16 17:00 | 2024-02-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Applications ITSI Dashboards - complete (AWS) | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-07-19 17:00 | 2024-07-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Applications ITSI Dashboards - complete (AZURE) | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-07-19 17:00 | 2024-07-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Implements across AWS & Azure Anycloud - complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-07-19 17:00 | 2024-07-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 7 | Procurement Documentation Complete | Unassigned | Yes | Assumed Completed | 6. Implement | 1000298 |  | Delay reason known here | 2024-04-04 17:00 | 2024-04-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 14 | Project: Redgate Migration Complete | Deliverable | Go-Live | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2024-03-28 08:00 | 2024-03-28 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | -5% to 0% | Project 14 | Project: PCM Migration to DOMO Complete | Deliverable | Go-Live | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2024-04-30 17:00 | 2024-03-28 08:00 | -21 | -0.019126 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | -5% to 0% | Project 14 | Project: FMCS Decommission Complete | Deliverable | Go-Live | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2024-01-22 08:00 | 2023-12-29 08:00 | -10 | -0.0091075 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 5 | Commence Contract Negotiation | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2023-11-13 17:00 | 2023-11-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | FIP approval to award vendor contract | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-03-15 17:00 | 2024-03-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2022-05-12 17:00 | 2022-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2022-06-02 17:00 | 2022-06-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Obtain Funding to Support Procurement | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2022-07-04 17:00 | 2022-07-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2023-07-27 17:00 | 2023-07-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Briefing Note Approval to Recruit IT Delivery Lead | Governance | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-07-30 17:00 | 2024-07-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Briefing Note Approval to Recruit Remaining Roles | Governance | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | N/A | Project 44 | Test Complete | Unassigned | Unassigned | Assumed Completed | Unassigned | 1001051 |  | Delay reason known here | 2024-05-31 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 1 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 44 | Implement Complete | Unassigned | Unassigned | Assumed Completed | Unassigned | 1001051 |  | Delay reason known here | 2024-07-19 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 1 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 44 | 533 AIMS Enhancement Complete | Unassigned | Unassigned | Assumed Completed | Unassigned | 1001051 |  | Delay reason known here | 2024-07-19 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 1 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | 0% | Project 13 | Pilot Test Plan signed off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-02-13 17:00 | 2023-02-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-05-24 17:00 | 2024-05-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-04-08 17:00 | 2024-04-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-07-11 17:00 | 2024-07-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-04-08 17:00 | 2024-04-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | PCR Approved 8 Feb'24 | Governance | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-02-08 08:00 | 2024-02-08 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 9 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-09-21 17:00 | 2023-09-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-09-21 17:00 | 2023-09-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 3.16 Stakeholder Assessment & Eng Plan | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-10-30 17:00 | 2023-10-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 3.01 Non-Standard Service Request Submitted | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2022-12-16 17:00 | 2022-12-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 4.12 Comms Plan Sign-off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 3.02 GR Cyber Security Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 3.03 GR Cyber Security Assessment Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | GR4.16 Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 19 | FPE-ST Decomm Complete | Deliverable | Unassigned | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 9 | IIMSS IMPLEMENTATION 2 (5 Aug'24) | Deliverable | Go-Live | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | N/A | Project 17 | 2.00 Investment Brief (IB) / SoW Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2023-09-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | N/A | Project 17 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2023-09-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | N/A | Project 17 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2023-09-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 9 | PCR-01: Enhancements SalesForce 2 way Integration | Governance | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-01-24 17:00 | 2024-01-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | -5% to 0% | Project 9 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-11-08 17:00 | 2024-10-04 17:00 | -24 | -0.049818 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | N/A | Project 20 | IMPLEMENT PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-10-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | N/A | Project 20 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-11-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | N/A | Project 20 | 6.03 Go Live Readiness Complete | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-09-26 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | N/A | Project 20 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-05-17 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | N/A | Project 20 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-05-24 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | N/A | Project 20 | 5.03 Release Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | N/A | Project 20 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-05-17 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | N/A | Project 17 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | N/A | Project 14 | (PDA) Architecture & Security Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2023-05-04 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2023 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | N/A | Project 14 | Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2023-05-04 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2023 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | N/A | Project 14 | P20 Cost Estimate Approved | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2023-05-04 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2023 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | N/A | Project 14 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2023-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2023 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | N/A | Project 14 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | N/A | Project 14 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2024-07-10 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | N/A | Project 14 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2024-07-10 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | N/A | Project 14 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2024-07-10 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | N/A | Project 14 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2024-07-24 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 27 | Investment Brief (IB)/SoW Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000840 |  | Delay reason known here | 2024-07-09 17:00 | 2024-07-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 27 | (PDA) Architecture & Security Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000840 |  | Delay reason known here | 2024-07-09 17:00 | 2024-07-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 27 | Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000840 |  | Delay reason known here | 2024-07-09 17:00 | 2024-07-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 27 | P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000840 |  | Delay reason known here | 2024-07-09 17:00 | 2024-07-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 27 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 2. Concept | 1000840 |  | Delay reason known here | 2024-07-09 17:00 | 2024-07-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 13 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-09-13 17:00 | 2023-09-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-09-13 17:00 | 2023-09-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 23 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-12-11 17:00 | 2024-12-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2025-03-03 17:00 | 2025-03-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | -5% to 0% | Project 23 | 6.03 Go Live Readiness Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2025-04-24 17:00 | 2025-04-08 17:00 | -10 | -0.017007 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | -10% to -5% | Project 23 | 6.05 Service Design & Definition Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2025-04-24 17:00 | 2025-03-05 17:00 | -34 | -0.057823 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | -5% to 0% | Project 13 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-12-05 17:00 | 2024-11-29 08:00 | -5 | -0.0090253 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-04-26 17:00 | 2024-04-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-07-24 17:00 | 2024-07-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.11 Prelim Solution Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-03-15 17:00 | 2024-03-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | -5% to 0% | Project 13 | DEP OUT: TRAK2 is a Soft Dependency for Solaris | Unassigned | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-06 17:00 | -1 | -0.0018051 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-04-10 17:00 | 2024-04-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-04-10 17:00 | 2024-04-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-04-10 17:00 | 2024-04-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-04-10 17:00 | 2024-04-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-04-12 17:00 | 2024-04-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-05-24 17:00 | 2024-05-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 9 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-10-30 17:00 | 2023-10-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 6.05 Service Design & Definition Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | GR:6.07 Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | PCR-02: Extend project to end Aug'24 | Governance | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-06-20 17:00 | 2024-06-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | Service Continuity Runbook Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-08 17:00 | 2024-04-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | GR5.07 Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-05-24 17:00 | 2024-05-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 5.03 Release Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-05-24 17:00 | 2024-05-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-05-24 17:00 | 2024-05-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 08:00 | 2024-04-19 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-09-07 17:00 | 2023-09-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | GR4.17 Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 13 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 10 | 2.00 Investment Brief (IB) / SoW Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2022-08-18 17:00 | 2022-08-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2022-08-18 17:00 | 2022-08-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2022-08-18 17:00 | 2022-08-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2022-08-18 17:00 | 2022-08-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.00 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2022-11-25 17:00 | 2022-11-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 5.03 Release Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2024-11-21 17:00 | 2024-11-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 17 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-06-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | N/A | Project 17 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-06-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 10 | PCR-02: Extend project to FY25 Q2 (Approved 26/6) | Governance | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2024-06-26 17:00 | 2024-06-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 79 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-06-27 17:00 | 2024-06-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-06-27 17:00 | 2024-06-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-06-27 17:00 | 2024-06-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-06-27 17:00 | 2024-06-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-06-27 17:00 | 2024-06-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | N/A | Project 11 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2019-10-21 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2020 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2019-10-21 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2020 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2019-10-21 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2020 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-07-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-07-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-07-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-07-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-07-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-07-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-07-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-07-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-07-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 11 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-07-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | -10% to -5% | Project 27 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000840 |  | Delay reason known here | 2024-09-18 17:00 | 2024-08-02 17:00 | -33 | -0.068465 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | -10% to -5% | Project 27 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000840 |  | Delay reason known here | 2024-09-18 17:00 | 2024-08-02 17:00 | -33 | -0.068465 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | -5% to 0% | Project 27 | 3.04 PACT Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000840 |  | Delay reason known here | 2024-09-02 17:00 | 2024-08-02 17:00 | -21 | -0.043568 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | -5% to 0% | Project 27 | 3.06 Business Requirements Document Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000840 |  | Delay reason known here | 2024-09-02 17:00 | 2024-08-02 17:00 | -21 | -0.043568 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | -5% to 0% | Project 27 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000840 |  | Delay reason known here | 2024-09-02 17:00 | 2024-08-02 17:00 | -21 | -0.043568 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | -5% to 0% | Project 27 | 3.14 Project Management Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000840 |  | Delay reason known here | 2024-09-02 17:00 | 2024-08-02 17:00 | -21 | -0.043568 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | -10% to -5% | Project 27 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Unassigned | Assumed Completed | 2. Concept | 1000840 |  | Delay reason known here | 2024-09-30 17:00 | 2024-08-02 17:00 | -41 | -0.085062 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-07 17:00 | 2024-08-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-07 17:00 | 2024-08-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-07-15 17:00 | 2024-07-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-07-01 17:00 | 2024-07-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-07-24 17:00 | 2024-07-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-07-19 17:00 | 2024-07-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-22 17:00 | 2024-08-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-22 17:00 | 2024-08-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-09-17 17:00 | 2024-09-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 23 | 2.00 Investment Brief Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-04-28 17:00 | 2023-04-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-04-28 17:00 | 2023-04-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-04-28 17:00 | 2023-04-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-04-28 17:00 | 2023-04-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-04-28 17:00 | 2023-04-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | -5% to 0% | Project 23 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2025-04-24 17:00 | 2025-03-31 17:00 | -16 | -0.027211 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | -5% to 0% | Project 23 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2025-04-01 17:00 | 2025-03-10 17:00 | -16 | -0.027211 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | -5% to 0% | Project 23 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2025-04-24 17:00 | 2025-03-28 17:00 | -17 | -0.028912 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-11-26 17:00 | 2024-11-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-11-26 17:00 | 2024-11-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-11-26 17:00 | 2024-11-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-11-27 17:00 | 2024-11-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-06-24 17:00 | 2024-06-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-10-10 17:00 | 2024-10-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | HDI>>ODS Control Systems 23/8 (Andrew Wilson) | External | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | SDI>>ODS Control Systems 23/8 (Andrew Wilson) | External | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 13 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-07-11 17:00 | 2024-07-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-07-19 17:00 | 2024-07-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-06-14 17:00 | 2024-06-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 29 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2021-07-01 17:00 | 2021-07-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 29 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2021-09-30 17:00 | 2021-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 29 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2021-09-30 17:00 | 2021-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 29 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2021-07-30 17:00 | 2021-07-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 29 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2021-09-30 17:00 | 2021-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 5 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2022-07-04 17:00 | 2022-07-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 2.00 Investment Brief (IB / BN) / SoW Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2022-07-04 17:00 | 2022-07-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2022-07-04 17:00 | 2022-07-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2022-07-04 17:00 | 2022-07-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 29 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2024-11-07 17:00 | 2024-11-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 29 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-01-06 17:00 | 2025-01-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 29 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-01-23 17:00 | 2025-01-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 29 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2024-11-21 17:00 | 2024-11-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 29 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2024-12-18 17:00 | 2024-12-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 29 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 29 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2024-11-21 17:00 | 2024-11-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% to 5% | Project 29 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-04-09 17:00 | 2025-04-17 17:00 | 6 | 0.0047207 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 5% to 10% | Project 13 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-04 17:00 | 2024-11-22 17:00 | 34 | 0.061372 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-11-22 17:00 | 2024-11-29 17:00 | 5 | 0.0090253 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-11-01 17:00 | 2024-11-15 17:00 | 10 | 0.018051 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-25 17:00 | 2024-11-22 17:00 | 20 | 0.036101 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-28 17:00 | 2024-10-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-25 17:00 | 2024-10-28 17:00 | 1 | 0.0018051 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-09 17:00 | 2024-10-28 17:00 | 13 | 0.023466 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-11-01 17:00 | 2024-11-08 17:00 | 5 | 0.0090253 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-25 17:00 | 2024-10-28 17:00 | 1 | 0.0018051 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-25 17:00 | 2024-10-28 17:00 | 1 | 0.0018051 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-21 17:00 | 2024-10-28 17:00 | 5 | 0.0090253 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-21 17:00 | 2024-10-28 17:00 | 5 | 0.0090253 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-28 17:00 | 18 | 0.032491 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-28 17:00 | 18 | 0.032491 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-28 17:00 | 18 | 0.032491 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 79 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 79 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 42 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 5% to 10% | Project 42 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-12-02 17:00 | 2025-02-28 17:00 | 53 | 0.075931 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-09-11 17:00 | 2024-09-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-12 17:00 | 2024-08-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-12 17:00 | 2024-08-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-12 17:00 | 2024-08-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-12 17:00 | 2024-08-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 42 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% to 5% | Project 42 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-10-31 17:00 | 2024-11-01 17:00 | 1 | 0.0014327 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | -5% to 0% | Project 42 | 4.01 Sol'n Architecture Design (SAD) ProgArchV1.4 | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-04-04 17:00 | 2025-02-26 17:00 | -27 | -0.038682 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | -10% to -5% | Project 42 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-04-14 17:00 | 2025-02-21 17:00 | -36 | -0.051576 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | -10% to -5% | Project 42 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-04-30 17:00 | 2025-02-14 17:00 | -50 | -0.071633 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | -10% to -5% | Project 42 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-05-05 17:00 | 2025-01-31 17:00 | -63 | -0.090258 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | -10% to -5% | Project 42 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-05-06 17:00 | 2025-02-27 17:00 | -45 | -0.06447 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 5 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-08-06 17:00 | 2024-08-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-06-05 17:00 | 2024-06-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-02-25 17:00 | 2025-02-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-07-24 17:00 | 2024-07-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-02-25 17:00 | 2025-02-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-08-05 17:00 | 2024-08-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-02-25 17:00 | 2025-02-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 61 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-09 17:00 | 2024-10-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-10 17:00 | 2024-10-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-20 17:00 | 2024-09-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | -5% to 0% | Project 61 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2025-04-17 17:00 | 2025-04-01 17:00 | -12 | -0.029484 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 23 | 3.12 Program Architecture Guide Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 62 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001347 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 16
Assumed Completed | 0% | Project 62 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001347 |  | Delay reason known here | 2024-09-09 17:00 | 2024-09-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 16
Assumed Completed | 0% | Project 62 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001347 |  | Delay reason known here | 2024-09-23 17:00 | 2024-09-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 16
Assumed Completed | 0% | Project 62 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001347 |  | Delay reason known here | 2024-09-23 17:00 | 2024-09-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 16
Assumed Completed | 0% | Project 62 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1001347 |  | Delay reason known here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 16
Assumed Completed | 0% | Project 19 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-12-15 17:00 | 2023-12-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-08-31 17:00 | 2023-08-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-08-31 17:00 | 2023-08-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-08-31 17:00 | 2023-08-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-08-31 17:00 | 2023-08-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-08-31 17:00 | 2023-08-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | -10% to -5% | Project 3 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-12-06 17:00 | 2024-06-28 17:00 | -114 | -0.092834 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2025 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | -10% to -5% | Project 3 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-12-06 17:00 | 2024-06-28 17:00 | -114 | -0.092834 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2025 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | -25% to -10% | Project 3 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-01-31 17:00 | 2024-06-28 17:00 | -143 | -0.11645 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2025 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | -25% to -10% | Project 3 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-01-31 17:00 | 2024-06-28 17:00 | -143 | -0.11645 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2025 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | -25% to -10% | Project 3 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-01-31 17:00 | 2024-06-28 17:00 | -143 | -0.11645 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2025 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 10% to 25% | Project 3 | 7.02 PIR Sign Off (done for Phase 2 Only) | Deliverable | Gate 3 Approval | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-08-30 17:00 | 2025-06-20 17:00 | 194 | 0.15798 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 77 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001364 |  | Delay reason known here | 2024-09-24 17:00 | 2024-09-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 77 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001364 |  | Delay reason known here | 2024-09-24 17:00 | 2024-09-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 77 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001364 |  | Delay reason known here | 2024-09-24 17:00 | 2024-09-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 77 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001364 |  | Delay reason known here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 77 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1001364 |  | Delay reason known here | 2024-09-24 17:00 | 2024-09-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | -5% to 0% | Project 77 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001364 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 08:00 | -1 | -0.0032051 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | -25% to -10% | Project 77 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-04-17 17:00 | 2025-01-31 08:00 | -55 | -0.17628 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | -25% to -10% | Project 77 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-03-31 17:00 | 2025-02-14 08:00 | -32 | -0.10256 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 93 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-05-10 17:00 | 2024-05-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-08-05 17:00 | 2024-08-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-08-07 17:00 | 2024-08-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-08-09 17:00 | 2024-08-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 76 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 76 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 76 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 76 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 76 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 76 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 59 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-04-24 17:00 | 2024-04-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-04-26 17:00 | 2024-04-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-04-29 17:00 | 2024-04-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-04-30 17:00 | 2024-04-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-05-24 17:00 | 2024-05-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-12 17:00 | 2024-08-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | -25% to -10% | Project 59 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-03-28 17:00 | 2024-12-20 17:00 | -59 | -0.13382 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 68 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-10-14 17:00 | 2024-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-10-21 17:00 | 2024-10-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-11-11 17:00 | 2024-11-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-11-20 17:00 | 2024-11-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-01-09 17:00 | 2025-01-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-11-19 17:00 | 2024-11-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-11-06 17:00 | 2024-11-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-11-19 17:00 | 2024-11-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-11-19 17:00 | 2024-11-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-05-10 17:00 | 2024-05-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-10-09 17:00 | 2024-10-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-11-06 17:00 | 2024-11-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-12-04 17:00 | 2024-12-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-01-28 17:00 | 2025-01-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-18 17:00 | 2025-02-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-11-19 17:00 | 2024-11-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-19 17:00 | 2025-02-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | -25% to -10% | Project 66 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-03-28 17:00 | 2024-12-20 17:00 | -59 | -0.18266 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | -5% to 0% | Project 66 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-04-17 17:00 | 2025-04-04 17:00 | -9 | -0.027864 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-03 17:00 | 2025-02-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-12-04 17:00 | 2024-12-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% to 5% | Project 66 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-04-24 17:00 | 2025-04-30 17:00 | 3 | 0.0092879 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | -5% to 0% | Project 75 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-27 17:00 | -1 | -0.0037313 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% to 5% | Project 75 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-02-21 17:00 | 2025-02-28 17:00 | 5 | 0.018657 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 5% to 10% | Project 75 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-12-20 17:00 | 2025-01-31 17:00 | 19 | 0.070896 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 75 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-01-24 17:00 | 2025-01-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | -5% to 0% | Project 75 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-03-14 17:00 | 2025-02-27 17:00 | -11 | -0.041045 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | -10% to -5% | Project 75 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-03-07 17:00 | 2025-02-03 17:00 | -24 | -0.089552 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 5% to 10% | Project 75 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-12-20 17:00 | 2025-02-11 17:00 | 26 | 0.097015 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | -10% to -5% | Project 75 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-10 17:00 | -14 | -0.052239 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 10% to 25% | Project 75 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-02-21 17:00 | 2025-04-04 17:00 | 30 | 0.11194 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 71 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | 0% | Project 71 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | 0% | Project 71 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | 0% | Project 71 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | 0% | Project 71 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | -5% to 0% | Project 71 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-11-22 17:00 | 2024-11-04 17:00 | -14 | -0.041071 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | 0% | Project 71 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | -5% to 0% | Project 71 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-11-22 17:00 | 2024-11-08 17:00 | -10 | -0.029336 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | 0% | Project 71 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | -25% to -10% | Project 71 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-01-17 17:00 | 2024-11-12 17:00 | -38 | -0.11148 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | -25% to -10% | Project 71 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-01-17 17:00 | 2024-11-14 17:00 | -36 | -0.10561 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | -25% to -10% | Project 71 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-02-21 17:00 | 2024-11-13 17:00 | -61 | -0.17895 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | -25% to -10% | Project 71 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-01-13 17:00 | 2024-11-08 17:00 | -36 | -0.10561 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | <-25% | Project 71 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-04-24 17:00 | 2024-11-15 17:00 | -101 | -0.2963 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | 0% | Project 71 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | 0% | Project 64 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-09-06 17:00 | 2024-09-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-09-09 17:00 | 2024-09-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-09-10 17:00 | 2024-09-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-09-11 17:00 | 2024-09-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-09-12 17:00 | 2024-09-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-10-09 17:00 | 2024-10-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-01 17:00 | 2024-11-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-10-09 17:00 | 2024-10-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-12-04 17:00 | 2024-12-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2025-03-28 17:00 | 2025-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | -5% to 0% | Project 64 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2025-04-09 17:00 | 2025-04-01 17:00 | -6 | -0.038961 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 4.00 Infra' Sol'n Design Sign Off - LLID DEV+SIT | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-01 17:00 | 2024-11-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-11 17:00 | 2024-11-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-04 17:00 | 2024-11-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-01 17:00 | 2024-11-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-15 17:00 | 2024-11-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-12-04 17:00 | 2024-12-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-12-06 17:00 | 2024-12-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-12-06 17:00 | 2024-12-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2025-01-15 17:00 | 2025-01-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | GO LIVE | Deliverable | Go-Live | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 64 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-28 17:00 | 2024-10-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-16 17:00 | 2024-10-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-11-22 17:00 | 2024-11-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-28 17:00 | 2024-10-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-28 17:00 | 2024-10-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-09 17:00 | 2024-09-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | EVALUATE END (DOCUMENTUM) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2025-02-11 17:00 | 2025-02-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | GO LIVE Oracle Solaris: MY TIME & PAY | Deliverable | Go-Live | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 85 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-09-24 17:00 | 2024-09-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-09-26 17:00 | 2024-09-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-14 17:00 | 2024-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-11-06 17:00 | 2024-11-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-14 17:00 | 2024-10-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-11-06 17:00 | 2024-11-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 85 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 61 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2025-03-31 17:00 | 2025-03-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 61 | BUILD & TEST PHASE COMPLETE (TPS) | Governance | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 65 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-08-05 17:00 | 2024-08-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-08-05 17:00 | 2024-08-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-12-19 17:00 | 2024-12-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-10 17:00 | 2024-09-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-05 17:00 | 2024-09-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-12 17:00 | 2024-09-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-10-08 17:00 | 2024-10-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-12 17:00 | 2024-09-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-12-19 17:00 | 2024-12-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | -25% to -10% | Project 65 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-04-14 17:00 | 2025-02-28 17:00 | -31 | -0.14027 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | -5% to 0% | Project 65 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-04-17 17:00 | 2025-04-04 17:00 | -9 | -0.040724 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-08-28 17:00 | 2024-08-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 65 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-12 17:00 | 2024-09-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 16 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-09-01 17:00 | 2021-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-09-01 17:00 | 2021-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-09-01 17:00 | 2021-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-09-01 17:00 | 2021-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-09-01 17:00 | 2021-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | -5% to 0% | Project 16 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-01-15 17:00 | 2024-11-29 17:00 | -23 | -0.010713 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | -5% to 0% | Project 16 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-02-21 17:00 | 2024-11-29 17:00 | -49 | -0.022823 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | -5% to 0% | Project 16 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-02-24 17:00 | 2024-11-29 17:00 | -50 | -0.023288 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 23 | OT-IT Phase 2 Drop 1 Go Live | Deliverable | Go-Live | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | -5% to 0% | Project 23 | OT-IT Phase 2 Drop 3 Go Live | Deliverable | Go-Live | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2025-04-28 17:00 | 2025-04-14 17:00 | -7 | -0.011905 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | OT-IT Phase 2 Drop 2 Go Live | Deliverable | Go-Live | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-11-01 17:00 | 2024-11-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | PCR-02: Extend project to end Mar'25 | Governance | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 5% to 10% | Project 5 | 4.02 Functional Specification Sign Off (R1.1) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-04-17 17:00 | 2026-01-13 17:00 | 176 | 0.066215 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2025 | Yes | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | -5% to 0% | Project 59 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-03-28 17:00 | 2025-02-28 17:00 | -20 | -0.045364 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | -10% to -5% | Project 59 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-04-11 17:00 | 2025-03-03 17:00 | -29 | -0.065778 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2025-03-03 17:00 | 2025-03-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-09-19 17:00 | 2024-09-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 59 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-09-19 17:00 | 2024-09-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | -25% to -10% | Project 93 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-03-03 17:00 | 2024-12-04 17:00 | -52 | -0.10277 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | -10% to -5% | Project 93 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-03-03 17:00 | 2024-12-12 17:00 | -46 | -0.090909 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-04-15 17:00 | 2025-04-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-04-17 17:00 | 2025-04-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-04-23 17:00 | 2025-04-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-04-28 17:00 | 2025-04-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-04-15 17:00 | 2025-04-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | N/A | Project 93 | 4.05 Sprint Plan (Repeat for each sprint) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-03-03 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | N/A | Project 93 | 4.06 Sprint Review (Repeat for each sprint) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-03-03 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | N/A | Project 93 | 4.07 Sprint Retrospective (Repeat for each sprint) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-03-03 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | N/A | Project 31 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | GO LIVE | Deliverable | Go-Live | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | N/A | Project 31 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Assumed Completed | 0% | Project 9 | IIMSS IMPLEMENTATION 3 (30 Sep'24) | Deliverable | Go-Live | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 63 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-03-26 17:00 | 2024-03-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-11-07 17:00 | 2024-11-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-10-15 17:00 | 2024-10-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-12-10 17:00 | 2024-12-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-11-13 17:00 | 2024-11-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-10-17 17:00 | 2024-10-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-10-28 17:00 | 2024-10-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-12-13 17:00 | 2024-12-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 5% to 10% | Project 63 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2025-01-17 17:00 | 2025-02-24 17:00 | 25 | 0.075301 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 63 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-11-18 17:00 | 2024-11-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 4 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2022-12-12 17:00 | 2022-12-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2023-03-21 17:00 | 2023-03-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2023-01-23 17:00 | 2023-01-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-25 17:00 | 2024-10-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | GO LIVE TMC Digital Rostering System (Ph 1) | Deliverable | Go-Live | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-11-04 17:00 | 2024-11-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 4 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Assumed Completed | 0% | Project 76 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-04-17 17:00 | 2025-04-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 76 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-04-28 17:00 | 2025-04-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 76 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-04-28 17:00 | 2025-04-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 76 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-04-28 17:00 | 2025-04-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 76 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-04-28 17:00 | 2025-04-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 76 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-04-28 17:00 | 2025-04-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 76 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 23 | PLM1060 System Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-05-21 17:00 | 2024-05-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | -5% to 0% | Project 23 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2025-04-30 17:00 | 2025-04-22 17:00 | -5 | -0.0085034 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% to 5% | Project 23 | 4.00 Technical Sol'n Design Sign Off - PLM1080 | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2025-04-30 17:00 | 2025-05-19 17:00 | 13 | 0.022109 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 64 | PCR-01: Scope & Timeline Change SUBMITTED | Governance | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 19 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 5.01 Test Cases Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% to 5% | Project 19 | 5.06 Release Requested (Opt) | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-03-07 17:00 | 2025-03-31 17:00 | 16 | 0.0098826 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% to 5% | Project 19 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-03-17 17:00 | 2025-03-31 17:00 | 10 | 0.0061767 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 5.01 Test Cases Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-04-07 17:00 | 2025-04-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 5.06 Release Requested (Opt) | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 29 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 29 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-03-17 17:00 | 2025-03-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 29 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2025-03-17 17:00 | 2025-03-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | N/A | Project 110 | Integrations (EiPaaS or TIBCO) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | Java 6 to Java 17 Migration | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | WebSphere to Tomcat | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | Spring to Springboot Conversion | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | OUD to Smart ID Connect | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | Oracle 11g to Oracle 19C | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | Solaris to RHEL | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | JAVA 6 to 17 Upgrade | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-01-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | IBM Websphere to Springboot Framework Migration | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-01-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | Pilot Build Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2024-11-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | Pilot Solution Architecture Design Sign Off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2024-11-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | OUD Replacement with Entra ID Solution | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-01-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | Automation Test Suite Assessment | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2024-12-16 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | Pilot Outcomes Review Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-02-27 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2024-11-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2024-07-05 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-02-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-02-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2024-09-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2024-09-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-03-11 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-02-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-02-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-02-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-02-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-02-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 19 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-09-16 17:00 | 2024-09-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 5.01 Test Cases Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-09-09 17:00 | 2024-09-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-02-24 17:00 | 2025-02-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 5.06 Release Requested - Primavera | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-11-04 17:00 | 2024-11-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 5.00 Service Continuity Runbook Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-02-24 17:00 | 2025-02-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Primavera BUILD & TEST PHASE COMPLETE | Governance | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-02-24 17:00 | 2025-02-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 6.02 Implementation Plan Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 6.00 Application Handover Checklist Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-03-03 17:00 | 2025-03-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Primavera GO LIVE | Deliverable | Go-Live | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-03-03 17:00 | 2025-03-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Primavera ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% to 5% | Project 75 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-11-15 17:00 | 2024-11-28 17:00 | 9 | 0.033582 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 75 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-11-28 17:00 | 2024-11-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 75 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 75 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 75 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | -10% to -5% | Project 75 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-02 17:00 | -14 | -0.052239 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% to 5% | Project 75 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-11-22 17:00 | 2024-11-28 17:00 | 4 | 0.014925 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 19 | BlockSheets ANALYSIS & DESIGN PHASE COMPLETE | Governance | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-12-02 17:00 | 2024-12-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 5.01 Test Cases Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-02-03 17:00 | 2025-02-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | BlockSheets BUILD & TEST PHASE COMPLETE | Governance | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | -5% to 0% | Project 19 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-04-11 17:00 | 2025-03-31 17:00 | -9 | -0.005559 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | -5% to 0% | Project 19 | 6.00 Application Handover Checklist Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-04-17 17:00 | 2025-03-31 17:00 | -13 | -0.0080296 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | SSTS ANALYSIS & DESIGN PHASE COMPLETE | Governance | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 5.01 Test Cases Sign Off | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-03-07 17:00 | 2025-03-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Final Decision: RAMSYS TRACKWARE CANCELLED | Governance | Unassigned | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-10-24 17:00 | 2024-10-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 74 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | 0% | Project 74 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | 0% | Project 74 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | 0% | Project 74 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | 0% | Project 74 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2024-10-30 17:00 | 2024-10-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | 0% | Project 7 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000298 |  | Delay reason known here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% to 5% | Project 7 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000298 |  | Delay reason known here | 2025-02-27 17:00 | 2025-03-03 17:00 | 2 | 0.002635 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 7 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000298 |  | Delay reason known here | 2024-03-26 17:00 | 2024-03-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 7 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000298 |  | Delay reason known here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 7 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000298 |  | Delay reason known here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 7 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000298 |  | Delay reason known here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 7 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1000298 |  | Delay reason known here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 62 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-01-21 17:00 | 2025-01-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 16
Assumed Completed | 0% | Project 74 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2024-11-07 17:00 | 2024-11-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | 0% | Project 74 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-04-04 17:00 | 2025-04-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | 0% | Project 74 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-04-04 17:00 | 2025-04-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | 0% | Project 74 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | -5% to 0% | Project 74 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-04-29 17:00 | 2025-04-17 17:00 | -5 | -0.020325 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | 0% to 5% | Project 74 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-04-29 17:00 | 2025-04-30 17:00 | 1 | 0.004065 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | 0% | Project 74 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-02-03 17:00 | 2025-02-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | 0% | Project 74 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-01-29 17:00 | 2025-01-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Assumed Completed | N/A | Project 111 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1001618 |  | Delay reason known here | 2024-11-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Assumed Completed | 0% | Project 64 | 4.00 LLID for Pre Production & Prod Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001350 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | N/A | Project 119 | Kick Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1001774 |  | Delay reason known here | 2024-11-01 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 63 | 3.21 Final Business Case Sign Off 3/12 | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001349 |  | Delay reason known here | 2024-12-03 17:00 | 2024-12-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Assumed Completed | 0% | Project 7 | EOI Submission Complete | Unassigned | Yes | Assumed Completed | 6. Implement | 1000298 |  | Delay reason known here | 2024-05-07 17:00 | 2024-05-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 13 | Pilot SIT Completed | Deliverable | Yes | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-11-28 17:00 | 2023-11-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 24 | Concept Phase Complete | Unassigned | Yes | Assumed Completed | 2. Concept | 1000315 |  | Delay reason known here | 2023-10-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 35
Assumed Completed | 0% | Project 19 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-01 17:00 | 2023-11-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 13 | 3.21 Strategic Business Case (SBC) Approved (FIAC) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-03-08 08:00 | 2024-03-08 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 11 | TMS R4 UAT environment setup- Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-07-26 17:00 | 2024-10-01 17:00 | 47 | 0.027437 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 13 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-09-01 17:00 | 2023-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 19 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-12-15 17:00 | 2023-12-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-12-15 17:00 | 2023-12-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 3 | Business Justification signed off | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2022-07-28 | 2022-07-28 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 3 | Concept Phase Complete | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2022-02-07 | 2022-02-07 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 3 | Evaluate Phase complete | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2022-08-18 | 2022-08-18 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 10 | Build Phase Complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-04-20 | 2023-04-20 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 16 | 3.06 Business Requirements Document Sign Off | Unassigned | Unassigned | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-09-23 17:00 | 2021-09-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 3 | SAD signed off | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2022-09-15 | 2022-09-15 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 14 | Investment Brief (IB)/SoW Sign Off (Phase 1) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2023-05-04 | 2023-05-04 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 16 | 3.14 Project Management Plan Sign Off | Unassigned | Unassigned | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-09-23 17:00 | 2021-09-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% to 5% | Project 16 | 3.21 Strategic/Final Business Case Approved (FIAC) | Unassigned | Unassigned | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-06-14 17:00 | 2021-09-23 17:00 | 73 | 0.034001 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2021 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 16 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 14 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2023-05-04 | 2023-05-04 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 3 | Build and Test SGR Completed | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2022-12-02 | 2022-12-02 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 3 | Test strategy and plan signed off | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2022-10-05 | 2022-10-05 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 3 | Test Summary Report | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2022-12-02 | 2022-12-02 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 9 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-08 17:00 | 2024-04-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 13 | Pilot PSAD signed off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-10-05 08:00 | 2023-10-05 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | <-25% | Project 20 | UAT Execution and completion | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-09-13 17:00 | 2024-01-29 17:00 | -160 | -0.36613 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2025 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | 0% | Project 19 | Oracle Apex - GSU Migration Discovery Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-12-04 17:00 | 2023-12-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | -5% to 0% | Project 20 | Investment Brief (IB) or SoW Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-09-28 17:00 | 2023-09-01 17:00 | -19 | -0.043478 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | 0% to 5% | Project 13 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-11-15 17:00 | 2024-11-29 17:00 | 10 | 0.018051 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | -5% to 0% | Project 20 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-09-29 17:00 | 2023-09-08 17:00 | -15 | -0.034325 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | 0% | Project 19 | Oracle Apex - GSU Migration Analysis Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | -25% to -10% | Project 20 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-11-10 17:00 | 2023-09-08 17:00 | -44 | -0.10069 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | 0% | Project 19 | Ph1 - GovDC Migration Establishment | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Ph1 - GovDC uplift Migration Discovery Complet | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-02-28 17:00 | 2024-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Ph1 - Migration Analysis Complete | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-04-02 17:00 | 2024-04-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Oracle Apex - GSU Migration Implementation and go- | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-04-22 17:00 | 2024-04-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 14 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 7. Closure | 1000305 |  | Delay reason known here | 2023-05-04 | 2023-05-04 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | 0% | Project 19 | Oracle Apex - GSU Migration Establishment | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-23 17:00 | 2023-10-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 19 | Ph1 - GovDC uplift Migration Scratch and Desig | Governance | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-07-01 17:00 | 2024-07-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | -5% to 0% | Project 13 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-12-05 17:00 | 2024-12-05 08:00 | -1 | -0.0018051 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 3 | Develop Implementation plan | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2022-11-23 | 2022-11-23 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | <-25% | Project 20 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-09-13 17:00 | 2024-01-16 08:00 | -169 | -0.38673 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2025 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | <-25% | Project 20 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-09-25 17:00 | 2024-01-12 08:00 | -179 | -0.40961 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2025 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | 0% | Project 11 | 2.00 Investment Brief (IB) / SoW Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2019-10-21 | 2019-10-21 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2020 | 2020 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | -5% to 0% | Project 11 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-04-06 17:00 | 2023-04-06 | -1 | -0.00058377 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 3 | Pilot Phase Business Go-Live for Digital Roster an | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2022-12-12 | 2022-12-12 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | -5% to 0% | Project 11 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2019-10-21 17:00 | 2019-10-21 | -1 | -0.00058377 | #REF! | Duplicate | Sub-Portfolio 7 | 2020 | 2020 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2024-07-31 17:00 | 2024-07-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% to 5% | Project 20 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-11-07 17:00 | 2023-11-17 08:00 | 7 | 0.016018 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | 0% to 5% | Project 11 | TMS R4 SIT Test summary report- Complete | Deliverable | Yes | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-06-28 17:00 | 2024-08-27 17:00 | 42 | 0.024518 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2024 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | -25% to -10% | Project 3 | 7.03 Closure Memo Sign Off for Phase 2 | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2025-03-28 17:00 | 2024-01-31 08:00 | -287 | -0.23371 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2025 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 20 | P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-07-25 17:00 | 2023-07-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | 0% to 5% | Project 11 | TMS R4 SIT Test summary report- Commencement | Deliverable | Yes | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-06-28 17:00 | 2024-08-21 17:00 | 38 | 0.022183 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2024 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 3 | Implementation Pilot phase complete | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2023-01-13 | 2023-01-13 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 16 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-07-14 17:00 | 2023-07-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | <-25% | Project 20 | GO LIVE - Tactical Fix: SQL 2000 DB Upg to 2014 | Deliverable | Go-Live | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-10-22 17:00 | 2024-02-02 17:00 | -182 | -0.41648 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2025 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | 0% | Project 3 | Phase 2 (all Maritime) Business Go-Live for Digita | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2023-07-24 | 2023-07-24 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 19 | CMS Phase 1 Migration Establishment | Deliverable | Yes | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | -5% to 0% | Project 17 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2023-09-29 17:00 | 2023-09-29 08:00 | -1 | -0.0013717 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | -10% to -5% | Project 17 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2023-12-08 17:00 | 2023-09-22 08:00 | -55 | -0.075446 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 19 | Rail.hr Migration Implementation and go-live | Deliverable | Go-Live | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 20 | P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-08-25 17:00 | 2023-08-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Assumed Completed | 0% | Project 19 | Ramsys & Trackware Migrt. Scratch &Design Complete | Governance | Unassigned | Assumed Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-07-01 17:00 | 2024-07-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 6
Assumed Completed | 0% | Project 10 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2022-11-25 17:00 | 2022-11-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | -10% to -5% | Project 17 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2023-11-30 17:00 | 2023-09-28 17:00 | -44 | -0.060357 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% to 5% | Project 11 | Execute TMS R4 SIT test cases- Complete | Unassigned | Yes | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-06-24 17:00 | 2024-08-06 17:00 | 31 | 0.018097 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2024 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2022-02-23 17:00 | 2022-02-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 3 | Deliverable 1 Finished | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2021-11-08 | 2021-11-08 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 10 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-01-11 17:00 | 2023-01-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% to 5% | Project 11 | Execute TMS R4 SIT test cases- Commencement | Deliverable | Yes | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-05-31 17:00 | 2024-07-10 17:00 | 27 | 0.015762 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2024 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 16 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 17:00 | 2023-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Assumed Completed | 0% | Project 17 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2023-11-24 17:00 | 2023-11-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 17 | Project Health Check Complete 1/12 | Governance | Yes | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2023-12-01 17:00 | 2023-12-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 9 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-02-29 08:00 | 2024-02-29 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 3 | Raise shopping cart to create PO | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2022-05-30 | 2022-05-30 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 3 | Build Complete | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2022-10-17 | 2022-10-17 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 10 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-07 17:00 | 2023-02-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 10 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2022-08-18 17:00 | 2022-08-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | -5% to 0% | Project 11 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 | 2023-07-31 | -1 | -0.00058377 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 9 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-10-16 17:00 | 2023-10-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% to 5% | Project 11 | TMS R4 UAT Interface & Testing Support Commenced | Deliverable | Yes | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-06-28 17:00 | 2024-10-17 17:00 | 78 | 0.045534 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2024 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | -5% to 0% | Project 11 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-06-30 17:00 | 2023-06-30 | -1 | -0.00058377 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | -25% to -10% | Project 17 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2023-09-15 17:00 | 2023-04-05 | -114 | -0.15638 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 10 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | -5% to 0% | Project 11 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 | 2023-07-31 | -1 | -0.00058377 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 9 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-07-25 | 2023-07-25 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 2.00 Investment Brief (IB) / SoW Sign Off | Deliverable | Yes | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-09-21 17:00 | 2023-09-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-09-21 17:00 | 2023-09-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 72 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2024-03-26 17:00 | 2024-03-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 9 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-10-30 17:00 | 2023-10-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 72 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-01-20 17:00 | 2025-01-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 72 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-01-21 17:00 | 2025-01-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 72 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-01-22 17:00 | 2025-01-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 72 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-01-23 17:00 | 2025-01-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 73 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2024-03-26 17:00 | 2024-03-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 9 | 3.14 Project Management Plan | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-06-18 17:00 | 2024-06-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 73 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-01-20 17:00 | 2025-01-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 73 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-01-21 17:00 | 2025-01-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 73 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-01-22 17:00 | 2025-01-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 73 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-01-23 17:00 | 2025-01-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 9 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 4.01 Solution Arch Design (SAD) Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-09-07 17:00 | 2023-09-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | -5% to 0% | Project 9 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-11-08 17:00 | 2024-10-31 17:00 | -6 | -0.012455 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | N/A | Project 110 | System Architect Discovery & Analysis | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-02-27 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | Automation Test Suite Migration ¦ DMBS SGT | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-01-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | N/A | Project 110 | Pilot Regression Validation and Verification | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001617 |  | Delay reason known here | 2025-02-18 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 7 | Demonstrations Complete | Deliverable | Yes | Assumed Completed | 6. Implement | 1000298 |  | Delay reason known here | 2024-09-23 17:00 | 2024-09-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 9 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-02-16 17:00 | 2024-02-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | -5% to 0% | Project 13 | TECHNICAL DEPLOYMENT | Unassigned | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-12-06 17:00 | 2024-12-06 08:00 | -1 | -0.0018051 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 9 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-05-28 17:00 | 2024-05-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-05-28 17:00 | 2024-05-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 10 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 9 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-29 17:00 | 2024-04-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | -5% to 0% | Project 9 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-11-08 17:00 | 2024-10-25 17:00 | -10 | -0.020758 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 10 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 9 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-03-27 17:00 | 2023-03-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 9 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 13 | Pilot Test strategy signed off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-11-03 08:00 | 2023-11-03 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 9 | IIMSS GO LIVE 1 | Deliverable | Go-Live | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-06-03 17:00 | 2024-06-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 23 | EVALUATE PHASE COMPLETE (GATE 1) | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | MIL: Phase 1 Design & Analysis - complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-04-12 17:00 | 2024-04-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | MIL: Phase 1 Build - complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-05-30 17:00 | 2024-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | -10% to -5% | Project 13 | SIT Complete | Unassigned | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-10-15 17:00 | 2024-08-30 08:00 | -32 | -0.057762 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 23 | MIL: Phase 1 Implement - complete | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-06-14 17:00 | 2024-06-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 13 | Pilot UAT Complete | Deliverable | Yes | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-12-11 17:00 | 2023-12-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 23 | MIL: Phase 1 - complete | Deliverable | Go-Live | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-06-14 17:00 | 2024-06-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 23 | ANALYSIS & DESIGN PHASE 2 COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 13 | Pilot Build complete | Deliverable | Yes | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-11-10 17:00 | 2023-11-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | -5% to 0% | Project 23 | BUILD & TEST PHASE 2 COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2025-04-24 17:00 | 2025-03-31 17:00 | -16 | -0.027211 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | -5% to 0% | Project 23 | IMPLEMENT PHASE 2 COMPLETE | Governance | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2025-04-28 17:00 | 2025-04-15 17:00 | -6 | -0.010204 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 9 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-09-01 17:00 | 2023-09-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 10 | BUILD & TEST PHASE COMPLETE | Governance | Yes | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2024-08-16 17:00 | 2024-08-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 13 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-08-25 | 2023-08-25 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-09-13 17:00 | 2023-09-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 9 | 4.11 Security Risk Assessment (Opt) Sign Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-10-23 17:00 | 2023-10-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 13 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-09-14 17:00 | 2023-09-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | Pilot - Business Requirements Document Signed Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-11-09 08:00 | 2023-11-09 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 9 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-05-27 17:00 | 2024-05-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 13 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-11-17 17:00 | 2023-11-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | 3.21 Final Business Case (FBC) Approved (FIAC) | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-04-10 08:00 | 2024-04-10 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | Pilot Solution Architecture Design Signed Off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-12-05 17:00 | 2023-12-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | -5% to 0% | Project 9 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-11-08 17:00 | 2024-10-11 17:00 | -20 | -0.041515 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% to 5% | Project 13 | 6.05 Service Design & Definition Complete (Opt) | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-12-02 17:00 | 2024-12-05 08:00 | 2 | 0.0036101 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% to 5% | Project 13 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-11-01 17:00 | 2024-11-08 17:00 | 5 | 0.0090253 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | Pilot Test Summary Report signed off | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2023-12-14 17:00 | 2023-12-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | -10% to -5% | Project 17 | 3.11 Prelim Solution Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2023-11-30 17:00 | 2023-09-28 17:00 | -44 | -0.060357 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 9 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-08-01 | 2023-08-01 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 3 | Implementation SGR Completed | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2023-07-24 | 2023-07-24 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% to 5% | Project 13 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-11-13 17:00 | 2024-11-14 17:00 | 1 | 0.0018051 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | -5% to 0% | Project 13 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 08:00 | -1 | -0.0018051 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 93 | TrackAR AnyCloud Development & Test | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-01-10 17:00 | 2025-01-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | Safecomm AnyCloud Development & Test | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-07 17:00 | 2025-02-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | -5% to 0% | Project 93 | TrackAR AnyCloud Prod Deployment | Deliverable | Go-Live | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-28 17:00 | 2025-01-29 17:00 | -22 | -0.043478 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | -5% to 0% | Project 93 | Safecomm AnyCloud Prod Deployment | Deliverable | Go-Live | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-20 17:00 | -6 | -0.011858 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | -25% to -10% | Project 17 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2023-09-15 17:00 | 2023-04-05 | -114 | -0.15638 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | N/A | Project 24 | Obtain Sign off on Concept paper | Unassigned | Yes | Assumed Completed | 2. Concept | 1000315 |  | Delay reason known here | 2023-02-21 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2023 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 35
Assumed Completed | 0% to 5% | Project 11 | TMS R4 UAT environment setup- Commencement | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-05-31 17:00 | 2024-09-25 17:00 | 82 | 0.047869 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2024 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 13 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-06-07 17:00 | 2024-06-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | -5% to 0% | Project 13 | BUSINESS GO LIVE | Deliverable | Go-Live | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 08:00 | -1 | -0.0018051 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 13 | Project Health Check Completed 8 Mar'24 | Governance | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-03-08 08:00 | 2024-03-08 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 5% to 10% | Project 11 | Freight Timetable Data (TRIMS) interfaces unit tes | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-12-08 17:00 | 2024-05-09 17:00 | 95 | 0.055458 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | -5% to 0% | Project 11 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-02-20 17:00 | 2023-02-20 | -1 | -0.00058377 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 7 | Approval for RFP | Deliverable | Yes | Assumed Completed | 6. Implement | 1000298 |  | Delay reason known here | 2024-10-10 17:00 | 2024-10-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 72 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-04-11 17:00 | 2025-04-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 72 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-04-03 17:00 | 2025-04-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 72 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-04-16 17:00 | 2025-04-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 72 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-05-01 17:00 | 2025-05-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 72 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-03-11 17:00 | 2025-03-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 3 | Business Requirements signed off | Unassigned | Yes | Assumed Completed | 3. Evaluate | 1000294 |  | Delay reason known here | 2022-07-15 | 2022-07-15 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 4
Assumed Completed | 0% | Project 72 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001359 |  | Delay reason known here | 2025-03-17 17:00 | 2025-03-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | -5% to 0% | Project 13 | UAT Complete | Unassigned | Unassigned | Assumed Completed | 7. Closure | 1000304 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-21 08:00 | -7 | -0.012635 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 22
Assumed Completed | 0% | Project 73 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-17 17:00 | 2025-04-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% to 5% | Project 73 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-01 17:00 | 2025-04-15 17:00 | 10 | 0.025189 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | -5% to 0% | Project 73 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-17 17:00 | 2025-04-15 17:00 | -2 | -0.0050378 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% to 5% | Project 73 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-17 17:00 | 2025-04-24 17:00 | 3 | 0.0075567 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% to 5% | Project 73 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-17 17:00 | 2025-04-24 17:00 | 3 | 0.0075567 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% to 5% | Project 73 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-17 17:00 | 2025-04-24 17:00 | 3 | 0.0075567 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% to 5% | Project 73 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-17 17:00 | 2025-04-24 17:00 | 3 | 0.0075567 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% to 5% | Project 73 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-17 17:00 | 2025-04-24 17:00 | 3 | 0.0075567 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% to 5% | Project 73 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-01 17:00 | 2025-04-17 17:00 | 12 | 0.030227 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% to 5% | Project 73 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-01 17:00 | 2025-04-17 17:00 | 12 | 0.030227 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 61 | PCR-236824 Approved for EoT to Aug'25 | Governance | Unassigned | Assumed Completed | 6. Implement | 1001328 |  | Delay reason known here | 2025-02-20 17:00 | 2025-02-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Assumed Completed | N/A | Project 120 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1001775 |  | Delay reason known here | 2025-03-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | N/A | Project 120 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1001775 |  | Delay reason known here | 2025-03-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | N/A | Project 121 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1001776 |  | Delay reason known here | 2025-03-14 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | N/A | Project 121 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1001776 |  | Delay reason known here | 2025-03-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 122 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Assumed Completed | 2. Concept | 1001777 |  | Delay reason known here | 2025-03-31 17:00 | 2025-03-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Assumed Completed | 0% | Project 66 | PCR-01 | Governance | Unassigned | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-03 17:00 | 2025-02-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 5 | Cloud hosting decision paper endorse by GSIT PDA | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-03-28 17:00 | 2024-03-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Cloud design endorse by GSIT PDA | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-07-18 17:00 | 2024-07-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Network Design & AVD Deployment Solution | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-03-07 17:00 | 2025-03-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | TPS.Plan DEV01 environment handover to SIEMENS | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | TPS.Plan Sandpit environment handover to SIEMENS a | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-10-23 17:00 | 2024-10-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | TPS.Plan TEST environment handover to SIEMENS | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-01-09 17:00 | 2025-01-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | TPS.Plan DEV02 environment handover to SIEMENS | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-01-15 17:00 | 2025-01-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | TPS.Plan PREPROD environment readiness | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-04-11 17:00 | 2025-04-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Integration SAD sign-off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-03-17 17:00 | 2025-03-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Integration solution build | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Procurement service request and engagement | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-08-13 17:00 | 2024-08-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Procurement strategy sign-off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Procurement documents and RFP packing | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Release RFP for tender | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-10-21 17:00 | 2024-10-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Tender evaluation report and approval | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-03-11 17:00 | 2025-03-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | HCL Briefing & Engagement | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Draft Test Strategy | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 5 | Test Strategy review and sign-off | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-12-09 17:00 | 2024-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 23 | PCR-03: Extend project to end Jun'25 | Governance | Unassigned | Assumed Completed | 6. Implement | 1000314 |  | Delay reason known here | 2025-02-26 17:00 | 2025-02-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 33
Assumed Completed | 0% | Project 66 | Vendor Onboarding Complete | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 66 | Vendor Solution Design Submitted for Review | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-03-14 17:00 | 2025-03-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 93 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 93 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | N/A | Project 71 | PCR-01 | Governance | Unassigned | Assumed Completed | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-02-26 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 30
Assumed Completed | 0% | Project 68 | PCR-01 - inc. Scope, Resource Avail., Time & Cost | Governance | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-03-11 17:00 | 2025-03-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | Phase 1 Go Live | Deliverable | Go-Live | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | N/A | Project 5 | 4.01 Sol'n Architecture Design (SAD) Sign Off 1.1 | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2025-03-17 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Assumed Completed | 0% | Project 73 | Kick Off Sprint 1 | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-03-26 17:00 | 2025-03-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 73 | End of Sprint 1 | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-08 17:00 | 2025-04-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 73 | End of Sprint 2 | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-22 17:00 | 2025-04-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | N/A | Project 65 | SQUIZ - CI PORTAL GO LIVE | Deliverable | Go-Live | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-04-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | 0% | Project 68 | Kick Off Sprint 1 | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-03-04 17:00 | 2025-03-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | End of Sprint 1 | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-03-18 17:00 | 2025-03-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | End of Sprint 2 | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | End of Sprint 3 | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-04-15 17:00 | 2025-04-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | End of Sprint 4 | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-04-29 17:00 | 2025-04-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | N/A | Project 93 | Safecomm Legacy AWS Decommissioning | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-03-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | N/A | Project 93 | TrackAR Legacy AWS Decommissioning | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2025-03-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 13
Assumed Completed | 0% | Project 76 | Vendor SoW Sign Off by GSIT | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-03-27 17:00 | 2025-03-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Assumed Completed | 0% | Project 73 | Sprint Plan | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-08 17:00 | 2025-04-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 73 | Sprint Retrospective | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-08 17:00 | 2025-04-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 73 | Sprint Review | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-08 17:00 | 2025-04-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 73 | Sprint Plan | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-22 17:00 | 2025-04-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 73 | Sprint Review | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-22 17:00 | 2025-04-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 73 | Sprint Retrospective | Deliverable | Unassigned | Assumed Completed | 4. Analyse & Design | 1001360 |  | Delay reason known here | 2025-04-22 17:00 | 2025-04-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 21
Assumed Completed | 0% | Project 10 | PCR-03: Extend project to Oct'25 (Approved 26/3) | Governance | Unassigned | Assumed Completed | 6. Implement | 1000301 |  | Delay reason known here | 2025-03-26 17:00 | 2025-03-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Assumed Completed | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-03-18 17:00 | 2025-03-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-03-18 17:00 | 2025-03-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-03-18 17:00 | 2025-03-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-04-15 17:00 | 2025-04-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-04-15 17:00 | 2025-04-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-04-15 17:00 | 2025-04-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | Sprint Plan | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-04-29 17:00 | 2025-04-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | Sprint Review | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-04-29 17:00 | 2025-04-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | 0% | Project 68 | Sprint Retrospective | Deliverable | Unassigned | Assumed Completed | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-04-29 17:00 | 2025-04-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 12
Assumed Completed | N/A | Project 65 | CI PORTAL UAT COMPLETE | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-03-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | N/A | Project 65 | CI Portal Transitional Support to GSIT from Corp | Deliverable | Unassigned | Assumed Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-03-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Assumed Completed | -5% to 0% | Project 74 | PCR-0001 - Extension to Oct'25 | Governance | Project Kickoff | Assumed Completed | 3. Evaluate | 1001361 |  | Delay reason known here | 2025-04-02 17:00 | 2025-04-02 08:00 | -1 | -0.004065 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 28
Prepare for Closure | -25% to -10% | Project 13 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Prepare for Closure | 7. Closure | 1000304 |  | Delay reason known here | 2025-05-16 17:00 | 2025-02-14 17:00 | -62 | -0.11191 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 22
Prepare for Closure | -25% to -10% | Project 13 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Prepare for Closure | 7. Closure | 1000304 |  | Delay reason known here | 2025-05-16 17:00 | 2025-02-14 17:00 | -62 | -0.11191 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 22
Prepare for Closure | <-25% | Project 20 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Prepare for Closure | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2025-05-01 08:00 | 2024-02-05 17:00 | -303 | -0.69336 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 31
Prepare for Closure | <-25% | Project 20 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Prepare for Closure | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2025-05-01 08:00 | 2024-02-09 17:00 | -299 | -0.68421 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Project Manager 31
Prepare for Closure | -25% to -10% | Project 13 | 7.03 Closure Checklist & Memo Sign Off | Deliverable | Gate 3 Approval | Prepare for Closure | 7. Closure | 1000304 |  | Delay reason known here | 2025-05-16 17:00 | 2025-02-14 17:00 | -62 | -0.11191 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 22
Prepare for Closure | -25% to -10% | Project 13 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Prepare for Closure | 7. Closure | 1000304 |  | Delay reason known here | 2025-05-16 17:00 | 2025-02-14 17:00 | -62 | -0.11191 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Project Manager 22
Completed | 0% | Project 19 | CIS Applications(RTTA, PMG)Migration Establishment | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-12-19 08:00 | 2023-12-19 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | CIS Migrt. Scratch &Design Comple | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-04-02 08:00 | 2024-04-02 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | CIS Migration Analysis Complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-02-19 08:00 | 2024-02-19 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | CIS Migration Discovery Complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-01-31 08:00 | 2024-01-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Azure ASEv3 Platform (including Security)-complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-04-30 08:00 | 2024-04-30 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Integration with AnyCloud Accounts - complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-04-02 08:00 | 2024-04-02 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Security Alerts integrations - complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-02-19 08:00 | 2024-02-19 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Security Alerts integrations | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-08-01 08:00 | 2023-08-01 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Integration with AnyCloud Subscription - complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-04-02 08:00 | 2024-04-02 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Security Alerts integrations - complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-02-19 08:00 | 2024-02-19 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Establish Tagging Standard - complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Define/Identify Governance Reports - complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-02-19 08:00 | 2024-02-19 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | -10% to -5% | Project 1 | Production migration | Deliverable | Go-Live | Completed | 7. Closure | 1000292 |  | Delay reason known here | 2024-05-27 08:00 | 2024-04-24 17:00 | -21 | -0.053846 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | -5% to 0% | Project 1 | Data Analysis and Extraction | Unassigned | Yes | Completed | 7. Closure | 1000292 |  | Delay reason known here | 2024-04-26 08:00 | 2024-04-19 08:00 | -4 | -0.010256 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | -5% to 0% | Project 1 | Migration Scripts Development and build | Unassigned | Yes | Completed | 7. Closure | 1000292 |  | Delay reason known here | 2024-05-07 08:00 | 2024-04-18 08:00 | -12 | -0.030769 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | -5% to 0% | Project 1 | UAT Complete | Unassigned | Yes | Completed | 7. Closure | 1000292 |  | Delay reason known here | 2024-05-17 08:00 | 2024-04-26 08:00 | -15 | -0.038462 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 1 | P20 Cost Estimate Approved | Unassigned | Yes | Completed | 7. Closure | 1000292 |  | Delay reason known here | 2024-01-11 08:00 | 2024-01-11 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 1 | PSAD signed off | Unassigned | Yes | Completed | 7. Closure | 1000292 |  | Delay reason known here | 2024-01-31 08:00 | 2024-01-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | -5% to 0% | Project 1 | Vendor On Boarding Complete | Unassigned | Yes | Completed | 7. Closure | 1000292 |  | Delay reason known here | 2024-02-19 08:00 | 2024-01-29 08:00 | -15 | -0.038462 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | -5% to 0% | Project 1 | Solution Architecture Design Signed Off | Unassigned | Yes | Completed | 7. Closure | 1000292 |  | Delay reason known here | 2024-02-16 08:00 | 2024-01-29 08:00 | -14 | -0.035897 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | -10% to -5% | Project 1 | Access provisioning | Unassigned | Yes | Completed | 7. Closure | 1000292 |  | Delay reason known here | 2024-03-15 08:00 | 2024-01-25 08:00 | -35 | -0.089744 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | -5% to 0% | Project 1 | Analysis of security and Acces control mapping | Unassigned | Yes | Completed | 7. Closure | 1000292 |  | Delay reason known here | 2024-04-11 08:00 | 2024-04-02 08:00 | -7 | -0.017949 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 18 | Evaluate- PMP | Unassigned | Unassigned | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2024-03-22 08:00 | 2024-03-22 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 18 | Evaluate- BRD | Unassigned | Unassigned | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2024-03-19 17:00 | 2024-03-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 5 | Complete Tender Evaluation | Deliverable | Unassigned | Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2022-10-12 08:00 | 2022-10-12 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Completed | 0% | Project 5 | Release RFP | Deliverable | Unassigned | Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2022-05-02 08:00 | 2022-05-02 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Completed | 0% | Project 5 | Limited Trial Evaluation Report | Deliverable | Unassigned | Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2023-05-11 08:00 | 2023-05-11 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Completed | 0% | Project 5 | Finalise Funding Approval for Stage 1 - FIAC | Governance | Unassigned | Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2023-12-22 08:00 | 2023-12-22 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Completed | 0% | Project 5 | Present P20 IT Estimation to Stakeholders | Deliverable | Unassigned | Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2022-06-08 08:00 | 2022-06-08 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Completed | 0% | Project 5 | Conceptual Architecture Design | Deliverable | Unassigned | Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2023-09-14 08:00 | 2023-09-14 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Completed | 0% | Project 5 | Present Conceptual Architecture to TAC | Governance | Unassigned | Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2023-09-28 08:00 | 2023-09-28 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Completed | 0% | Project 5 | Present Conceptual Architecture to GSIT PDA | Governance | Unassigned | Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2023-11-02 08:00 | 2023-11-02 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Completed | 0% | Project 5 | Complete IT Delivery Org Design | Deliverable | Unassigned | Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2023-09-27 08:00 | 2023-09-27 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Completed | 0% | Project 5 | Present IT Delivery Org to Stakeholders | Governance | Unassigned | Completed | 3. Evaluate | 1000296 |  | Delay reason known here | 2023-10-10 08:00 | 2023-10-10 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 8
Completed | 0% | Project 2 | Raise Change Request | Unassigned | Unassigned | Completed | 6. Implement | 1000293 |  | Delay reason known here | 2023-12-18 08:00 | 2023-12-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 2 | Test Phase UAT | Unassigned | Unassigned | Completed | 6. Implement | 1000293 |  | Delay reason known here | 2024-01-16 17:00 | 2024-01-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 2 | Business Training | Unassigned | Unassigned | Completed | 6. Implement | 1000293 |  | Delay reason known here | 2024-01-29 08:00 | 2024-01-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 12 | Test completion report signed off | Unassigned | Yes | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-12-05 17:00 | 2023-12-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 12 | Implement- SGR Completed | Unassigned | Yes | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-12-05 17:00 | 2023-12-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 12 | Closure phase complete | Unassigned | Yes | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-12-15 17:00 | 2023-12-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 12 | Business Go-Live | Unassigned | Yes | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-12-05 17:00 | 2023-12-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 8 | Create project delivery milestone | Unassigned | Unassigned | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-02-09 08:00 | 2024-02-09 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | Analysis & Design, BRD, SAD completion | Deliverable | Unassigned | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | Solution Detailed design/SOW/Procurement | Deliverable | Unassigned | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | Development | Unassigned | Unassigned | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-05-03 08:00 | 2024-05-03 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | SIT | Unassigned | Unassigned | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-06-05 17:00 | 2024-06-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | UAT | Unassigned | Unassigned | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-06-19 17:00 | 2024-06-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | GO-LIVE | Deliverable | Go-Live | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-06-27 08:00 | 2024-06-27 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | Warranty and Acceptance | Unassigned | Unassigned | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-08-09 17:00 | 2024-08-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 45 | Analysis & Design, BRD signoff | Unassigned | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2023-12-12 08:00 | 2023-12-12 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | SOW (WIPRO), PO/Procurement completion | Unassigned | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-03-22 17:00 | 2024-03-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | GO LIVE Part 1 -6 Sep now 10 Sep to accom DCV Proj | Deliverable | Go-Live | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-09-24 17:00 | 2024-09-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 8 | Reporting requrements signoff | Unassigned | Unassigned | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-05-10 08:00 | 2024-05-10 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | Reporting Development Resource Assignment Complete | Unassigned | Unassigned | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-06-14 08:00 | 2024-06-14 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | eMFT server feed business engagement E STATE AUTOM | Unassigned | Unassigned | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-05-24 08:00 | 2024-05-24 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | N/A | Project 44 | Supplier Engagement Complete | Unassigned | Unassigned | Completed | Unassigned | 1001051 |  | Delay reason known here | 2024-04-05 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 1 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Completed | N/A | Project 44 | Build Complete | Unassigned | Unassigned | Completed | Unassigned | 1001051 |  | Delay reason known here | 2024-05-08 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 1 | 1900 | 2024 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 7
Completed | 0% | Project 85 | Contract issued and Executed | Unassigned | Unassigned | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-14 17:00 | 2024-08-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 18 | EOI Closure | Deliverable | Yes | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2024-05-07 08:00 | 2024-05-07 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 18 | Demonstrations Complete | Deliverable | Yes | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2024-08-09 17:00 | 2024-08-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 18 | Decision | Deliverable | Yes | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2024-09-16 17:00 | 2024-09-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 21 | UAT Sign Off | Deliverable | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2024-07-08 17:00 | 2024-07-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 21 | GO LIVE (Technical) | Deliverable | Go-Live | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 61 | 2.00 Investment Brief (IB) / SoW Sign Off | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-03-13 17:00 | 2024-03-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 10 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1000301 |  | Delay reason known here | 2024-11-15 08:00 | 2024-11-15 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 45 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2025-02-26 17:00 | 2025-02-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2025-02-26 17:00 | 2025-02-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-08-29 17:00 | 2024-08-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | HYB6.04 Release Retrospective Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-09-02 08:00 | 2024-09-02 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2025-02-19 17:00 | 2025-02-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 21 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 21 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 8 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-08-12 17:00 | 2024-08-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-08-14 17:00 | 2024-08-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 45 | GO LIVE Part 2 (WIPRO Reconciliation Work) | Deliverable | Go-Live | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 29 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 29 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Completed | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2024-10-18 17:00 | 2024-10-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 45 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-04-05 17:00 | 2024-04-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-04-05 17:00 | 2024-04-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-04-05 17:00 | 2024-04-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-04-05 17:00 | 2024-04-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-04-05 17:00 | 2024-04-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | -5% to 0% | Project 42 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Completed | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-04-04 17:00 | 2025-02-27 17:00 | -26 | -0.037249 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 48 | MIL: Analysis & Design phase - complete | Unassigned | Unassigned | Completed | 7. Closure | 1001239 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 3 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Completed | 0% | Project 48 | MIL: Seed funding released | Unassigned | Unassigned | Completed | 7. Closure | 1001239 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 3 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Completed | 0% | Project 48 | MIL: Concept phase - complete | Unassigned | Unassigned | Completed | 7. Closure | 1001239 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 3 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Completed | 0% | Project 48 | MIL: Evaluate phase - complete | Unassigned | Unassigned | Completed | 7. Closure | 1001239 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 3 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Completed | 0% | Project 48 | MIL: Build& Test phase - complete | Unassigned | Unassigned | Completed | 7. Closure | 1001239 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 3 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Completed | 0% | Project 48 | MIL: Go Live | Unassigned | Unassigned | Completed | 7. Closure | 1001239 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 3 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Completed | 0% | Project 48 | MIL: Implement phase - complete | Unassigned | Unassigned | Completed | 7. Closure | 1001239 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 3 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Completed | 0% | Project 48 | MIL: Procurement contract awarded | Unassigned | Unassigned | Completed | 7. Closure | 1001239 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 3 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Completed | 0% | Project 48 | MIL: Project closed | Unassigned | Unassigned | Completed | 7. Closure | 1001239 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 3 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Completed | 0% | Project 61 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 3.05 Business Impact Assessment Sign Off MTAP | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 3.06 Business Requirements Document Sign Off MTAP | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-08-09 17:00 | 2024-08-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | EVALUATE END (MY TIME & PAY) | Governance | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-06 17:00 | 2024-09-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 93 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-10-23 17:00 | 2024-10-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 13
Completed | 0% | Project 76 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2024-03-26 17:00 | 2024-03-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 59 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-10-11 17:00 | 2024-10-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 45 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-01 17:00 | 2024-05-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 61 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2025-01-10 17:00 | 2025-01-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-06 17:00 | 2024-09-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-06 17:00 | 2024-09-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 85 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-09-16 17:00 | 2024-09-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | N/A | Project 85 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 85 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-11-18 17:00 | 2024-11-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | N/A | Project 85 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 85 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 85 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 85 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 85 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-11-20 17:00 | 2024-11-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 85 | BUSINESS GO LIVE | Deliverable | Go-Live | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-11-22 17:00 | 2024-11-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 85 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2024-12-19 17:00 | 2024-12-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 85 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2025-01-31 08:00 | 2025-01-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 85 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 85 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 85 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Completed | 7. Closure | 1001399 |  | Delay reason known here | 2025-01-31 17:00 | 2025-01-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 14
Completed | 0% | Project 61 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-17 17:00 | 2024-10-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | EVALUATE END (MY TIME & PAY) | Governance | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-17 17:00 | 2024-10-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-10-17 17:00 | 2024-10-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-25 17:00 | 2024-09-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-26 17:00 | 2024-09-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 61 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-26 17:00 | 2024-09-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 65 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | N/A | Project 65 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | -10% to -5% | Project 65 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-03-19 17:00 | 2025-02-28 17:00 | -13 | -0.058824 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-11-25 17:00 | 2024-11-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-10-22 17:00 | 2024-10-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | N/A | Project 65 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 65 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-12 17:00 | 2024-09-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | -10% to -5% | Project 65 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-03-21 17:00 | 2025-02-28 17:00 | -15 | -0.067873 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | -5% to 0% | Project 65 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1001351 |  | Delay reason known here | 2025-03-03 17:00 | 2025-02-28 17:00 | -1 | -0.0045249 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 29
Completed | 0% | Project 45 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-04-05 17:00 | 2024-04-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-06-28 17:00 | 2024-06-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-05-31 17:00 | 2024-05-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-06-03 17:00 | 2024-06-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-06-11 17:00 | 2024-06-11 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-09-03 17:00 | 2024-09-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-06-28 08:00 | 2024-06-28 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-09-04 17:00 | 2024-09-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-09-03 17:00 | 2024-09-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-06-03 17:00 | 2024-06-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-09-18 17:00 | 2024-09-18 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 45 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Completed | 7. Closure | 1001122 |  | Delay reason known here | 2024-09-10 17:00 | 2024-09-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 4 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2023-01-23 17:00 | 2023-01-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-28 17:00 | 2024-10-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-09-27 17:00 | 2024-09-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-09-09 17:00 | 2024-09-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-09-19 17:00 | 2024-09-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-31 08:00 | 2024-10-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-10-03 17:00 | 2024-10-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | 6.01 Training Docs & App H'over Checklist Complete | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 4 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | N/A | Project 4 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 61 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off MTAP | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here | 2024-08-06 17:00 | 2024-08-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 25
Completed | N/A | Project 61 | 3.20 Test Strategy Sign Off MTAP | Deliverable | Project Kickoff | Completed | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 25
Completed | 0% | Project 76 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-01-22 17:00 | 2025-01-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 76 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Completed | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-01-24 17:00 | 2025-01-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 75 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 75 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 75 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 75 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 75 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-07-29 17:00 | 2024-07-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Completed | 5% to 10% | Project 75 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-11-07 17:00 | 2024-11-28 17:00 | 15 | 0.05597 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 75 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-11-22 17:00 | 2024-11-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Completed | -25% to -10% | Project 75 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-03-14 17:00 | 2024-11-29 17:00 | -64 | -0.23881 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 75 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-11-14 17:00 | 2024-11-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 75 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-11-21 17:00 | 2024-11-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 18
Completed | N/A | Project 111 | Project Team Kick Off | Deliverable | Unassigned | Completed | 6. Implement | 1001618 |  | Delay reason known here | 2024-09-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | N/A | Project 111 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Completed | 6. Implement | 1001618 |  | Delay reason known here | 2024-11-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | N/A | Project 111 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Completed | 6. Implement | 1001618 |  | Delay reason known here | 2024-11-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | N/A | Project 111 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Completed | 6. Implement | 1001618 |  | Delay reason known here | 2024-11-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | N/A | Project 111 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Completed | 6. Implement | 1001618 |  | Delay reason known here | 2024-11-06 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | N/A | Project 111 | SIT Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001618 |  | Delay reason known here | 2025-04-16 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | N/A | Project 111 | Code Migration / Setup Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001618 |  | Delay reason known here | 2025-04-11 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | N/A | Project 111 | Build VIM Instances existing Azure Infra Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001618 |  | Delay reason known here | 2025-02-14 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | N/A | Project 111 | Vendor PO Release & Onboarding Complete | Deliverable | Unassigned | Completed | 6. Implement | 1001618 |  | Delay reason known here | 2024-11-15 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 21 | Briefing Note | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2022-07-01 | 2022-07-01 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 21 | PACT | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2022-07-01 | 2022-07-01 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 18 | Concept SGR Completed | Unassigned | Unassigned | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2022-11-30 | 2022-11-30 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 21 | Concept SGR Completed | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2022-07-01 | 2022-07-01 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 19 | Program Schedule | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 08:00 | 2023-11-30 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 18 | PACT | Unassigned | Unassigned | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2022-09-26 | 2022-09-26 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 12 | SAD signed off | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2022-12-09 17:00 | 2022-12-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 25 | Test strategy and plan signed off | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2023-04-20 | 2023-04-20 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 18 | Investment Brief | Unassigned | Unassigned | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2022-11-30 | 2022-11-30 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 19 | Business Case Issued for Approval | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-15 08:00 | 2023-11-15 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | N/A | Project 8 | PMP signed off | Unassigned | Yes | Completed | 6. Implement | 1000299 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | Yes | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 25 | Analyse and Design Phase complete | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2023-06-05 | 2023-06-05 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 19 | WBS Set up | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-08-31 08:00 | 2023-08-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 12 | Test strategy and plan signed off | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-10-13 17:00 | 2023-10-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 11 | Present DTIP HL report to Customer Ops and DSP | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2020-10-20 | 2020-10-20 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2021 | 2021 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 18 | Test completion report signed off | Unassigned | Yes | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2024-04-09 17:00 | 2024-04-09 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 16 | Endorsement to proceed with contract - TCOPS Steer | Unassigned | Unassigned | Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-02-13 | 2023-02-13 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Completed | 0% | Project 11 | TMS R3 TEST (SIT) environment setup - Commencement | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-03 | 2023-07-03 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 16 | FIP - Approval to award contract | Unassigned | Unassigned | Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-02-27 | 2023-02-27 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Completed | 0% | Project 12 | Service design signed off | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-07-21 | 2023-07-21 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 11 | CTM interfaces (Passenger TT) - R3 - Release data | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2021-02-08 | 2021-02-08 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2021 | 2021 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 12 | Analyse and Design Phase complete | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-10-13 17:00 | 2023-10-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 11 | Execute TMS R3 SIT test cases- commencement | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-03 | 2023-07-03 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 4 | PMP signed off | Unassigned | Unassigned | Completed | 6. Implement | 1000295 |  | Delay reason known here | 2023-02-15 | 2023-02-15 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 15
Completed | 0% | Project 2 | Obtain Sign off on Concept paper | Unassigned | Unassigned | Completed | 6. Implement | 1000293 |  | Delay reason known here | 2022-09-01 | 2022-09-01 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 18 | Business Requirements Document | Unassigned | Unassigned | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2022-12-23 | 2022-12-23 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 19 | Azure ASEv3 Platform (including Security) - start | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 10 | UAT Complete | Unassigned | Yes | Completed | 6. Implement | 1000301 |  | Delay reason known here | 2024-02-29 17:00 | 2024-02-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 18 | Project Management Plan | Unassigned | Unassigned | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2023-01-27 | 2023-01-27 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 21 | P1S2.1 Asset Association Design & Analysis Complet | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2023-03-16 | 2023-03-16 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 18 |  | Unassigned | Yes | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2024-03-20 08:00 | 2024-03-20 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 19 | Integration with AnyCloud Accounts Data Streams | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-07-17 08:00 | 2023-07-17 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 11 | TMS R3 UAT interface testing & support- Commenceme | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-08-09 | 2023-08-09 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 19 | Security Alerts integrations | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-07-17 08:00 | 2023-07-17 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 25 | Go Live complete | Unassigned | Go-Live | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2024-04-02 08:00 | 2024-04-02 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 11 | Test Plan | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-06-20 | 2023-06-20 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 16 | Negotiation Strategy Completed and Approved | Unassigned | Unassigned | Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2022-12-05 | 2022-12-05 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Completed | 0% | Project 19 | Applications ITSI Dashboards (FY24 Progress. task) | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-20 17:00 | 2023-10-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 2 | Business Requirements signed off | Unassigned | Yes | Completed | 6. Implement | 1000293 |  | Delay reason known here | 2022-09-14 | 2022-09-14 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 11 | SAD | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-02-20 | 2023-02-20 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 16 | Awareness to Steer Co regarding decision to procee | Unassigned | Unassigned | Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2022-12-07 | 2022-12-07 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Completed | 0% | Project 19 | Integration with AnyCloud Subscription Data Stream | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-23 08:00 | 2023-10-23 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 18 |  | Unassigned | Yes | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2024-03-28 08:00 | 2024-03-28 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 12 | Build and Test phase complete | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-10-27 17:00 | 2023-10-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 19 | Applications ITSI Dashboards (FY24 Progress. task) | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-20 17:00 | 2023-10-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 11 | Gather estimation for PROD data access solution | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2022-09-08 | 2022-09-08 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 19 | Establish Tagging Standard | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-23 08:00 | 2023-10-23 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Define/Identify Governance Reports and Process | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-20 17:00 | 2023-10-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% to 5% | Project 11 | TMS R3 Go-live (TBC) | Unassigned | Yes | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-03-28 17:00 | 2024-05-20 17:00 | 34 | 0.019848 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 25 | Implementation phase complete | Unassigned | Yes | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2024-04-02 08:00 | 2024-04-02 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | -25% to -10% | Project 20 | SIT Complete | Unassigned | Yes | Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-05-24 08:00 | 2023-12-22 08:00 | -96 | -0.21968 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Completed | 0% | Project 19 | Implements across AWS & Azure Anycloud Accts/ Subs | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-20 17:00 | 2023-10-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 25 | Closure phase complete | Unassigned | Yes | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2024-04-15 08:00 | 2024-04-15 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | -25% to -10% | Project 20 | Build complete | Unassigned | Yes | Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-05-24 08:00 | 2023-12-22 08:00 | -96 | -0.21968 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Completed | 0% | Project 20 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Unassigned | Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-09-25 17:00 | 2023-09-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Completed | 0% | Project 2 | Production go-live | Deliverable | Go-Live | Completed | 6. Implement | 1000293 |  | Delay reason known here | 2024-02-02 17:00 | 2024-02-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 2 | Concept Phase Complete | Unassigned | Yes | Completed | 6. Implement | 1000293 |  | Delay reason known here | 2023-03-03 | 2023-03-03 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 20 | 3.04 PACT Sign Off | Deliverable | Unassigned | Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-09-08 17:00 | 2023-09-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Completed | 0% | Project 22 | Review and Update Critical Application Business Ow | Unassigned | Yes | Completed | 7. Closure | 1000313 |  | Delay reason known here | 2023-10-20 08:00 | 2023-10-20 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 1 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 32
Completed | 0% | Project 11 | TMS R4 TEST (SIT) environment setup - Complete | Unassigned | Yes | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-07-02 17:00 | 2024-07-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 20 | Solution Architecture Design Signed Off | Unassigned | Unassigned | Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-09-07 17:00 | 2023-09-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Completed | 0% | Project 2 | Development Phase | Unassigned | Yes | Completed | 6. Implement | 1000293 |  | Delay reason known here | 2023-12-15 17:00 | 2023-12-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 21 | P1S6.2 Read & Understood into UAT | Unassigned | Yes | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2024-02-29 08:00 | 2024-02-29 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 10 | TLA Technical Design Completed | Unassigned | Unassigned | Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-01-30 | 2023-01-30 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 8 | Investment Brief Sign-off | Deliverable | Project Kickoff | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2022-11-15 | 2022-11-15 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 20 | Analyse and Design SGR Completed | Unassigned | Unassigned | Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-09-15 17:00 | 2023-09-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Completed | 0% | Project 11 | TMS R3 Test summary report (SIT)- Complete | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-24 | 2023-07-24 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 21 | P1S3.3a Missing Crew | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2022-07-01 | 2022-07-01 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 19 | TCSS - Digital Mobility Migration Establishment | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 16 | Phase 0 - Value Committment for All - Acceptance | Unassigned | Yes | Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-11-27 08:00 | 2023-11-27 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Completed | 0% | Project 19 | TCSS Migration Analysis Complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-02-28 08:00 | 2024-02-28 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 16 | P1a - VC for R&S - MVP & Optimisation | Unassigned | Yes | Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2024-01-31 17:00 | 2024-01-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Completed | 0% | Project 9 | Technical deployment | Unassigned | Unassigned | Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-05-31 08:00 | 2024-05-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Completed | 0% | Project 11 | TMS R4 UAT environment setup- Completed | Unassigned | Yes | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-10-01 17:00 | 2024-10-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 11 | DTIP- R4 - Governance Forums and ADRB Endorsement | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2021-06-17 | 2021-06-17 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2021 | 2021 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 21 | Drop 5 Two Way TA (scope added) into UAT | Unassigned | Yes | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2024-02-29 08:00 | 2024-02-29 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 20 | Raise ICT Release Request | Unassigned | Unassigned | Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-07-19 17:00 | 2023-07-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Completed | 0% | Project 11 | TMS R4 TIBCO Interface contracts- Complete | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-08-28 | 2023-08-28 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 21 | Drop 1 One Way TA no interfaces | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2022-03-07 | 2022-03-07 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 2 | Deploy in SandPit | Unassigned | Unassigned | Completed | 6. Implement | 1000293 |  | Delay reason known here | 2023-12-20 17:00 | 2023-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 21 | Drop 2 One Way TA Standby Sync Increased | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2023-05-12 | 2023-05-12 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 19 | TCSS - Digital Mobility Migration Disc. Comple | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 21 | Drop 3 eSCDs Distribution List | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2022-03-07 | 2022-03-07 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 21 | MyRoster+ Application Changes | Deliverable | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2024-07-19 08:00 | 2024-07-19 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 21 | P1S3.3 Stopping Pattern Report MVP | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2022-07-01 | 2022-07-01 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 11 | TMS R4 - Solution build complete | Unassigned | Yes | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-06-25 17:00 | 2024-06-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 16 | Negotiation sessions Complete | Unassigned | Unassigned | Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-02-08 | 2023-02-08 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Completed | 0% | Project 21 | Drop 3 Task Assigner PBIs for IVR Swith Off | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2022-10-04 | 2022-10-04 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 20 | Security Risk Assesment Completed | Unassigned | Yes | Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-12-22 17:00 | 2023-12-22 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Completed | 0% | Project 21 | Drop 4 One Way TA Real-Time Updates | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2023-08-21 | 2023-08-21 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 25 | P80 estimate for delivery phase signed off | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2022-03-25 | 2022-03-25 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | -5% to 0% | Project 11 | TMS R4 UAT completed | Unassigned | Yes | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2025-05-30 17:00 | 2025-04-28 17:00 | -24 | -0.014011 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 25 | Closure Memo Completed | Unassigned | Gate 3 Approval | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2024-05-15 08:00 | 2024-05-15 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 19 | CMS Phase 1 Migration Discovery Complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | -5% to 0% | Project 11 | DTIP interfaces unit testing- Complete | Unassigned | Yes | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-05-31 17:00 | 2024-04-10 17:00 | -36 | -0.021016 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 12 | Investment Brief Signed off (if applicable) | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-06-05 | 2023-06-05 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 19 | CMS Phase 1 Migration Analysis Complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-31 08:00 | 2023-10-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 21 | P2S1.3 CoPAL Complete | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2022-12-12 | 2022-12-12 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 2 | VIM Proof of Concept phase complete | Unassigned | Yes | Completed | 6. Implement | 1000293 |  | Delay reason known here | 2023-06-16 | 2023-06-16 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 19 | CMS Phase 1 Migration Scratch & Design Complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-07 08:00 | 2023-11-07 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | CMS Phase 1 Migration Build and Test Complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-15 08:00 | 2023-11-15 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 21 | P2S1.3 MVP Clearance of Planned Annual Leave (COPA | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2021-10-05 | 2021-10-05 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 11 | TMS R3 UAT environment setup- Complete | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-08-14 | 2023-08-14 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 19 | CMS Phase 1 Migration Implementation and go-live | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 08:00 | 2023-11-30 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Rail.hr (GovDC) Migration Discovery Complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-23 08:00 | 2023-10-23 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 18 | Closure memo - Signed off | Unassigned | Yes | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2024-03-28 08:00 | 2024-03-28 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 25 | Contract signed off | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2022-12-22 | 2022-12-22 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 19 | Rail.hr Migration Analysis Complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-23 08:00 | 2023-10-23 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Rail.hr Migration Scratch and Design Complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-23 08:00 | 2023-10-23 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Rail.hr Migration Build and Test Complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 25 | Build Complete | Unassigned | Yes | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2023-10-31 17:00 | 2023-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 12 | PMP | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-06-26 | 2023-06-26 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 19 | Ramsys & Trackware Migration Discovery Complete | Unassigned | Unassigned | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-02-19 08:00 | 2024-02-19 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 12 | Maritime SOW signed off | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-06-05 | 2023-06-05 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 25 | RFx activities | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2022-08-08 | 2022-08-08 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 19 | Ramsys & Trackware Migration Analysis Complete | Unassigned | Unassigned | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-02-28 08:00 | 2024-02-28 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 11 | TMS R3 TEST (SIT) environment setup - Complete | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-13 | 2023-07-13 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 10 | Obtain Sign off on Concept paper | Unassigned | Unassigned | Completed | 6. Implement | 1000301 |  | Delay reason known here | 2022-08-18 | 2022-08-18 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 12 | UAT Complete | Unassigned | Yes | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-10-31 17:00 | 2023-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% to 5% | Project 11 | TMS R3 UAT interface testing & support- Complete | Unassigned | Yes | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-12-08 17:00 | 2024-02-14 17:00 | 37 | 0.0216 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 8 | Business Justification (Lean Business Case) Sign-o | Unassigned | Yes | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2023-10-13 17:00 | 2023-10-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 19 | Scoping and piroritisation - FY24 | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 08:00 | 2023-11-30 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 12 | Build complete | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-10-13 17:00 | 2023-10-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 11 | Present PROD data access solution to DSP | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2022-08-25 | 2022-08-25 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 19 | Integrum Archival and Decomm | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 08:00 | 2023-11-30 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | FPE-ST Archival Complete | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2024-05-27 17:00 | 2024-05-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 11 | DSP repurpose of funds to implement PROD data acce | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-06-13 | 2023-06-13 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 19 | LIU Legacy Decomm | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 08:00 | 2023-11-30 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Archiving & Decommission - Applications/DBs 4-6 | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-12-15 08:00 | 2023-12-15 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 10 | Network Connectivity- PROD environment connectivit | Unassigned | Yes | Completed | 6. Implement | 1000301 |  | Delay reason known here | 2024-02-29 17:00 | 2024-02-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 10 | Solutions Options Paper signed off | Unassigned | Unassigned | Completed | 6. Implement | 1000301 |  | Delay reason known here | 2022-07-07 | 2022-07-07 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 8 | Business Requirements Document signed off | Unassigned | Yes | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2023-02-28 | 2023-02-28 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2023-11-15 17:00 | 2023-11-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 19 | COM Options paper for PSG | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-12-15 08:00 | 2023-12-15 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | COM - Steerco and PSG recommendations | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-31 08:00 | 2023-10-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 10 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Completed | 6. Implement | 1000301 |  | Delay reason known here | 2024-10-31 17:00 | 2024-10-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 9 | SIT Complete | Unassigned | Yes | Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-03-28 08:00 | 2024-03-28 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Completed | 0% | Project 21 | Business Case | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2022-02-04 | 2022-02-04 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 21 | Drop 1 eSCDs MVP | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2021-11-01 | 2021-11-01 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 9 | UAT Complete | Unassigned | Unassigned | Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-05-22 08:00 | 2024-05-22 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Completed | 0% | Project 21 | Drop 2 eSCDs Offline Documents | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2022-02-08 | 2022-02-08 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 9 | IIMSS Build Complete | Unassigned | Unassigned | Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-02-16 17:00 | 2024-02-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Completed | 0% | Project 25 | PMP Approved | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2022-07-15 | 2022-07-15 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 9 | Vendor On Boarding Complete | Unassigned | Yes | Completed | 7. Closure | 1000300 |  | Delay reason known here | 2023-10-04 17:00 | 2023-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Completed | 0% | Project 11 | Present PROD data access solution estimation to DS | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-03-02 | 2023-03-02 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 20 | 3.11 Prelim Solution Arch Design (PSAD) Sign Off | Deliverable | Unassigned | Completed | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2023-08-18 | 2023-08-18 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 31
Completed | 0% | Project 21 | 7.03 Closure Checklist & Memo Sign Off | Deliverable | Gate 3 Approval | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2024-11-25 17:00 | 2024-11-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 12 | Finalise the SOW with VIPRO | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-04-21 | 2023-04-21 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 21 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2024-11-25 17:00 | 2024-11-25 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 25 | PSAD | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2022-07-15 | 2022-07-15 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 11 | TMS R3 Test summary report (SIT)- Commencement | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-11 | 2023-07-11 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 9 | ANALYSIS & DESIGN PHASE COMPLETE | Governance | Unassigned | Completed | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Completed | 0% | Project 11 | Digital Timetable Information Portal (DTIP) interf | Unassigned | Yes | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-03-26 17:00 | 2024-03-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 21 | P1S6.1 eSCDs Complete | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2022-08-15 | 2022-08-15 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 11 | TMS R4 Solution Architecture design approval- Comp | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-02-17 | 2023-02-17 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 16 | Execution of contract | Unassigned | Unassigned | Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 | 2023-03-13 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Completed | 0% | Project 16 | Procurement Strategy Revision (TfNSW) Sign-Off | Unassigned | Unassigned | Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2022-08-30 | 2022-08-30 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Completed | 0% | Project 21 | P2S1.3 MVP Clearance of Planned Annual Leave (COPA | Unassigned | Unassigned | Completed | 7. Closure | 1000312 |  | Delay reason known here | 2021-10-05 | 2021-10-05 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 10
Completed | 0% | Project 2 | Vendor On Boarding Complete | Unassigned | Yes | Completed | 6. Implement | 1000293 |  | Delay reason known here | 2022-08-16 | 2022-08-16 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 18 | Investment Brief/BC Completed | Unassigned | Unassigned | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2022-11-30 | 2022-11-30 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 11 | TMS R4 TIBCO Interface contracts- Commencement | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-02-14 | 2023-02-14 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 18 | Investment Brief/BC Commenced | Unassigned | Unassigned | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2022-08-01 | 2022-08-01 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 16 | Tender Evaluation Completed | Unassigned | Unassigned | Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2022-11-24 | 2022-11-24 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Completed | 0% | Project 16 | Phase 0 - VC for All - Commencement | Unassigned | Unassigned | Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-06-01 | 2023-06-01 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Completed | 0% | Project 11 | Present PROD data access solution to SAF | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2022-08-11 | 2022-08-11 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 25 | Obtain Sign off on Concept paper | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2022-01-19 | 2022-01-19 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 25 | Obtain Sign off on PACT | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2022-01-19 | 2022-01-19 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 11 | TMS R3 UAT completed | Unassigned | Yes | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-04-12 17:00 | 2024-04-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 25 | Business Requirements Specification signed off | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2022-03-11 | 2022-03-11 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 16 | Procurement Complete - Product & System Integrator | Unassigned | Unassigned | Completed | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-13 | 2023-03-13 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Completed | 0% | Project 18 | Solutions Options Paper signed off | Unassigned | Yes | Completed | 7. Closure | 1000309 |  | Delay reason known here | 2024-01-31 17:00 | 2024-01-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 3
Completed | 0% | Project 11 | TMS Data Interfaces- Separable Portion initiation | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2020-06-01 | 2020-06-01 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2020 | 2020 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 12 | Obtain Sign off on PACT | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-04-28 | 2023-04-28 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 11 | DSP repurpose of funds to implement PROD data acc | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-05-31 | 2023-05-31 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 11 | Present PROD data access solution estimation to DS | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-01-09 | 2023-01-09 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 8 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2022-11-30 17:00 | 2022-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | Investment Brief | Unassigned | Yes | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2022-11-15 | 2022-11-15 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 8 | PACT | Unassigned | Yes | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2022-11-15 | 2022-11-15 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 12 | Business Requirements signed off | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-06-30 | 2023-06-30 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 11 | TMS R3 - Design approval | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2022-05-23 | 2022-05-23 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 11 | Execute TMS R3 SIT test cases- Complete | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-17 | 2023-07-17 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 25 | Vendor On Boarding - Completed | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2023-03-22 | 2023-03-22 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 10 | Network Connectivity- NonProd environment connecti | Unassigned | Unassigned | Completed | 6. Implement | 1000301 |  | Delay reason known here | 2023-07-03 | 2023-07-03 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 11 | Document PROD data access solution | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2022-07-21 | 2022-07-21 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 11 | TMS R3 TPS / CTM interface unit testing | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2022-08-01 | 2022-08-01 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% to 5% | Project 11 | FARS interfaces unit testing- Commencement | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-11-24 17:00 | 2024-01-09 | 21 | 0.012259 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 11 | TMS R4 TEST (SIT) environment setup - Commencement | Unassigned | Yes | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-06-26 17:00 | 2024-06-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 11 | FARS interfaces unit testing- Complete | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-06-28 | 2023-06-28 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 25 | Concept Phase Complete | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2022-01-21 | 2022-01-21 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 11 | TMS R3 UAT environment setup- Commencement | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-25 | 2023-07-25 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 25 | Evaluate Phase complete | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2022-03-25 | 2022-03-25 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2022 | 2022 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 11 | TRIMS interfaces unit testing- Complete | Unassigned | Yes | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2024-05-13 17:00 | 2024-05-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 12 | Concept Phase Complete | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-06-05 | 2023-06-05 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 25 | SAD signed off | Unassigned | Unassigned | Completed | 7. Closure | 1000316 |  | Delay reason known here | 2023-05-15 | 2023-05-15 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Completed | 0% | Project 8 | Solutions Options - PSAD endorsed by PDA | Unassigned | Yes | Completed | 6. Implement | 1000299 |  | Delay reason known here | 2023-03-10 | 2023-03-10 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 36
Completed | 0% | Project 12 | Evaluate Phase complete | Unassigned | Unassigned | Completed | 7. Closure | 1000303 |  | Delay reason known here | 2023-08-08 | 2023-08-08 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Completed | 0% | Project 11 | TMS R4 Solution Architecture design approval- Comm | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2023-01-31 | 2023-01-31 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 11 | PROD data access endorsement from IT stakeholders | Unassigned | Unassigned | Completed | 6. Implement | 1000302 |  | Delay reason known here | 2022-10-20 | 2022-10-20 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Completed | 0% | Project 15 | MIL: Analysis & Design phase - complete | Unassigned | Unassigned | Completed | 7. Closure | 1000306 |  | Delay reason known here | 2018-02-28 17:00 | 2018-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 5 | 2018 | 2018 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 26
Completed | 0% | Project 15 | MIL: Seed funding released | Unassigned | Unassigned | Completed | 7. Closure | 1000306 |  | Delay reason known here | 2018-01-12 17:00 | 2018-01-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 5 | 2018 | 2018 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 26
Completed | 0% | Project 15 | MIL: Concept phase - complete | Unassigned | Unassigned | Completed | 7. Closure | 1000306 |  | Delay reason known here | 2018-01-16 17:00 | 2018-01-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 5 | 2018 | 2018 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 26
Completed | 0% | Project 15 | MIL: Evaluate phase - complete | Unassigned | Unassigned | Completed | 7. Closure | 1000306 |  | Delay reason known here | 2018-01-17 17:00 | 2018-01-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 5 | 2018 | 2018 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 26
Completed | 0% | Project 15 | MIL: Build & Test phase - complete | Unassigned | Unassigned | Completed | 7. Closure | 1000306 |  | Delay reason known here | 2018-03-06 17:00 | 2018-03-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 5 | 2018 | 2018 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 26
Completed | 0% | Project 15 | MIL: Procurement contract awarded | Unassigned | Unassigned | Completed | 7. Closure | 1000306 |  | Delay reason known here | 2018-02-06 17:00 | 2018-02-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 5 | 2018 | 2018 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 26
Completed | 0% | Project 15 | MIL: Project closed | Unassigned | Unassigned | Completed | 7. Closure | 1000306 |  | Delay reason known here | 2018-05-24 17:00 | 2018-05-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 5 | 2018 | 2018 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 26
Completed | 0% | Project 114 | 2.00 Investment Brief (or Equivalent) Sign Off | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001647 |  | Delay reason known here | 2024-11-19 17:00 | 2024-11-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 20
Completed | 0% | Project 114 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-02-07 17:00 | 2025-02-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 20
Completed | 0% | Project 114 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 20
Completed | 0% | Project 114 | 2.00 P20 Cost Estimate Ready | Deliverable | Project Kickoff | Completed | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 20
Completed | 0% | Project 114 | CONCEPT PHASE COMPLETE (GATE 0) | Governance | Project Kickoff | Completed | 3. Evaluate | 1001647 |  | Delay reason known here | 2025-02-26 17:00 | 2025-02-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | Project Manager 20
Completed | 0% | Project 19 | Ramsys & Trackware Migration Establishment | Unassigned | Unassigned | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-11-30 17:00 | 2023-11-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Completed | 0% | Project 19 | Rail.hr (GovDC) Migration Establishment | Unassigned | Yes | Completed | 5. Build & Test | 1000310 |  | Delay reason known here | 2023-10-23 08:00 | 2023-10-23 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | Yes | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Cancelled | 0% | Project 22 | PACT | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1000313 |  | Delay reason known here | 2024-05-30 17:00 | 2024-05-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 1 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 32
Cancelled | 0% | Project 22 | Go live | Deliverable | Go-Live | Cancelled | 7. Closure | 1000313 |  | Delay reason known here | 2023-12-20 17:00 | 2023-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 1 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 32
Cancelled | N/A | Project 20 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Cancelled | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-10-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 31
Cancelled | N/A | Project 20 | 6.05 Service Design & Definition Complete (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-08-23 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 31
Cancelled | N/A | Project 20 | GR:6.07 Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-08-23 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 31
Cancelled | N/A | Project 20 | 6.04 Release Retrospective | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-08-23 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 31
Cancelled | N/A | Project 20 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-11-12 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 31
Cancelled | N/A | Project 20 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 31
Cancelled | N/A | Project 17 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-08-16 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 17 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-08-02 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 17 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-08-02 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 17 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-03-26 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 17 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-04 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | 0% | Project 13 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 7. Closure | 1000304 |  | Delay reason known here | 2024-11-29 17:00 | 2024-11-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 22
Cancelled | N/A | Project 9 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 7. Closure | 1000300 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 9 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1000300 |  | Delay reason known here | 2024-04-19 17:00 | 2024-04-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 17 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-09-16 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 17 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-11 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 17 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-25 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 17 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-09-16 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 17 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-11 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 17 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-10-11 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | 0% | Project 10 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | 0% | Project 10 | DCS REGISTRATION COMPLETE | Deliverable | Unassigned | Cancelled | 6. Implement | 1000301 |  | Delay reason known here | 2023-02-28 17:00 | 2023-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | 0% | Project 10 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000301 |  | Delay reason known here | 2023-05-12 17:00 | 2023-05-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | 0% | Project 10 | GR5.07 Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000301 |  | Delay reason known here | 2024-08-15 08:00 | 2024-08-15 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | 0% | Project 10 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000301 |  | Delay reason known here | 2024-08-16 08:00 | 2024-08-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | 0% | Project 10 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000301 |  | Delay reason known here | 2024-11-18 08:00 | 2024-11-18 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 17 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-08-16 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 17 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-08-16 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 17 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000308 |  | Delay reason known here | 2024-08-16 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 11 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 11 | 3.22 IT Work Package (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 11 | DCS REGISTRATION COMPLETE | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2023-07-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 11 | GR4.16 Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2024-08-05 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 11 | GR4.17 Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2024-08-05 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 11 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2024-08-05 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 11 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2024-08-05 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 11 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2024-08-05 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 11 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2024-08-05 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 11 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2024-08-05 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 11 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2025-09-30 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2026 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 11 | 4.03 HYB Team Charter (Optional) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2024-08-02 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 11 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2024-08-02 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 27 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here |  | 2024-08-02 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 27 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here |  | 2024-08-02 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 27 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here |  | 2024-08-02 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 27 | 3.05 Business Impact Assessment Sign Off | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 27 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 27 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here |  | 2024-08-02 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 27 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 27 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here |  | 2024-08-02 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 27 | 3.17 Change on a Page Complete | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here |  | 2024-08-02 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 27 | 3.18 Change Management Plan Complete | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 27 | 3.20 Test Strategy Sign Off | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 27 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 27 | 3.22 IT Work Package (Opt) | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here |  | 2024-08-02 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 27 | DCS REGISTRATION COMPLETE | Governance | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 27 | 3.00 P50 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 2. Concept | 1000840 |  | Delay reason known here |  | 2024-08-02 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 79 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 79 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 23 | GR: Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | 0% | Project 23 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | 0% | Project 23 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | 0% | Project 23 | 3.17 Change on a Page Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | 0% | Project 23 | 3.22 IT Work Package (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | 0% | Project 23 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000314 |  | Delay reason known here | 2023-07-07 17:00 | 2023-07-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | N/A | Project 23 | 5.03 Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | 0% | Project 23 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here | 2024-11-01 08:00 | 2024-11-01 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | N/A | Project 23 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | N/A | Project 23 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | 0% | Project 23 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here | 2024-09-30 17:00 | 2024-09-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | N/A | Project 23 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | N/A | Project 23 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | 0% | Project 23 | 4.14 Detailed Service Design & Def'n Onboard Pack | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here | 2024-10-03 08:00 | 2024-10-03 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | N/A | Project 23 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | N/A | Project 23 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | N/A | Project 23 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | 0% | Project 23 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000314 |  | Delay reason known here | 2024-11-28 17:00 | 2024-11-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | N/A | Project 29 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | 0% | Project 29 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2024-08-28 17:00 | 2024-08-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | 0% | Project 29 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here | 2024-08-28 17:00 | 2024-08-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 13 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 7. Closure | 1000304 |  | Delay reason known here |  | 2024-12-05 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 22
Cancelled | N/A | Project 13 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 7. Closure | 1000304 |  | Delay reason known here |  | 2024-12-05 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 22
Cancelled | N/A | Project 13 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 7. Closure | 1000304 |  | Delay reason known here |  | 2024-10-28 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 22
Cancelled | N/A | Project 13 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 7. Closure | 1000304 |  | Delay reason known here |  | 2024-10-28 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 22
Cancelled | N/A | Project 13 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 7. Closure | 1000304 |  | Delay reason known here |  | 2024-09-13 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 22
Cancelled | 0% | Project 79 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 79 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 79 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 79 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 79 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 79 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 79 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 79 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001373 |  | Delay reason known here | 2024-08-15 17:00 | 2024-08-15 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 61 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 42 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-01 17:00 | 2024-08-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-02 17:00 | 2024-08-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | -10% to -5% | Project 42 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-04-11 17:00 | 2025-02-21 17:00 | -35 | -0.050143 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | -10% to -5% | Project 42 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-03-28 17:00 | 2025-01-24 17:00 | -44 | -0.063037 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | N/A | Project 42 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here |  | 2024-09-30 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | N/A | Project 42 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here |  | 2024-09-30 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | N/A | Project 5 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | 0% | Project 5 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | 0% | Project 5 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | 0% | Project 5 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | 0% | Project 5 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | 0% | Project 5 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | 0% | Project 5 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-09-13 17:00 | 2024-09-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | 0% | Project 5 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-09-13 17:00 | 2024-09-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | N/A | Project 61 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 3.10 Product Backlog Ready | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 3.12 Program Architecture Guide Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2024-09-16 08:00 | 2024-09-16 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 42 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 42 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000987 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 5 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-08-16 17:00 | 2024-08-16 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | 0% | Project 5 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | 0% | Project 5 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | N/A | Project 3 | 7.03 Closure Memo Sign Off for Phase 3 | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | 1000294 |  | Delay reason known here |  | 2025-06-27 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 3 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Cancelled | 3. Evaluate | 1000294 |  | Delay reason known here |  | 2025-06-30 08:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 77 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-04-01 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-04-01 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 77 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-01-31 08:00 | 2025-01-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 77 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-01-31 08:00 | 2025-01-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 77 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 93 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | 0% | Project 93 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here | 2024-08-26 17:00 | 2024-08-26 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 76 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2024-08-27 17:00 | 2024-08-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2024-08-27 17:00 | 2024-08-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2024-08-27 17:00 | 2024-08-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2024-08-27 17:00 | 2024-08-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-01-24 17:00 | 2025-01-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2024-08-27 17:00 | 2024-08-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 59 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 08:00 | 2024-08-19 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 68 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 68 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 68 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here | 2025-02-28 17:00 | 2025-02-28 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 68 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001355 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 66 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 66 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 66 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 66 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 66 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-10-03 17:00 | 2024-10-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2024-12-12 17:00 | 2024-12-12 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 66 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 66 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-07 17:00 | 2025-02-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 66 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-03 17:00 | 2025-02-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-21 17:00 | 2025-02-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-07 17:00 | 2025-02-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-03 17:00 | 2025-02-03 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-03-04 17:00 | 2025-03-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-04-01 17:00 | 2025-04-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-03-17 17:00 | 2025-03-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 66 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | 0% | Project 66 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here | 2025-05-05 17:00 | 2025-05-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 66 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001353 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 12
Cancelled | N/A | Project 75 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2025-02-27 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2025-01-24 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2025-01-28 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2025-02-28 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2025-02-20 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2025-02-26 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | 0% | Project 75 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-11-08 17:00 | 2024-11-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2025-04-01 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | 0% | Project 75 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-05-01 17:00 | 2025-05-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2025-05-19 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | 0% | Project 71 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | -25% to -10% | Project 71 | 3.21 Strategic/Final Business Case Approved (FIAC) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 | 2024-08-21 17:00 | -81 | -0.23762 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | -5% to 0% | Project 71 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 | 2024-11-22 17:00 | -15 | -0.044004 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-03-31 17:00 | 2025-03-31 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-08-21 17:00 | 2024-08-21 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2024-12-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-01 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 30
Cancelled | 0% | Project 71 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-01 17:00 | 2025-05-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-01 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-01 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-05-01 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 71 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | 1001358 |  | Delay reason known here | 2025-06-13 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 30
Cancelled | N/A | Project 64 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 64 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here | 2024-11-01 17:00 | 2024-11-01 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 64 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 6. Implement | 1001350 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 77 | BUILD COMPLETE | Governance | Unassigned | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 77 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Cancelled | 3. Evaluate | 1001364 |  | Delay reason known here | 2025-06-05 17:00 | 2025-06-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 29 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 61 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2025-01-24 17:00 | 2025-01-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2025-01-07 17:00 | 2025-01-07 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2024-12-20 17:00 | 2024-12-20 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2024-12-06 17:00 | 2024-12-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2024-12-06 17:00 | 2024-12-06 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2025-01-10 17:00 | 2025-01-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2025-01-23 17:00 | 2025-01-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 85 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-30 17:00 | 2024-08-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 85 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-10-04 17:00 | 2024-10-04 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 85 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 7. Closure | 1001399 |  | Delay reason known here | 2024-08-08 17:00 | 2024-08-08 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 61 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2025-01-17 17:00 | 2025-01-17 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2025-02-05 17:00 | 2025-02-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 61 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | N/A | Project 61 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001328 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 25
Cancelled | 0% | Project 65 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-12-10 17:00 | 2024-12-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | N/A | Project 65 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001351 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2025-04-30 17:00 | 2025-04-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2025-01-10 17:00 | 2025-01-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | N/A | Project 65 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001351 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 65 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1001351 |  | Delay reason known here | 2024-09-02 17:00 | 2024-09-02 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 29
Cancelled | 0% | Project 16 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-11-23 17:00 | 2023-11-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2024 | 2024 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-29 17:00 | 2023-03-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-29 17:00 | 2023-03-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-29 17:00 | 2023-03-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | N/A | Project 16 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-11-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2022 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | N/A | Project 16 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-11-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2022 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | N/A | Project 16 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-11-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2022 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-29 17:00 | 2023-03-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-29 17:00 | 2023-03-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | >25%+ | Project 16 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-11-30 17:00 | 2024-11-29 17:00 | 760 | 0.35398 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2022 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2023-03-29 17:00 | 2023-03-29 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2023 | 2023 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | N/A | Project 16 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-11-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2022 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | N/A | Project 16 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-11-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2022 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2024-09-27 17:00 | 2024-09-27 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | N/A | Project 16 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-11-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2022 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | N/A | Project 16 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2021-11-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2022 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 5 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-09-02 08:00 | 2024-09-02 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | 0% | Project 5 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here | 2024-09-02 08:00 | 2024-09-02 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | N/A | Project 5 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | N/A | Project 5 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1000296 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 8
Cancelled | 0% | Project 59 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 4.00 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 59 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here | 2024-08-19 17:00 | 2024-08-19 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 59 | SAA BUILD COMPLETE (Vendor) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001282 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | 0% | Project 3 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-08-23 17:00 | 2024-08-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | 0% | Project 3 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-08-23 17:00 | 2024-08-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | 0% | Project 3 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-08-23 17:00 | 2024-08-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | 0% | Project 3 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-08-23 17:00 | 2024-08-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | 0% | Project 3 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-08-23 17:00 | 2024-08-23 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | N/A | Project 93 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 93 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001440 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 13
Cancelled | N/A | Project 31 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 7
Cancelled | N/A | Project 31 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1000872 |  | Delay reason known here | 2024-04-30 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 7
Cancelled | N/A | Project 31 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 7
Cancelled | N/A | Project 31 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 2. Concept | 1000872 |  | Delay reason known here | 2024-05-31 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 7
Cancelled | N/A | Project 31 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 2. Concept | 1000872 |  | Delay reason known here | 2024-06-28 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 2024 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 7
Cancelled | 0% | Project 16 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-04-30 08:00 | 2025-04-30 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 34
Cancelled | 0% | Project 16 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 5. Build & Test | 1000307 |  | Delay reason known here | 2025-08-25 08:00 | 2025-08-25 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 7 | 2026 | 2026 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 34
Cancelled | N/A | Project 63 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  | 2025-02-21 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 4 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 4 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Cancelled | 6. Implement | 1000295 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 15
Cancelled | N/A | Project 76 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-01-30 17:00 | 2025-01-30 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-02-14 17:00 | 2025-02-14 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-02-17 08:00 | 2025-02-17 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-02-17 08:00 | 2025-02-17 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-03-31 08:00 | 2025-03-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 76 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 76 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001363 |  | Delay reason known here | 2025-03-31 08:00 | 2025-03-31 08:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 19 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.04 HYB Release Retrospective Complete | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.04 HYB Release Retrospective Complete | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 29 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 29 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1000869 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 110 | Pilot PSAD Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001617 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 22
Cancelled | N/A | Project 110 | Pilot Business Requirements Document Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001617 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 22
Cancelled | N/A | Project 110 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001617 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 22
Cancelled | N/A | Project 110 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001617 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 22
Cancelled | N/A | Project 110 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001617 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 22
Cancelled | N/A | Project 110 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001617 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 22
Cancelled | N/A | Project 19 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.04 HYB Release Retrospective Complete | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 75 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2024-11-14 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2024-11-14 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2024-11-14 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2024-11-14 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2024-11-14 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2024-11-28 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2024-11-28 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2024-11-14 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2024-11-14 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 75 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here |  | 2024-11-14 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | 0% | Project 75 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here | 2024-12-05 17:00 | 2024-12-05 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 19 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 5.00 Service Continuity Runbook Complete | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  | 2025-02-28 17:00 |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.04 HYB Release Retrospective Complete | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.04 HYB Release Retrospective Complete | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 19 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 7 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | EVALUATE PHASE COMPLETE (GATE 1) | Governance | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 7 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 6. Implement | 1000298 |  | Delay reason known here | 2024-12-13 17:00 | 2024-12-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.01 Sol'n Architecture Design (SAD) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.02 Functional Specification Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.00 P80 Cost Estimate Ready | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 5.07 GR Cyber Sec Test Support Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 5.03 HYB Release Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 5.00 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | BUILD & TEST PHASE COMPLETE | Governance | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 6.00 Application Handover Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.16 GR Cyber Sec Change Consult Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | N/A | Project 7 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1000298 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 38
Cancelled | 0% | Project 62 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-24 17:00 | 2025-02-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-02-10 17:00 | 2025-02-10 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-01-24 17:00 | 2025-01-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | 0% | Project 62 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001347 |  | Delay reason known here | 2025-01-24 17:00 | 2025-01-24 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 16
Cancelled | N/A | Project 74 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 4.03 HYB Team Charter (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 4.04 HYB Definition of Done | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 4.00 Technical Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 4.08 Infrastructure Sol'n Design Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 4.10 Traceability Matrix Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 4.12 Comms Plan Sign Off | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 4.13 Bus Change Readiness Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 4.14 Detailed Service Design & Defn Onboard Pack | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 4.15 Detailed Change Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 4.00 ITSM Onboarding Checklist Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 4.00 ICT Release Impact Assessment Complete | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 74 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001361 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 28
Cancelled | N/A | Project 109 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001608 |  | Delay reason known here | 2024-11-08 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 5
Cancelled | N/A | Project 109 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001608 |  | Delay reason known here | 2024-11-08 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 5
Cancelled | N/A | Project 109 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001608 |  | Delay reason known here | 2024-11-08 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 5
Cancelled | N/A | Project 109 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001608 |  | Delay reason known here | 2024-11-08 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 5
Cancelled | N/A | Project 109 | 6.01 Training Docs & App H'over Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001608 |  | Delay reason known here | 2024-11-08 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 5
Cancelled | N/A | Project 109 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001608 |  | Delay reason known here | 2024-11-08 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 5
Cancelled | N/A | Project 109 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Cancelled | 6. Implement | 1001608 |  | Delay reason known here | 2024-11-08 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 5
Cancelled | N/A | Project 109 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 6. Implement | 1001608 |  | Delay reason known here | 2024-11-08 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 5
Cancelled | N/A | Project 75 | Cyber Sec Requirements Complete | Deliverable | Project Kickoff | Cancelled | 3. Evaluate | 1001362 |  | Delay reason known here | 2025-03-07 08:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 2025 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 63 | Service Design & Def'n & Onb'ding Pack Prepared | Deliverable | Unassigned | Cancelled | 3. Evaluate | 1001349 |  | Delay reason known here |  | 2025-02-28 08:00 |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 2025 | 1900 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 18
Cancelled | N/A | Project 24 | Contract signed off | Unassigned | Yes | Cancelled | 2. Concept | 1000315 |  | Delay reason known here | 2024-04-08 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 35
Cancelled | -25% to -10% | Project 3 | Closure- SGR Completed | Unassigned | Yes | Cancelled | 3. Evaluate | 1000294 |  | Delay reason known here | 2024-12-20 17:00 | 2024-02-29 17:00 | -206 | -0.16775 | #REF! | Duplicate | Sub-Portfolio 4 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 4
Cancelled | <-25% | Project 20 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 4. Analyse & Design | 1000311 |  | Delay reason known here | 2024-10-31 17:00 | 2024-02-05 17:00 | -188 | -0.43021 | #REF! | Duplicate | Sub-Portfolio 8 | 2024 | 2025 | No | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 31
Cancelled | N/A | Project 24 | RFx activities complete | Unassigned | Yes | Cancelled | 2. Concept | 1000315 |  | Delay reason known here | 2024-03-25 17:00 |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 2024 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 35
Cancelled | 0% | Project 19 | Archiving and Decommission - Applications/DBs 7-9 | Unassigned | Yes | Cancelled | 5. Build & Test | 1000310 |  | Delay reason known here | 2025-06-13 17:00 | 2025-06-13 17:00 | 0 | 0 | #REF! | Duplicate | Sub-Portfolio 8 | 2025 | 2025 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Manager 6
Cancelled | N/A | Project 23 | GO LIVE - OT-IT Ph2 | Deliverable | Go-Live | Cancelled | 6. Implement | 1000314 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 7 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 33
Cancelled | 0% to 5% | Project 11 | TMS R4 UAT environment setup- Commencement | Deliverable | Unassigned | Cancelled | 6. Implement | 1000302 |  | Delay reason known here | 2024-05-31 17:00 | 2024-09-25 17:00 | 82 | 0.047869 | #REF! | Duplicate | Sub-Portfolio 7 | 2025 | 2024 | No | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | Project Manager 17
Cancelled | N/A | Project 72 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.06 Business Requirements Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 72 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001359 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.17 Change on a Page Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.18 Change Management Plan Complete | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 120 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.20 Test Strategy Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 120 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001775 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 121 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001776 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 2.00 Arch Review & Cyber Sec Assessment Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 2.00 Prioritisation Score Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.01 Non-Standard Service Request Raised (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.04 PACT Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.05 Business Impact Assessment Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.07 Product Vision Sign Off (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.08 HYB Release Plan | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.09 HYB High Level Story Map | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.10 HYB Product Backlog | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.11 Prelim Sol'n Arch Design (PSAD) Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.12 Program Architecture Guide | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.13 RFx/Other Procurement Document Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.14 Project Management Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.15 Benefits Realisation Plan Sign Off | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.16 Stakeholder Assessment & Eng Plan Complete | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.21 Final Business Case Approved - FIAC (>$1M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.22 IT Work Package (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | DCS REGISTRATION COMPLETE (>$5M) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.00 P50 Cost Estimate Ready | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.02 GR Cyber Sec Requirements Form Submitted | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.03 GR Cyber Sec Assessment Form Submitted (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.19 GR Service Design & Definition Team Engaged | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 122 | 3.23 GR Records Management Team Engaged (Opt) | Deliverable | Project Kickoff | Cancelled | 2. Concept | 1001777 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 4 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 14
Cancelled | N/A | Project 73 | 4.09 Test Plan Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 4.11 Security Risk Assessment (SRA) Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 4.17 GR Cyber Sec Sol'n Review Requested (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 5.01 Test Cases Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 5.02 Test Summary Report/Cert Sign Off | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 5.04 Training Management Plan Sign Off (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 5.05 Service Continuity Runbook Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 5.06 Release Requested (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 5.00 ICT Release Board Approval (CAB) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 6.07 GR Cyber Sec Pre-Rel. Review Complete (Opt) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 6.04 HYB Release Retrospective Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 6.05 Service Design & Def'n & Onb'ding Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 6.01 Training Docs & App H'over Checklist Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 6.02 Implementation Plan Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 6.03 Go Live / Prod Readiness Checklist Complete | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 6.06 New Form for Creating New Service (IT Catal.) | Deliverable | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | GO LIVE | Deliverable | Go-Live | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | IMPLEMENT PHASE COMPLETE (GATE 2) | Governance | Unassigned | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 7.01 Handover Document Sign Off | Deliverable | Gate 3 Approval | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 7.02 PIR Sign Off | Deliverable | Gate 3 Approval | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | 7.03 Closure Memo Sign Off | Deliverable | Gate 3 Approval | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
Cancelled | N/A | Project 73 | PROJECT CLOSED (GATE 3) | Governance | Gate 3 Approval | Cancelled | 4. Analyse & Design | 1001360 |  | Delay reason known here |  |  |  |  | #REF! | Duplicate | Sub-Portfolio 8 | 1900 | 1900 | No | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Project Manager 21
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Note on R7: Andy Luu: Variance (%) = (Milestone Variance/Project Duration) * 100

## PV_Risks
WRK09
Last Extracted | 2025-05-07
59 | 0 | 8 | 0
Work ID # | # Active Risks | Overdue | No Mitigation Action Plan | Project Description | Risk Title | CRI ID | Description | Status | Inherent risk level | Category | Residual Risk Level | Owner | Due Date | Inherent Consequence | Inherent Likelihood | Cause | Cause Description | Consequence Description | Mitigation Strategy | Mitigation Action Plan | Residual Risk Consequence | Residual Risk Likelihood | Initiated On | Risk Age | Sub-Portfolio | Work Type | Risk Type | PMO Comment
1000308 | 0 | 0 | 0 | Project 17 | Master Data to support ePAS go live 1 Sep24 | 138635 | Whilst focusing on data analysis and also functioning as SI, the risk remain high to not be able to fulfil full data ask on 1 Sep2024 | On Hold | Medium (C) | Information & Data | High (B) | Project Manager 4 | 2024-06-28 | C3 - Major | L4 - Unlikely | Information – Accuracy/Timeliness/Relevancy | Cause Description 1 | Consequence Description 1 | Treat | Mitigation Action Plan 1 | C3 – Major | L2 – Very Likely | 2023-11-13 | 547 | Sub-Portfolio 7 | Project | Unassigned
1000312 | 0 | 1 | 0 | Project 21 | Scope change from Union Consultations | 152411 | Potential change to scope due to union consultations. Note that this risk has now been extended to cover the Enterprise Bargaining Agreement negotiations, which commence July 2024. It is expected that union consulation for TEW will recommence once the EBA negotiations are finalised | Open | Medium (C) | Unassigned | Unassigned | Project Manager 10 | 2024-12-31 | C4 - Moderate | L3 - Likely | External – Political/Economic/Natural Events | Cause Description 2 | Consequence Description 2 | Treat | Mitigation Action Plan 2 | Unassigned | Unassigned | 2023-12-07 | 523 | Sub-Portfolio 7 | Project | Unassigned
1000302 | 0 | 0 | 0 | Project 11 | ODS-TLS Project moved to Jul 25 Tentatively | 159880 | ODS-TLS Project implementation has moved for the third time to potentially July 24 from March 24, due to Control Systems being not ready for TLS to be onboarded. This delay may create contention with test environments and resourcing | Open | Medium (C) | Governance, Legal and Assurance | Medium (C) | Project Manager 17 | 2025-08-30 | C4 - Moderate | L3 - Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 3 | Consequence Description 3 | Tolerate | Mitigation Action Plan 3 | C5 – Minor | L3 – Likely | 2024-02-01 17:40 | 466.2638 | Sub-Portfolio 7 | Project | Unassigned
1000302 | 0 | 0 | 0 | Project 11 | Change to DSP TLS Config | 159881 | TLS config done to date, may require changes due to Siemens requirements. This will delay the completion of the testing. | Open | Medium (C) | Vendor | Medium (C) | Project Manager 17 | 2026-04-30 | C4 - Moderate | L3 - Likely | Quality – Assurance/Controls/Planning/Improvement | Cause Description 4 | Consequence Description 4 | Unassigned | Mitigation Action Plan 4 | C4 – Moderate | L3 – Likely | 2024-02-01 17:49 | 466.2576 | Sub-Portfolio 7 | Project | Unassigned
1000308 | 0 | 0 | 0 | Project 17 | EPS solution design governance | 203233 | EIIP has not documented EPS how the EPS solution design will be reviewed / approved. There is a risk the project will be delayed due to an inability to make / agreed solution design decisions | On Hold | Medium (C) | Governance, Legal and Assurance | High (B) | Project Manager 4 | 2024-08-30 | C2 - Severe | L5 - Very Unlikely | Process – Complexity/Absence/Compliance | Cause Description 5 | Consequence Description 5 | Transfer | Mitigation Action Plan 5 | C3 – Major | L2 – Very Likely | 2024-08-19 11:46 | 266.5099 | Sub-Portfolio 7 | Project | Unassigned
1000308 | 0 | 0 | 0 | Project 17 | EPS Master Data governance | 203234 | EPS data governance is not defined / agreed. There is a serious risk of project delays due to an inability to define solution scope required to support data governance activities | On Hold | High (B) | Information & Data | Very High (A) | Project Manager 4 | 2024-08-31 | C1 - Catastrophic | L5 - Very Unlikely | Management – Funding/Governance/Reporting/Strategy | Cause Description 6 | Consequence Description 6 | Transfer | Mitigation Action Plan 6 | C3 – Major | L1 - Almost Certain | 2024-08-19 11:52 | 266.5052 | Sub-Portfolio 7 | Project | Unassigned
1000308 | 0 | 0 | 0 | Project 17 | Analyse and Design phase: Exit risk | 203242 | Risk that inability to get solution design decisions approved will delay closing Analyse and Design phase | On Hold | Medium (C) | Governance, Legal and Assurance | Very High (A) | Project Manager 4 | 2024-08-30 | C2 - Severe | L5 - Very Unlikely | Management – Funding/Governance/Reporting/Strategy | Cause Description 7 | Consequence Description 7 | Treat | Mitigation Action Plan 7 | C4 – Moderate | L1 - Almost Certain | 2024-08-19 12:24 | 266.483 | Sub-Portfolio 7 | Project | Unassigned
1000308 | 0 | 0 | 0 | Project 17 | EPS Master Data sources | 203245 | Multiple sources of varying quality exist for each of the Master Data sources. Risk that project will be delayed if no agreement on which is the right source for each Master Data set | On Hold | Medium (C) | Information & Data | Very High (A) | Project Manager 4 | 2024-08-30 | C2 - Severe | L5 - Very Unlikely | Information – Accuracy/Timeliness/Relevancy | Cause Description 8 | Consequence Description 8 | Transfer | Mitigation Action Plan 8 | C3 – Major | L1 - Almost Certain | 2024-08-19 12:48 | 266.4664 | Sub-Portfolio 7 | Project | Unassigned
1001362 | 0 | 0 | 0 | Project 75 | Vanguard is at risk due to end of life/Support | 206332 | IF end of life/support Vanguard continues to be used THEN it could becomes unavailable due to either software or hardware failure possibly leading to eventuation of commercial compliance issues for Transport. CONTEXT: Vanguard is a tool developed within TfNSW to manage fare compliance across the Greater Sydney Network, delivered in March 2019 and currently supported by teams in CSO. It has inputs from Revenue NSW, Crime and research and the fare compliance teams. Its main capability that it is delivering as of 2024 is to provide reports from TfNSW to the Greater Sydney Bus Contract (GSBC) vendors on fare compliance and compliance activities within Greater Sydney. This is a commercial requirement KPI for TfNSW to deliver 95% compliance, failure to meet this leave TfNSW exposed to commercial penalties under the GSBC arrangements. | Open | Medium (C) | Unassigned | Unassigned | Project Manager 18 | 2025-06-20 | C4 - Moderate | L3 - Likely | Infrastructure – Delivery/Maintenance/Equipment | Cause Description 9 | Consequence Description 9 | Unassigned | Mitigation Action Plan 9 | Unassigned | Unassigned | 2024-08-26 08:46 | 259.6346 | Sub-Portfolio 4 | Project | Unassigned
1001328 | 0 | 0 | 0 | Project 61 | RailTable DB Blocker | 207442 | RailTable DB Blocker - There are business managed apps (BEX, Auto Prose, Prose Linker and Business Rules Engine) which are connected to RailTable DB. As part of Solaris Decom initiative, the databases are being migrated from Solaris to Exadata. Once the RailTable DB is migrated, these business managed apps should also point to the new database in Exadata. Currently there is There is no availability of the source code for these business managed applications which makes it difficult to point these apps to the new db in Exadata. Assessment underway to determine how to establish connectivity with these apps . A demo with the business team setup to collect more info on the way these applications function. | Open | Very High (A) | Information & Data | Medium (C) | Project Manager 31 | 2025-05-30 | C3 - Major | L1 - Almost Certain | Quality – Assurance/Controls/Planning/Improvement | Cause Description 10 | Consequence Description 10 | Treat | Mitigation Action Plan 10 | C3 – Major | L4 – Unlikely | 2024-08-28 14:03 | 257.4143 | Sub-Portfolio 8 | Project | Unassigned
1000301 | 0 | 0 | 0 | Project 10 | Union Strikes could impact ODS-TLS delay in Go Liv | 216372 | Union strike could impact ODS TLS Go Live | Open | Medium (C) | Unassigned | Low (D) | Project Manager 17 | 2025-08-29 | C4 - Moderate | L4 - Unlikely | External – Political/Economic/Natural Events | Cause Description 11 | Consequence Description 11 | Unassigned | Mitigation Action Plan 11 | C5 – Minor | L4 – Unlikely | 2024-09-23 16:25 | 231.316 | Sub-Portfolio 7 | Project | Unassigned
1000310 | 0 | 0 | 0 | Project 19 | Budget Risk | 226382 | Program is progressing this year without any contingency. The IRR (10.7%) was not included in the budget. Unexpected Opex cost still bore by the project on the CDS Support. Delays in Cloud Hosting Chargeback. | Open | High (B) | Finance & Procurement | Medium (C) | Project Manager 6 | 2025-06-30 | C3 - Major | L3 - Likely | Unassigned | Cause Description 12 | Consequence Description 12 | Tolerate | Mitigation Action Plan 12 | C4 – Moderate | L4 – Unlikely | 2024-10-24 17:23 | 200.2755 | Sub-Portfolio 8 | Project | Unassigned
1001349 | 0 | 1 | 0 | Project 63 | New Contract | 237200 | In case the future appointed third party vendor requires a new contract with TfNSW (not a contract variation or addendum to an existing contract), it could delay the project by circa 3 months | Open | Medium (C) | Unassigned | Unassigned | Project Manager 19 | 2025-04-30 | C4 - Moderate | L4 - Unlikely | Process – Complexity/Absence/Compliance | Cause Description 13 | Consequence Description 13 | Unassigned | Mitigation Action Plan 13 | Unassigned | Unassigned | 2024-11-26 10:26 | 167.5652 | Sub-Portfolio 4 | Project | Unassigned
1001617 | 0 | 0 | 0 | Project 110 | EiPaaS Migration dependencies | 237393 | The EiPaaS migration will have significant impact on the ICFMS testing 02/04: Internal assessment is complete, discussion with S&T is planned followed by a discussion with project steer. co for the next steps. | Open | Very High (A) | Technology & Cyber Security | Unassigned | Project Manager 22 | 2025-05-31 | C3 - Major | L1 - Almost Certain | Technology – Effectiveness/Usage/Integration/Failu | Cause Description 14 | Consequence Description 14 | Unassigned | Mitigation Action Plan 14 | Unassigned | Unassigned | 2024-11-27 00:49 | 166.966 | Sub-Portfolio 8 | Project | Unassigned
1001617 | 0 | 0 | 0 | Project 110 | Equip PRIME and RAISI program dependenciess | 237394 | Unavailability of Equip non-production environments for ICFMS replatforming due to the PRIME and RAISI programs. | On Hold | High (B) | Technology & Cyber Security | Unassigned | Project Manager 22 | 2025-03-31 | C3 - Major | L3 - Likely | Technology – Effectiveness/Usage/Integration/Failu | Cause Description 15 | Consequence Description 15 | Unassigned | Mitigation Action Plan 15 | Unassigned | Unassigned | 2024-11-27 00:53 | 166.9635 | Sub-Portfolio 8 | Project | Unassigned
1001358 | 0 | 1 | 0 | Project 71 | Time blowout due to commercial engagement | 243036 | Most products are for international companies that need to source local service partners and the end of year shutdown delays TSS engagement. | Open | High (B) | Finance & Procurement | Unassigned | Project Manager 30 | 2025-01-31 | C3 - Major | L2 - Very Likely | Process – Complexity/Absence/Compliance | Cause Description 16 | Consequence Description 16 | Unassigned | Mitigation Action Plan 16 | C3 – Major | Unassigned | 2024-12-18 21:56 | 145.0863 | Sub-Portfolio 8 | Project | Schedule
1001358 | 0 | 0 | 0 | Project 71 | Risk of identifying business opex | 243037 | Risk of identifying business owner for the hardware/software procurement and service's operational cost to charge back to. | Open | Medium (C) | Finance & Procurement | Unassigned | Project Manager 30 | 2025-05-31 | C3 - Major | L3 - Likely | Management – Funding/Governance/Reporting/Strategy | Cause Description 17 | Consequence Description 17 | Unassigned | Mitigation Action Plan 17 | C3 – Major | Unassigned | 2024-12-18 21:59 | 145.0837 | Sub-Portfolio 8 | Project | Budget
1001358 | 0 | 0 | 0 | Project 71 | Low "BAU" Effort | 243038 | As the project has lost almost 50% of its allocated budget, the project is leaning on BAU support from different groups including ISSI/EUS/Solution Architecture and Cybersecurity. | Open | Medium (C) | Unassigned | Unassigned | Project Manager 30 | 2025-05-31 | C3 - Major | L3 - Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 18 | Consequence Description 18 | Unassigned | Mitigation Action Plan 18 | C4 – Moderate | Unassigned | 2024-12-18 22:02 | 145.082 | Sub-Portfolio 8 | Project | Budget
1001358 | 0 | 1 | 0 | Project 71 | Ambiguities in Scope Around Implementation | 243039 | Vendor (Datacom) has indicated that some aspects of the hardware management and their compliance with Transport cybersecurity requirements are unclear and will need to be investigated during the Analyse & Design phase | Open | Medium (C) | Technology & Cyber Security | Unassigned | Project Manager 30 | 2025-04-30 | C4 - Moderate | L3 - Likely | Technology – Effectiveness/Usage/Integration/Failu | Cause Description 19 | Consequence Description 19 | Unassigned | Mitigation Action Plan 19 | C4 – Moderate | Unassigned | 2024-12-18 22:06 | 145.0795 | Sub-Portfolio 8 | Project | Scope
1001440 | 0 | 0 | 0 | Project 93 | New enhancements to eSCD and Task Assigner | 243155 | As a result of consultation, new requirements may emerge that are required before the upgrade is completed. This may potentially result in needing to upgrade the existing production version and retrofitting the changes into this project. Thereby increased cost, scope and timelines. | Open | High (B) | Unassigned | Medium (C) | Project Manager 13 | 2026-01-31 | C3 - Major | L3 - Likely | External – Political/Economic/Natural Events | Cause Description 20 | Consequence Description 20 | Treat | Mitigation Action Plan 20 | C4 – Moderate | L3 – Likely | 2024-12-19 12:23 | 144.4842 | Sub-Portfolio 8 | Project | Unassigned
1001834 | 0 | 0 | 0 | Project 145 | TM1 current version is 10.2 is out of support | 254722 | The current Version is 2.0.3 support expires in April 2025. There is a potential to replace TM1 through a finance business managed project "Onestream“. Meanwhile IT has been requested to retain TM1 and to mitigate the risk in the interim (next 2-3 years). | Open | Medium (C) | Unassigned | Unassigned | Project Manager 7 | 2025-06-30 | C4 - Moderate | L3 - Likely | Unassigned | Cause Description 21 | Consequence Description 21 | Unassigned | Mitigation Action Plan 21 | Unassigned | Unassigned | 2025-02-14 06:58 | 87.7099 | Sub-Portfolio 7 | Light Project | Unassigned
1001834 | 0 | 0 | 0 | Project 145 | Go live in Jun-2025 may be impacted by EOFY | 255733 | Go live in Jun-2025 may be impacted by EOFY | Open | Medium (C) | Unassigned | Unassigned | Project Manager 7 | 2025-06-30 | C4 - Moderate | L4 - Unlikely | Unassigned | Cause Description 22 | Consequence Description 22 | Unassigned | Mitigation Action Plan 22 | Unassigned | Unassigned | 2025-02-19 12:24 | 82.4831 | Sub-Portfolio 7 | Light Project | Unassigned
1000987 | 0 | 0 | 0 | Project 42 | Design and price readiness by the end of March '25 | 256840 | The proposed end of analysis & design phase is March 2025. While the technical designs have been progressing well since mid December there is a strong likelihood that the quality or the completeness of the work at the end of March will not meet acceptable standards to support a phase exit. | Open | High (B) | People | High (B) | Project Manager 29 | 2025-05-16 | C3 - Major | L2 - Very Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 23 | Consequence Description 23 | Treat | Mitigation Action Plan 23 | C4 – Moderate | L2 – Very Likely | 2025-02-24 10:27 | 77.5646 | Sub-Portfolio 7 | Project | Unassigned
1000310 | 0 | 0 | 0 | Project 19 | WinDSX Changes in Application Tiering | 258328 | WinDSX: Request to change the Application tiering from Business Operation to Business critical. Requested by business (Adam Chamberlain-TSS) which may necessitate rearchitect of solution. Scope discrepancies / misalignment with Business and IT​. | Open | High (B) | Technology & Cyber Security | Unassigned | Project Manager 6 | 2025-05-31 | C2 - Severe | L3 - Likely | Technology – Effectiveness/Usage/Integration/Failu | Cause Description 24 | Consequence Description 24 | Treat | Mitigation Action Plan 24 | C4 – Moderate | L4 – Unlikely | 2025-02-27 12:14 | 74.4902 | Sub-Portfolio 8 | Project | Unassigned
1001282 | 0 | 1 | 0 | Project 59 | Project Delivery Meeting Budget Is At Risk | 259110 | The approved project funding may not be able to fund for the challenges experienced and additional activities discoverd during solution implementation | Open | Medium (C) | Unassigned | Unassigned | Project Manager 14 | 2025-04-30 | C4 - Moderate | L3 - Likely | Management – Funding/Governance/Reporting/Strategy | Cause Description 25 | Consequence Description 25 | Unassigned | Mitigation Action Plan 25 | Unassigned | Unassigned | 2025-02-28 17:07 | 73.2867 | Sub-Portfolio 7 | Project | Unassigned
1000307 | 0 | 0 | 0 | Project 16 | Equip Release not aligned to Program Requirement | 259568 | Overall Equip implementation approach determined as a result of Evaluate phase may not align with program requirement to deploy technical solution on 26 September 2025. Potential aligning to Enterprise Release now in Nov 2025 | Open | Very High (A) | Technology & Cyber Security | Low (D) | Project Manager 40 | 2025-05-30 | C2 - Severe | L1 - Almost Certain | Technology – Effectiveness/Usage/Integration/Failu | Cause Description 26 | Consequence Description 26 | Treat | Mitigation Action Plan 26 | C5 – Minor | L4 – Unlikely | 2025-03-03 12:08 | 70.4945 | Sub-Portfolio 7 | Project | Unassigned
1001351 | 0 | 1 | 0 | Project 65 | Transition of support may likely affect go live of | 260219 | The GS IT application management team has demanded that support for CI Portal and Secure Library be transitioned from Corp IT prior to these portal going live. The administration that is required and the contract variation needed to support this demand may delay go live. | Open | High (B) | Customer Service & Experience | Unassigned | Project Manager 29 | 2025-04-04 | C3 - Major | L2 - Very Likely | Management – Funding/Governance/Reporting/Strategy | Cause Description 27 | Consequence Description 27 | Treat | Mitigation Action Plan 27 | Unassigned | Unassigned | 2025-03-04 16:27 | 69.3147 | Sub-Portfolio 8 | Project | Unassigned
1000296 | 0 | 0 | 0 | Project 5 | Couchbase Procurement Delay | 261246 | The Couchbase license procurement may take longer than expected and it's impacting the readiness of the SIT environment. | Open | High (B) | Technology & Cyber Security | Unassigned | Project Manager 8 | 2025-05-23 | C3 - Major | L2 - Very Likely | Process – Complexity/Absence/Compliance | Cause Description 28 | Consequence Description 28 | Tolerate | Mitigation Action Plan 28 | Unassigned | Unassigned | 2025-03-07 18:10 | 66.2429 | Sub-Portfolio 7 | Project | Schedule
1001361 | 0 | 0 | 0 | Project 74 | Rail Operations Site Migraiton | 263747 | Business is driving this migration. Current Go-Live is end of April. Risk that this may get delayed depending on user availability impacting overall project timeline. Very light communication from the team with lack of regular updates. | Open | Medium (C) | Assets and Service Delivery | Low (D) | Project Manager 28 | 2025-06-30 | C4 - Moderate | L3 - Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 29 | Consequence Description 29 | Treat | Mitigation Action Plan 29 | C5 – Minor | L4 – Unlikely | 2025-03-16 15:58 | 57.3347 | Sub-Portfolio 8 | Project | Unassigned
1001361 | 0 | 0 | 0 | Project 74 | Time Table Production Site Migration | 263748 | Business have been advised to work towards 1st April date to complete remaining development activities with Corp IT. Risk that they may not be able to achieve this and request for extension. | Open | Medium (C) | Assets and Service Delivery | Low (D) | Project Manager 28 | 2025-06-30 | C5 - Minor | L2 - Very Likely | Technology – Effectiveness/Usage/Integration/Failu | Cause Description 30 | Consequence Description 30 | Tolerate | Mitigation Action Plan 30 | C5 – Minor | L4 – Unlikely | 2025-03-16 16:00 | 57.3332 | Sub-Portfolio 8 | Project | Unassigned
1001361 | 0 | 0 | 0 | Project 74 | Additional significant user requirements | 263749 | For the sites identified there may be possible shift in user requirements increasing the scope for PowerApps development. | Open | Medium (C) | Assets and Service Delivery | Low (D) | Project Manager 28 | 2025-06-30 | C4 - Moderate | L4 - Unlikely | Process – Complexity/Absence/Compliance | Cause Description 31 | Consequence Description 31 | Treat | Mitigation Action Plan 31 | C5 – Minor | L4 – Unlikely | 2025-03-16 16:03 | 57.3315 | Sub-Portfolio 8 | Project | Unassigned
1001361 | 0 | 0 | 0 | Project 74 | Decommission - scope creep | 263750 | There is a risk that more users (sites out of scope) come forward requesting either more time before the site can be shut down or require further migration and development. Impacting scope, schedule, cost. | Open | High (B) | Assets and Service Delivery | Low (D) | Project Manager 28 | 2025-08-31 | C3 - Major | L2 - Very Likely | Process – Complexity/Absence/Compliance | Cause Description 32 | Consequence Description 32 | Treat | Mitigation Action Plan 32 | C5 – Minor | L5 – Very Unlikely | 2025-03-16 16:05 | 57.3301 | Sub-Portfolio 8 | Project | Unassigned
1001361 | 0 | 0 | 0 | Project 74 | Restructure and Business Availability | 263751 | Risk due to current changes in the organisation. | Open | Low (D) | People | Unassigned | Project Manager 28 | 2025-08-31 | C5 - Minor | L4 - Unlikely | External – Political/Economic/Natural Events | Cause Description 33 | Consequence Description 33 | Tolerate | Mitigation Action Plan 33 | Unassigned | Unassigned | 2025-03-16 16:08 | 57.3276 | Sub-Portfolio 8 | Project | Unassigned
1001359 | 0 | 0 | 0 | Project 72 | Potential Delay in NDD OS Upgrade | 264808 | NDD operating system upgrade to RHEL is at risk in FY 25 due to unavailability of application SME. | Open | High (B) | People | Medium (C) | Project Manager 21 | 2025-05-15 | C4 - Moderate | L2 - Very Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 34 | Consequence Description 34 | Tolerate | Mitigation Action Plan 34 | C5 – Minor | L3 – Likely | 2025-03-20 11:20 | 53.5279 | Sub-Portfolio 8 | Project | Unassigned
1001373 | 0 | 0 | 0 | Project 79 | Schedule Delays and its impact on test resourcing | 267597 | Potential project impacts in the event of Phase 1 schedule delays will impact the committed CIC project pipeline | Open | High (B) | People | High (B) | Project Manager 38 | 2025-06-30 | C3 - Major | L3 - Likely | Information – Accuracy/Timeliness/Relevancy | Cause Description 35 | Consequence Description 35 | Treat | Mitigation Action Plan 35 | C3 – Major | L3 – Likely | 2025-04-01 10:49 | 41.5495 | Sub-Portfolio 7 | Project | Schedule
1001373 | 0 | 0 | 0 | Project 79 | Schedule Delays and its impact on test resourcing | 267597 | Potential project impacts in the event of Phase 1 schedule delays will impact the committed CIC project pipeline | Open | High (B) | People | High (B) | Project Manager 38 | 2025-06-30 | C3 - Major | L3 - Likely | Information – Accuracy/Timeliness/Relevancy | Cause Description 36 | Consequence Description 36 | Treat | Mitigation Action Plan 36 | C3 – Major | L3 – Likely | 2025-04-01 10:49 | 41.5495 | Sub-Portfolio 7 | Project | Schedule
1000310 | 0 | 0 | 0 | Project 19 | Organisational Change | 267724 | Changes to the Business teams and IT Teams poises the risk that user priority, allocation are shifting, and this impact the budget spent for this FY | Open | High (B) | People | High (B) | Project Manager 6 | 2025-06-30 | C3 - Major | L3 - Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 37 | Consequence Description 37 | Tolerate | Mitigation Action Plan 37 | C3 – Major | L3 – Likely | 2025-04-01 21:47 | 41.0925 | Sub-Portfolio 8 | Project | Unassigned
1001834 | 0 | 0 | 0 | Project 145 | Impact of proposed changes to Group Technology | 267862 | Proposed changes to the Group Technology structure may impact project delivery | Open | Medium (C) | People | Unassigned | Project Manager 7 | 2025-06-30 | C4 - Moderate | L3 - Likely | External – Political/Economic/Natural Events | Cause Description 38 | Consequence Description 38 | Tolerate | Mitigation Action Plan 38 | Unassigned | Unassigned | 2025-04-02 14:46 | 40.3845 | Sub-Portfolio 7 | Light Project | Unassigned
1001873 | 0 | 0 | 0 | Project 155 | Impact of proposed changes to Group Technology | 267864 | Proposed changes to the Group Technology structure may impact project delivery | Open | Medium (C) | People | Unassigned | Project Manager 7 | 2025-06-30 | C4 - Moderate | L3 - Likely | External – Political/Economic/Natural Events | Cause Description 39 | Consequence Description 39 | Tolerate | Mitigation Action Plan 39 | Unassigned | Unassigned | 2025-04-02 14:59 | 40.3755 | Sub-Portfolio 7 | Minor Work | Unassigned
1001524 | 0 | 0 | 0 | Project 104 | Impact of proposed changes to Group Technology | 267921 | Proposed changes to the Group Technology structure may impact project delivery | Open | Medium (C) | People | Unassigned | Project Manager 7 | 2025-06-30 | C4 - Moderate | L3 - Likely | External – Political/Economic/Natural Events | Cause Description 40 | Consequence Description 40 | Tolerate | Mitigation Action Plan 40 | Unassigned | L2 – Very Likely | 2025-04-02 15:51 | 40.3398 | Sub-Portfolio 7 | Minor Work | Unassigned
1000296 | 0 | 0 | 0 | Project 5 | Organisation Restructure | 267922 | Both TfNSW Group Technology and Sydney Trains are undergoing a major restructure. | Open | High (B) | Assets and Service Delivery | Medium (C) | Project Manager 8 | 2025-06-30 | C3 - Major | L2 - Very Likely | Management – Funding/Governance/Reporting/Strategy | Cause Description 41 | Consequence Description 41 | Tolerate | Mitigation Action Plan 41 | C4 – Moderate | L3 – Likely | 2025-04-02 15:54 | 40.3377 | Sub-Portfolio 7 | Project | Schedule
1001355 | 0 | 1 | 0 | Project 68 | Delay in development of Product Back | 268194 | Product Owner is asking to know all available REM fields and ingest those, and not moving forward with development of Product Backlog | Open | Medium (C) | Unassigned | Unassigned | Project Manager 12 | 2025-04-30 | C4 - Moderate | L3 - Likely | Information – Accuracy/Timeliness/Relevancy | Cause Description 42 | Consequence Description 42 | Unassigned | Mitigation Action Plan 42 | Unassigned | Unassigned | 2025-04-03 21:52 | 39.0891 | Sub-Portfolio 8 | Project | Unassigned
1001282 | 0 | 0 | 0 | Project 59 | Performance degradation with D1 MVP | 268345 | OTIT project team raised concern over potential performance degredation with MetaSpatial Evolve solution as the new UI for OT/IT data uploading, searching and tagging. OTIT has requested SAA to conduct performance testing. | Open | Medium (C) | Unassigned | Unassigned | Project Manager 14 | 2025-06-20 | C5 - Minor | L3 - Likely | Technology – Effectiveness/Usage/Integration/Failu | Cause Description 43 | Consequence Description 43 | Test | Mitigation Action Plan 43 | Unassigned | Unassigned | 2025-04-04 12:16 | 38.4888 | Sub-Portfolio 7 | Project | Unassigned
1001282 | 0 | 0 | 0 | Project 59 | Support model: future code change ownership | 268349 | GSIT DnA team will be supporting SAA related configurations via Evolve Admin console. S&T deployed and will be supporting the infrastructure that has access to deploy Evolve code changes Metaspatial is the vendor experts who can provide the code change content In BAU scenario, who is responsible to deploy code changes | Open | Medium (C) | Unassigned | Unassigned | Project Manager 14 | 2025-06-20 | C5 - Minor | L3 - Likely | Process – Complexity/Absence/Compliance | Cause Description 44 | Consequence Description 44 | Unassigned | Mitigation Action Plan 44 | Unassigned | Unassigned | 2025-04-04 13:13 | 38.4492 | Sub-Portfolio 7 | Project | Unassigned
1001328 | 0 | 0 | 0 | Project 61 | Rail Operations business users unavailability for | 268350 | Business Users unavailability to support the UAT with RailTable related PoC and rest of the UAT. Business requested 12 weeks for the UAT of Rail Table and Downstream systems. Hence the go-live date for TPS Database have been shifted out into June 2025 with go live date for Rail Table changing to August 2025. Missing source code for of the 4 RailTable business managed applications have been discovered, However, there is no confidence that the source code matches the production EXE files. Work is required to update the source code to point to the Exadata and recompile them. Business have to do a thorough functional testing during the UAT because the source code currency is not guaranteed. Business requires to plan the time and effort to thoroughly test these 4 applications during UAT. | Open | High (B) | Unassigned | Low (D) | Project Manager 25 | 2025-07-31 | C4 - Moderate | L2 - Very Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 45 | Consequence Description 45 | Treat | Mitigation Action Plan 45 | C5 – Minor | L4 – Unlikely | 2025-04-04 13:30 | 38.4375 | Sub-Portfolio 8 | Project | Unassigned
1001373 | 0 | 1 | 0 | Project 79 | Delays in clearing the Analysis and Design phase | 269312 | The project is still in Analysis and Design phase as there is a pending test plan document to be completed. This is dependent on the outcome of the Security Risk assessment and mitigation strategies to address the same | Open | Medium (C) | Governance, Legal and Assurance | Unassigned | Project Manager 38 | 2025-04-30 | C4 - Moderate | L3 - Likely | Process – Complexity/Absence/Compliance | Cause Description 46 | Consequence Description 46 | Unassigned | Mitigation Action Plan 46 | Unassigned | Unassigned | 2025-04-09 14:21 | 33.4023 | Sub-Portfolio 7 | Project | Schedule
1001373 | 0 | 0 | 0 | Project 79 | Impact of Topline Technology Restructure | 269313 | There is a Group Technology Topline Organisational Redesign which is underway. This could result in a change in the IT leadership overseeing delivery of this IT work package during the project’s lifecycle. In the event this risk manifests, it could lead to delays in approvals, changes to governance forum representation / decision makers, loss of corporate knowledge specific to this project, loss of trusted relationships | Open | High (B) | Governance, Legal and Assurance | Unassigned | Project Manager 38 | 2025-06-30 | C3 - Major | L2 - Very Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 47 | Consequence Description 47 | Tolerate | Mitigation Action Plan 47 | Unassigned | Unassigned | 2025-04-09 14:32 | 33.3946 | Sub-Portfolio 7 | Project | Unassigned
1000301 | 0 | 0 | 0 | Project 10 | Another issue in Control Systems could delay go li | 269558 | DNS fix will go live on 21 June, there is the risk that another issue will be found to delay the go live of TLS | Open | Medium (C) | Technology & Cyber Security | Unassigned | Project Manager 17 | 2025-08-31 | C4 - Moderate | L4 - Unlikely | Technology – Effectiveness/Usage/Integration/Failu | Cause Description 48 | Consequence Description 48 | Unassigned | Mitigation Action Plan 48 | Unassigned | Unassigned | 2025-04-10 22:06 | 32.0789 | Sub-Portfolio 7 | Project | Unassigned
1000294 | 0 | 0 | 0 | Project 3 | To be (future) state processes | 270843 | Risk in - Agreeing design options with technical teams - Reviewing and selecting best option with technical and key business teams - Review agreed option with all business teams - Obtaining approval (dign off) on final to be (future) state process designs | Open | Medium (C) | Governance, Legal and Assurance | Unassigned | Project Manager 4 | 2025-06-14 | C3 - Major | L2 - Very Likely | Process – Complexity/Absence/Compliance | Cause Description 49 | Consequence Description 49 | Unassigned | Mitigation Action Plan 49 | Unassigned | Unassigned | 2025-04-16 15:58 | 26.3348 | Sub-Portfolio 4 | Project | Unassigned
1000294 | 0 | 0 | 0 | Project 3 | Resoucing CorpIT | 270845 | Risk that CorpIT cannot supply resources required to deliver project | Open | Medium (C) | People | Unassigned | Project Manager 4 | 2025-05-02 | C3 - Major | L2 - Very Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 50 | Consequence Description 50 | Unassigned | Mitigation Action Plan 50 | Unassigned | Unassigned | 2025-04-16 16:06 | 26.329 | Sub-Portfolio 4 | Project | Unassigned
1000294 | 0 | 0 | 0 | Project 3 | Resourcing TSS | 270846 | Risk that TSS cannot supply resources required to deliver project | Open | Medium (C) | People | Unassigned | Project Manager 4 | 2025-05-02 | C3 - Major | L2 - Very Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 51 | Consequence Description 51 | Unassigned | Mitigation Action Plan 51 | Unassigned | Unassigned | 2025-04-16 16:11 | 26.3259 | Sub-Portfolio 4 | Project | Unassigned
1000294 | 0 | 0 | 0 | Project 3 | Resourcing Maritime | 270847 | Risk that Maritime cannot supply resources required to deliver project | Open | Medium (C) | People | Unassigned | Project Manager 4 | 2025-05-02 | C4 - Moderate | L2 - Very Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 52 | Consequence Description 52 | Unassigned | Mitigation Action Plan 52 | Unassigned | Unassigned | 2025-04-16 16:18 | 26.3205 | Sub-Portfolio 4 | Project | Unassigned
1000294 | 0 | 0 | 0 | Project 3 | Resourcing key supplier (Tambla) | 270848 | Risk that the key supplier (Tambla) cannot supply resources to deliver the project | Open | Medium (C) | Vendor | Unassigned | Project Manager 4 | 2025-05-02 | C3 - Major | L2 - Very Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 53 | Consequence Description 53 | Unassigned | Mitigation Action Plan 53 | Unassigned | Unassigned | 2025-04-16 16:26 | 26.3154 | Sub-Portfolio 4 | Project | Unassigned
1000294 | 0 | 0 | 0 | Project 3 | Procurement / Contract key supplier (Tambla) | 270851 | Risk that the key supplier (Tambla) cannot project resources due to a procurement or contract issue | Open | High (B) | Finance & Procurement | Unassigned | Project Manager 4 | 2025-05-02 | C4 - Moderate | L2 - Very Likely | Process – Complexity/Absence/Compliance | Cause Description 54 | Consequence Description 54 | Unassigned | Mitigation Action Plan 54 | Unassigned | Unassigned | 2025-04-16 16:33 | 26.3102 | Sub-Portfolio 4 | Project | Unassigned
1001755 | 0 | 0 | 0 | Project 116 | Security assessment effort estimates and timline | 271980 | Security assessment effort and resource allocations yet to be finalised, this might impact the delivery timeline before June 2025 | Open | Medium (C) | Technology & Cyber Security | Unassigned | Project Manager 36 | 2025-05-05 | C4 - Moderate | L3 - Likely | Technology – Effectiveness/Usage/Integration/Failu | Cause Description 55 | Consequence Description 55 | Unassigned | Mitigation Action Plan 55 | Unassigned | Unassigned | 2025-04-23 14:39 | 19.3895 | Sub-Portfolio 4 | Project | Unassigned
1001755 | 0 | 0 | 0 | Project 116 | Testlead effort estimates and resource allocations | 271981 | Testing requirements review in progress, to be finalised for getting the 3rd party test resource for project booking. | Open | Medium (C) | Finance & Procurement | Unassigned | Project Manager 36 | 2025-05-06 | C4 - Moderate | L4 - Unlikely | Process – Complexity/Absence/Compliance | Cause Description 56 | Consequence Description 56 | Unassigned | Mitigation Action Plan 56 | Unassigned | Unassigned | 2025-04-23 14:49 | 19.3828 | Sub-Portfolio 4 | Project | Unassigned
1001349 | 0 | 0 | 0 | Project 63 | The PM has resigned on 17/04 | 274461 | The PM has resigned on 17/04. Handover has been given to Hanan, who is out of capacity | Open | High (B) | People | Unassigned | Project Manager 41 | 2025-05-30 | C4 - Moderate | L1 - Almost Certain | Unassigned | Cause Description 57 | Consequence Description 57 | Unassigned | Mitigation Action Plan 57 | Unassigned | Unassigned | 2025-05-06 10:54 | 6.546 | Sub-Portfolio 4 | Project | Unassigned
1001755 | 0 | 0 | 0 | Project 116 | BOSN application UI screens WIPRO development | 274460 | BOSN application UI screens (around 20+ screens) are having Edit/Approve/Create buttons which need to be changed or removed for READONLY role. This will need at least couple of months development from BOSN end by Wipro. Project required to raise a SoW once the SAD or Design is ready. | Open | High (B) | Unassigned | Unassigned | Project Manager 36 | 2025-05-09 | C3 - Major | L3 - Likely | Technology – Effectiveness/Usage/Integration/Failu | Cause Description 58 | Consequence Description 58 | Unassigned | Mitigation Action Plan 58 | Unassigned | Unassigned | 2025-05-06 13:36 | 6.4336 | Sub-Portfolio 4 | Project | Unassigned
1000296 | 0 | 0 | 0 | Project 5 | Additional scope items added to Rel 1.2 scope | 274817 | Additional scope items added to Rel 1.2 scope which were earlier sitting with Business. Impact Analysis to be conducted. | Open | High (B) | People | Low (D) | Project Manager 8 | 2025-06-07 | C4 - Moderate | L2 - Very Likely | People – Training/Availability/Capacity/Collaborat | Cause Description 59 | Consequence Description 59 | Tolerate | Mitigation Action Plan 59 | C5 – Minor | L5 – Very Unlikely | 2025-05-07 10:18 | 5.571 | Sub-Portfolio 7 | Project | Scope
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## PV_ActiveRisks
Project | Number | Risk Name | Category | Status | Inherent Risk Consequence | Inherent Risk Likelihood | Inherent Risk Level | Due Date | Reportable?
Project 30 | 165204 | PMS/SGT Migration not accepted into EIPaaS Pilot | Project Delivery | Open | C3 - Major | L2 - Very Likely | High (B) | 2024-02-29 | No
Project 30 | 165205 | The project may not meet the SIT/UAT timeframe | Project Delivery | Open | C3 - Major | L2 - Very Likely | High (B) | 2024-03-31 | No
Project 30 | 165207 | Lack of required funding to complete the PMS/SGT | Project Delivery | Open | C3 - Major | L2 - Very Likely | High (B) | 2024-06-30 | No
Project 30 | 165208 | Dependecny on the EIPaaS for the integration | Project Delivery | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2024-03-15 | No
Project 30 | 165362 | Insufficient time for the testers to prepare |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2024-03-31 | No
Project 42 | 210998 | GS IT Budget Shortfall | Information & Data | Open | C4 - Moderate | L2 - Very Likely | High (B) | 2025-05-09 | No
Project 42 | 256840 | Design and price readiness by the end of March '25 | People | Open | C3 - Major | L2 - Very Likely | High (B) | 2025-05-16 | Yes
Project 3 | 270843 | To be (future) state processes | Governance, Legal and Assurance | Open | C3 - Major | L2 - Very Likely | Medium (C) | 2025-06-14 | Yes
Project 3 | 270845 | Resoucing CorpIT | People | Open | C3 - Major | L2 - Very Likely | Medium (C) | 2025-05-02 | Yes
Project 3 | 270846 | Resourcing TSS | People | Open | C3 - Major | L2 - Very Likely | Medium (C) | 2025-05-02 | Yes
Project 3 | 270847 | Resourcing Maritime | People | Open | C4 - Moderate | L2 - Very Likely | Medium (C) | 2025-05-02 | Yes
Project 3 | 270848 | Resourcing key supplier (Tambla) | Vendor | Open | C3 - Major | L2 - Very Likely | Medium (C) | 2025-05-02 | Yes
Project 3 | 270851 | Procurement / Contract key supplier (Tambla) | Finance & Procurement | Open | C4 - Moderate | L2 - Very Likely | High (B) | 2025-05-02 | Yes
Project 4 | 173663 | My Timesheet - End to End Solution |  | Open | C3 - Major | L2 - Very Likely | High (B) | 2024-12-31 | No
Project 5 | 261246 | Couchbase Procurement Delay | Technology & Cyber Security | Open | C3 - Major | L2 - Very Likely | High (B) | 2025-05-23 | Yes
Project 5 | 267922 | Organisation Restructure | Assets and Service Delivery | Open | C3 - Major | L2 - Very Likely | High (B) | 2025-06-30 | Yes
Project 5 | 274817 | Additional scope items added to Rel 1.2 scope | People | Open | C4 - Moderate | L2 - Very Likely | High (B) | 2025-06-07 | Yes
Project 7 | 221462 | SME Engagement |  | Open | C4 - Moderate | L2 - Very Likely | High (B) | 2024-11-30 | No
Project 10 | 216372 | Union Strikes could impact ODS-TLS delay in Go Liv |  | Open | C4 - Moderate | L4 - Unlikely | Medium (C) | 2025-08-29 | Yes
Project 10 | 269558 | Another issue in Control Systems could delay go li | Technology & Cyber Security | Open | C4 - Moderate | L4 - Unlikely | Medium (C) | 2025-08-31 | Yes
Project 11 | 159880 | ODS-TLS Project moved to Jul 25 Tentatively | Governance, Legal and Assurance | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-08-30 | Yes
Project 11 | 159881 | Change to DSP TLS Config | Vendor | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-04-30 | Yes
Project 16 | 147969 | Stakeholder Risk - Rail ML | Vendor | Open | C5 - Minor | L4 - Unlikely | Low (D) | 2025-02-28 | No
Project 16 | 233293 | DS System testing & unit testing artifacts | Customer Service & Experience | Open | C3 - Major | L2 - Very Likely | High (B) | 2025-03-31 | No
Project 16 | 259567 | Final Equip design/ solution build | Technology & Cyber Security | Open | C3 - Major | L3 - Likely | High (B) | 2025-05-30 | No
Project 16 | 259568 | Equip Release not aligned to Program Requirement | Technology & Cyber Security | Open | C2 - Severe | L1 - Almost Certain | Very High (A) | 2025-05-30 | Yes
Project 16 | 259569 | Equip solution impacted by other parallel initiati | Technology & Cyber Security | Open | C2 - Severe | L4 - Unlikely | High (B) | 2025-07-31 | No
Project 16 | 259570 | Alignment with TSS Payroll | Customer Service & Experience | Open | C1 - Catastrophic | L3 - Likely | Very High (A) | 2025-07-31 | No
Project 16 | 259571 | Dedicated Equip Test landscape | Technology & Cyber Security | Open | C2 - Severe | L4 - Unlikely | High (B) | 2025-03-28 | No
Project 16 | 274345 | Project schedule/timelines not met | Assets and Service Delivery | Open | C3 - Major | L3 - Likely | High (B) | 2026-02-28 | No
Project 16 | 274939 | Insufficient resources to deliver the project |  | Open | C5 - Minor | L4 - Unlikely | Low (D) | 2026-02-28 | No
Project 16 | 274940 | New system not developed as required |  | Open | C4 - Moderate | L2 - Very Likely | High (B) | 2025-08-28 | No
Project 16 | 274943 | Budget/Contingency is P50 |  | Open | C3 - Major | L2 - Very Likely | High (B) | 2025-07-31 | No
Project 16 | 275008 | No funding for Hypercare of Phase 2 |  | Open | C6 - Insignificant | L1 - Almost Certain | Medium (C) | 2025-05-31 | No
Project 16 | 275009 | Data Integrity |  | Open | C5 - Minor | L1 - Almost Certain | High (B) | 2025-08-29 | No
Project 16 | 275012 | Lack of detailed functional specifications and NFR |  | Open | C5 - Minor | L3 - Likely | Medium (C) | 2025-08-29 | No
Project 17 | 138635 | Master Data to support ePAS go live 1 Sep24 | Information & Data | On Hold | C3 - Major | L4 - Unlikely | Medium (C) | 2024-06-28 | Yes
Project 17 | 203233 | EPS solution design governance | Governance, Legal and Assurance | On Hold | C2 - Severe | L5 - Very Unlikely | Medium (C) | 2024-08-30 | Yes
Project 17 | 203234 | EPS Master Data governance | Information & Data | On Hold | C1 - Catastrophic | L5 - Very Unlikely | High (B) | 2024-08-31 | Yes
Project 17 | 203242 | Analyse and Design phase: Exit risk | Governance, Legal and Assurance | On Hold | C2 - Severe | L5 - Very Unlikely | Medium (C) | 2024-08-30 | Yes
Project 17 | 203245 | EPS Master Data sources | Information & Data | On Hold | C2 - Severe | L5 - Very Unlikely | Medium (C) | 2024-08-30 | Yes
Project 19 | 226382 | Budget Risk | Finance & Procurement | Open | C3 - Major | L3 - Likely | High (B) | 2025-06-30 | Yes
Project 19 | 255734 | Proper logging and monitoring, |  | Open | C3 - Major | L4 - Unlikely | Medium (C) | 2026-02-18 | No
Project 19 | 258328 | WinDSX Changes in Application Tiering | Technology & Cyber Security | Open | C2 - Severe | L3 - Likely | High (B) | 2025-05-31 | Yes
Project 19 | 265632 | "Delays – 3rd Party Vendors. | Vendor | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265633 | Vendor Costs may be higher. | Vendor | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265634 | Change in Managed Service Provider (MSP) | Vendor | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265635 | All identified decommissions may not be possible | Assets and Service Delivery | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265636 | Lack of readiness of packaged solution vendors | Technology & Cyber Security | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265637 | Shared Infrastructure costs may not reduce in the |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265638 | Resistance to Change and Adoption |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265639 | Opex Forecasting may vary once Cloud provisioning |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265642 | Complexity |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265643 | Scope Changes |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265644 | Lack of detailed planning at the time of BC |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265645 | Business Objection |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265646 | MSP impacts and support tools are unknown |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265647 | Resources |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265648 | Archiving Solution |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265650 | Right Sizing and Solution |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 265651 | Operating Model |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2026-06-30 | No
Project 19 | 267724 | Organisational Change | People | Open | C3 - Major | L3 - Likely | High (B) | 2025-06-30 | Yes
Project 21 | 152411 | Scope change from Union Consultations |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2024-12-31 | Yes
Project 55 | 272961 | Slippage in Project Delivery dates | Information & Data | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-05-23 | No
Project 59 | 259110 | Project Delivery Meeting Budget Is At Risk |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-04-30 | Yes
Project 59 | 268345 | Performance degradation with D1 MVP |  | Open | C5 - Minor | L3 - Likely | Medium (C) | 2025-06-20 | Yes
Project 59 | 268349 | Support model: future code change ownership |  | Open | C5 - Minor | L3 - Likely | Medium (C) | 2025-06-20 | Yes
Project 61 | 207442 | RailTable DB Blocker | Information & Data | Open | C3 - Major | L1 - Almost Certain | Very High (A) | 2025-05-30 | Yes
Project 61 | 268350 | Rail Operations business users unavailability for |  | Open | C4 - Moderate | L2 - Very Likely | High (B) | 2025-07-31 | Yes
Project 62 | 275198 | ROC improvement program is surfacing new demand |  | Open | C4 - Moderate | L3 - Likely |  | 2025-06-27 | Yes
Project 62 | 275199 | Change management, not just for the ROC, but for a |  | Open |  |  |  | 2025-06-27
Project 63 | 237200 | New Contract |  | Open | C4 - Moderate | L4 - Unlikely | Medium (C) | 2025-04-30 | Yes
Project 63 | 237203 | Procurement Timelines |  | Open | C5 - Minor | L3 - Likely | Medium (C) | 2025-04-30 | No
Project 63 | 274461 | The PM has resigned on 17/04 | People | Open | C4 - Moderate | L1 - Almost Certain | High (B) | 2025-05-30 | Yes
Project 65 | 259058 | No warranty support | Technology & Cyber Security | Open | C6 - Insignificant | L5 - Very Unlikely | Low (D) | 2025-05-30 | No
Project 65 | 260219 | Transition of support may likely affect go live of | Customer Service & Experience | Open | C3 - Major | L2 - Very Likely | High (B) | 2025-04-04 | Yes
Project 66 | 241120 | Data Integrity and corruption during migration |  | Open | C3 - Major | L4 - Unlikely | Medium (C) | 2025-06-30 | No
Project 66 | 241176 | Performance and Access Speed Issues |  | Open | C3 - Major | L4 - Unlikely | Medium (C) | 2025-06-30 | No
Project 66 | 241177 | Data Privacy Legal Compliance |  | Open | C3 - Major | L3 - Likely | High (B) | 2025-06-30 | No
Project 68 | 268194 | Delay in development of Product Back |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-04-30 | No
Project 71 | 243036 | Time blowout due to commercial engagement | Finance & Procurement | Open | C3 - Major | L2 - Very Likely | High (B) | 2025-01-31 | Yes
Project 71 | 243037 | Risk of identifying business opex | Finance & Procurement | Open | C3 - Major | L3 - Likely | Medium (C) | 2025-05-31 | Yes
Project 71 | 243038 | Low "BAU" Effort |  | Open | C3 - Major | L3 - Likely | Medium (C) | 2025-05-31 | Yes
Project 71 | 243039 | Ambiguities in Scope Around Implementation | Technology & Cyber Security | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-04-30 | Yes
Project 71 | 243040 | Service underutilisation and profileration | Customer Service & Experience | Open | C5 - Minor | L4 - Unlikely | Low (D) | 2025-06-30 | No
Project 72 | 258268 | Application Incompatibility with RHEL 9 |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-05-15 | No
Project 72 | 258329 | Unavailability of Application SME - TCDC, NDD |  | Open | C4 - Moderate | L2 - Very Likely | High (B) | 2025-05-13 | No
Project 72 | 258633 | Changes in Scope | Technology & Cyber Security | Open | C5 - Minor | L3 - Likely | Medium (C) | 2025-05-07 | No
Project 72 | 258634 | Data Loss or Corruption During Upgrade | Technology & Cyber Security | Open | C5 - Minor | L4 - Unlikely | Low (D) | 2025-05-30 | No
Project 72 | 258642 | Extended Downtime During Upgrade |  | Open | C5 - Minor | L4 - Unlikely | Low (D) | 2025-05-30 | No
Project 72 | 258643 | Insufficient Testing and Validation | Technology & Cyber Security | Open | C5 - Minor | L4 - Unlikely | Low (D) | 2025-05-21 | No
Project 72 | 258645 | Misaligned H/W & S/W Resource Requirements | Technology & Cyber Security | Open | C4 - Moderate | L4 - Unlikely | Medium (C) | 2025-05-23 | No
Project 72 | 264808 | Potential Delay in NDD OS Upgrade | People | Open | C4 - Moderate | L2 - Very Likely | High (B) | 2025-05-15 | Yes
Project 72 | 267504 | PSAD delays could delay the project |  | Open | C4 - Moderate | L5 - Very Unlikely | Low (D) | 2025-05-15 | No
Project 73 | 255468 | FY26 funding unavailability to complete project |  | Open | C4 - Moderate | L4 - Unlikely | Medium (C) | 2025-05-15 | No
Project 73 | 273249 | Business Acceptance - Lack of User Buy-in | Customer Service & Experience | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-05-14 | No
Project 74 | 237660 | Decommissioning - Site Inventory | Information & Data | Open | C4 - Moderate | L4 - Unlikely | Medium (C) | 2025-06-30 | No
Project 74 | 263747 | Rail Operations Site Migraiton | Assets and Service Delivery | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-06-30 | Yes
Project 74 | 263748 | Time Table Production Site Migration | Assets and Service Delivery | Open | C5 - Minor | L2 - Very Likely | Medium (C) | 2025-06-30 | Yes
Project 74 | 263749 | Additional significant user requirements | Assets and Service Delivery | Open | C4 - Moderate | L4 - Unlikely | Medium (C) | 2025-06-30 | Yes
Project 74 | 263750 | Decommission - scope creep | Assets and Service Delivery | Open | C3 - Major | L2 - Very Likely | High (B) | 2025-08-31 | Yes
Project 74 | 263751 | Restructure and Business Availability | People | Open | C5 - Minor | L4 - Unlikely | Low (D) | 2025-08-31 | Yes
Project 75 | 206332 | Vanguard is at risk due to end of life/Support |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-06-20 | Yes
Project 75 | 234856 | ETL job migraiton | Technology & Cyber Security | Open |  |  | Medium (C) | 2025-04-25
Project 75 | 234911 | Report performance | Technology & Cyber Security | Open | C3 - Major | L4 - Unlikely | Medium (C) | 2025-04-24 | No
Project 75 | 234913 | ETL job performance | Technology & Cyber Security | Open | C3 - Major | L4 - Unlikely | Medium (C) | 2025-04-30 | No
Project 75 | 234914 | Data migration errors | Technology & Cyber Security | Open | C3 - Major | L4 - Unlikely | Medium (C) | 2025-04-28 | No
Project 75 | 234915 | BAU support | People | Open | C3 - Major | L5 - Very Unlikely | Medium (C) | 2025-06-27 | No
Project 75 | 234916 | Privacy risk | Governance, Legal and Assurance | Open | C3 - Major | L3 - Likely | High (B) | 2025-06-27 | No
Project 75 | 234917 | TDHP platform configuration | Technology & Cyber Security | Open | C4 - Moderate | L4 - Unlikely | Medium (C) | 2025-06-27 | No
Project 75 | 234918 | BAU support costs not accepted | Finance & Procurement | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-06-27 | No
Project 75 | 234919 | Project budget | Finance & Procurement | Open | C3 - Major | L4 - Unlikely | Medium (C) | 2025-05-30 | No
Project 76 | 221147 | Design Documents |  | Open | C5 - Minor | L4 - Unlikely | Low (D) | 2024-11-30 | No
Project 76 | 261162 | Delayed estimates from vendor |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-03-10 | No
Project 77 | 220086 | Funding | Finance & Procurement | Open | C3 - Major | L3 - Likely |  | 2025-02-28
Project 77 | 220088 | Closed RFP | Finance & Procurement | Open | C3 - Major | L3 - Likely |  | 2024-11-30 | No
Project 77 | 220090 | Business Engagement | People | Open | C4 - Moderate | L5 - Very Unlikely |  | 2025-03-31 | No
Project 77 | 220092 | Business Processess | People | Open | C4 - Moderate | L3 - Likely |  | 2025-05-31 | Yes
Project 77 | 220093 | Vendor Capability | Vendor | Open | C4 - Moderate | L3 - Likely |  | 2025-04-30 | Yes
Project 77 | 220094 | Vendor Availability | Vendor | Open | C4 - Moderate | L5 - Very Unlikely |  | 2025-04-30 | Yes
Project 79 | 267597 | Schedule Delays and its impact on test resourcing | People | Open | C3 - Major | L3 - Likely | High (B) | 2025-06-30 | Yes
Project 79 | 269312 | Delays in clearing the Analysis and Design phase | Governance, Legal and Assurance | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-04-30 | Yes
Project 79 | 269313 | Impact of Topline Technology Restructure | Governance, Legal and Assurance | Open | C3 - Major | L2 - Very Likely | High (B) | 2025-06-30 | Yes
Project 80 | 176137 | PMS/SGT Migration go-live is dependent on IIMS | Project Delivery | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2024-05-13 | No
Project 81 | 176138 | BAU resource avaliability | Project Delivery | Open | C5 - Minor | L4 - Unlikely | Low (D) | 2024-06-30 | No
Project 93 | 219343 | Mobile app compatibility |  | Open | C3 - Major | L3 - Likely | High (B) | 2025-11-28 | No
Project 93 | 243155 | New enhancements to eSCD and Task Assigner |  | Open | C3 - Major | L3 - Likely | High (B) | 2026-01-31 | Yes
Project 93 | 269614 | Dependency on EiPaaS project for MongoDB Data API | Technology & Cyber Security | Open | C3 - Major | L2 - Very Likely | High (B) | 2025-10-31 | No
Project 93 | 269771 | High dependency on Cloud Transformation AnyCloud | Technology & Cyber Security | Open | C3 - Major | L1 - Almost Certain | Very High (A) | 2026-01-31 | No
Project 93 | 269772 | Resource extensions may not be processed |  | Open | C3 - Major | L4 - Unlikely | Medium (C) | 2025-12-31 | No
Project 101 | 270752 | Test Risk |  | Open |  |  |  | 2025-06-20
Project 104 | 267921 | Impact of proposed changes to Group Technology | People | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-06-30 | Yes
Project 110 | 237393 | EiPaaS Migration dependencies | Technology & Cyber Security | Open | C3 - Major | L1 - Almost Certain | Very High (A) | 2025-05-31 | Yes
Project 110 | 237394 | Equip PRIME and RAISI program dependenciess | Technology & Cyber Security | On Hold | C3 - Major | L3 - Likely | High (B) | 2025-03-31 | Yes
Project 110 | 268195 | Documentum Migration Delays | Technology & Cyber Security | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-05-31 | No
Project 114 | 272960 | Slippage in Project Delivery dates | Information & Data | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-05-16 | No
Project 114 | 273246 | Procurement delays have impacted the schedule | Finance & Procurement | Open | C3 - Major | L3 - Likely | High (B) | 2025-05-30 | No
Project 116 | 271980 | Security assessment effort estimates and timline | Technology & Cyber Security | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-05-05 | Yes
Project 116 | 271981 | Testlead effort estimates and resource allocations | Finance & Procurement | Open | C4 - Moderate | L4 - Unlikely | Medium (C) | 2025-05-06 | Yes
Project 116 | 274460 | BOSN application UI screens WIPRO development |  | Open | C3 - Major | L3 - Likely | High (B) | 2025-05-09 | Yes
Project 116 | 274535 | SAD and solution options for test and delivery |  | Open | C4 - Moderate | L3 - Likely |  | 2025-05-14 | Yes
Project 145 | 254722 | TM1 current version is 10.2 is out of support |  | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-06-30 | Yes
Project 145 | 255733 | Go live in Jun-2025 may be impacted by EOFY |  | Open | C5 - Minor | L4 - Unlikely | Low (D) | 2025-06-30 | Yes
Project 145 | 267862 | Impact of proposed changes to Group Technology | People | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-06-30 | Yes
Project 155 | 267864 | Impact of proposed changes to Group Technology | People | Open | C4 - Moderate | L3 - Likely | Medium (C) | 2025-06-30 | Yes

## PV_Issues
WRK11
Last Extracted | 2025-05-07
5
Work ID # | Overdue | Project Description | Issue Title | CRI ID | Status | Category | Issue Rating | Owner | Due Date | Cause | Cause Description | Consequence Description | Issue Action Plan | Sub-Portfolio | Work Type | PMO Comment
1000872 | 1 | Project 31 | HCL schedule | 166933 | Open | Unassigned | High (B) | Project Manager 42 | 2024-03-15 | Cause 1 | Cause Description 1 | Consequence Description 1 | Issue Action Plan 1 | Sub-Portfolio 8 | Project
1000308 | 0 | Project 17 | Project delayed Master Data validation and uplift | 163990 | On Hold | Project Delivery | Medium (C) | Project Manager 35 | 2025-02-28 | Cause 2 | Cause Description 2 | Consequence Description 2 | Issue Action Plan 2 | Sub-Portfolio 7 | Project
1000308 | 0 | Project 17 | Project delayed Master Data governance issues | 203243 | On Hold | People | Very High (A) | Project Manager 4 | 2025-02-28 | Cause 3 | Cause Description 3 | Consequence Description 3 | Issue Action Plan 3 | Sub-Portfolio 7 | Project
1000308 | 0 | Project 17 | Project delay close Initiate phase | 203244 | On Hold | People | Very High (A) | Project Manager 4 | 2025-02-28 | Cause 4 | Cause Description 4 | Consequence Description 4 | Issue Action Plan 4 | Sub-Portfolio 7 | Project
1001328 | 0 | Project 61 | Documentum data is encrypted and cannot be copied | 243426 | Open | Vendor | High (B) | Project Manager 29 | 2025-08-30 | Cause 5 | Cause Description 5 | Consequence Description 5 | Issue Action Plan 5 | Sub-Portfolio 8 | Project
1000301 | 0 | Project 10 | Delay in implementation of ODS | 169297 | Open | Information & Data | Medium (C) | Project Manager 17 | 2025-07-31 | Cause 6 | Cause Description 6 | Consequence Description 6 | Issue Action Plan 6 | Sub-Portfolio 7 | Project
1000296 | 0 | Project 5 | Delay in Program Architecture PDA endorsement | 274820 | Open | Information & Data | High (B) | Project Manager 24 | 2025-05-15 | Cause 7 | Cause Description 7 | Consequence Description 7 | Issue Action Plan 7 | Sub-Portfolio 7 | Project
1000869 | 0 | Project 29 | Lack of Clarity on op. model and bus process. | 184623 | Open | Information & Data | Low (D) | Project Manager 17 | 2026-04-30 | Cause 8 | Cause Description 8 | Consequence Description 8 | Issue Action Plan 8 | Sub-Portfolio 7 | Project
1001355 | 1 | Project 68 | Resource availability from Vendor | 252477 | Open | People | Very High (A) | Project Manager 12 | 2025-02-28 | Cause 9 | Cause Description 9 | Consequence Description 9 | Issue Action Plan 9 | Sub-Portfolio 8 | Project
1001282 | 1 | Project 59 | TDHP pipeline change scale bigger than anticipated | 261177 | Open | Finance & Procurement | High (B) | Project Manager 14 | 2025-04-30 | Cause 10 | Cause Description 10 | Consequence Description 10 | Issue Action Plan 10 | Sub-Portfolio 7 | Project
1001282 | 0 | Project 59 | OTIT user network impact assessment | 268426 | Open | Unassigned | Low (D) | Project Manager 33 | 2025-06-20 | Cause 11 | Cause Description 11 | Consequence Description 11 | Issue Action Plan 11 | Sub-Portfolio 7 | Project
1000310 | 0 | Project 19 | Quantum Treasury System | 218922 | Open | Vendor | Medium (C) | Project Manager 6 | 2025-06-30 | Cause 12 | Cause Description 12 | Consequence Description 12 | Issue Action Plan 12 | Sub-Portfolio 8 | Project
1000310 | 0 | Project 19 | WinDSX: Firewall requirement | 238048 | Open | Technology & Cyber Security | Medium (C) | Project Manager 6 | 2025-05-30 | Cause 13 | Cause Description 13 | Consequence Description 13 | Issue Action Plan 13 | Sub-Portfolio 8 | Project
1000310 | 0 | Project 19 | Benefit Realisation for the Program | 238050 | Open | Finance & Procurement | Medium (C) | Project Manager 6 | 2025-06-30 | Cause 14 | Cause Description 14 | Consequence Description 14 | Issue Action Plan 14 | Sub-Portfolio 8 | Project
1001349 | 1 | Project 63 | Scheduling and budget impacts owing to RFP delays | 267373 | Open | Finance & Procurement | High (B) | Project Manager 27 | 2025-04-30 | Cause 15 | Cause Description 15 | Consequence Description 15 | Issue Action Plan 15 | Sub-Portfolio 4 | Project
1001239 | 1 | Project 48 | Solution Architect leaving during Design Phase | 241681 | Open | Unassigned | High (B) | Project Manager 14 | 2025-01-24 | Cause 16 | Cause Description 16 | Consequence Description 16 | Issue Action Plan 16 | Sub-Portfolio 3 | Minor Work
1001618 | 0 | Project 111 | Security assessment signoff for SAD approval | 268347 | Open | Technology & Cyber Security | Very High (A) | Project Manager 36 | 2025-05-09 | Cause 17 | Cause Description 17 | Consequence Description 17 | Issue Action Plan 17 | Sub-Portfolio 4 | Minor Work
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## PV Financials
New_or_Inflight | Requesting_Area | Capex_Opex | Project_Hub_ID | PlanView_ID | Project_Name | Project | Funding_Source_Category | Sponsor | Project_Manager_Owner | SubPortfolio | Status | Period1_Jul_Actual | Period2_Aug_Actual | Period3_Sep_Actual | Period4_Oct_Actual | Period5_Nov_Actual | Period6_Dec_Actual | Period7_Jan_Actual | Period8_Feb_Actual | Period9_Mar_Actual | Period10_Apr_Actual | Period11_May_Actual | Period12_Jun_5 | Total_Actuals | Period1_Jul_Forecast | Period2_Aug_Forecast | Period3_Sep_Forecast | Period4_Oct_Forecast | Period5_Nov_Forecast | Period6_Dec_Forecast | Period7_Jan_Forecast | Period8_Feb_Forecast | Period9_Mar_Forecast | Period10_Apr_Forecast | Period11_May_Forecast | Period12_Jun_5_1 | Full_Year_Forecast | ORIGINAL_BUDGET | Month_Actual | Month_Budget | Month_Variance | Percentage_Var | YTD_Actuals | YTD_Budget | YTD_Variance | YTD_Percentage_Var | FY_Forecast | FY_Budget | FY_Variance | FY_Percentage_Var
Inflight | Sydney Trains | Opex | 100070 | 1000302 | Digital Systems Program (DSP) | Project 11 | Business Funded | Sponsor 23 | Project Manager 17 | Sub-Portfolio 7 | Open/Active | 78154.82 | 58618.44 | 68503.26 | 49087.26 | 45692.62 | 18573.69 | 14271.54 | 28965.97 | 35505.14 | 21819.44 |  |  | 419192.18 | [10 empty] | 29523 | 35405 | 484120.18 | 573115 | 21819.44 | 34837 | 13017.56 | 0.37367 | 419192.18 | 429703.6 | 10511.42 | 0.024462 | 484120.18 | 505446 | 21325.82 | 0.042192
Inflight |  | Opex | AAA141 | 1000308 | Electrical Isolations Improvement Support (EIIP) | Project 17 | Business Funded | Sponsor 37 | Project Manager 4 | Sub-Portfolio 7 | Open/Active | 114288.67 | 147537.08 | 64114.54 | 874.57 | 873.71 |  | 0 | 0 | 0 |  |  |  | 327688.57 | [12 empty] | 327688.57 | 0 | 0 | 0 | 0 | 0 | 327688.57 | 0 | -327688.57 | 0 | 327688.57 | 0 | -327688.57 | 0
Inflight | NSW Train Link | Opex | 1000869 | 1000869 | Regional Rail Program (RRP) | Project 29 | Business Funded | Sponsor 50 | Project Manager 35 | Sub-Portfolio 7 | Open/Active | 55688.37 | 24342.79 | 26262.27 | 22349.55 | 15845.58 | 12898.34 | 3560.16 | 15982.86 | 14486.94 | 12388.93 |  |  | 203805.79 | [10 empty] | 21488.45 | 25835.04 | 251129.28 | 3432538 | 12388.93 | 73845 | 61456.07 | 0.83223 | 203805.79 | 302636.92 | 98831.13 | 0.32657 | 251129.28 | 632037.92 | 380908.64 | 0.60267
Inflight | Sydney Trains | Opex | AAA140 | 1000314 | OT-IT Integration Implementation Phase (IT Stream) | Project 23 | Business Funded | Sponsor 14 | Project Manager 33 | Sub-Portfolio 7 | Open/Active | 255785.25 | 271262.35 | 286219.41 | 263812.32 | 223352.59 | 158021.98 | 81407.06 | 103919.07 | 149620.84 | 137216.42 |  |  | 1930617.29 | [10 empty] | 210693 | 146425 | 2287735.29 | 1962484 | 137216.42 | 146087 | 8870.58 | 0.060721 | 1930617.29 | 1985516.03 | 54898.74 | 0.02765 | 2287735.29 | 2287821 | 85.71 | 3.7464e-05
Inflight | Sydney Trains | Capex | 100044 | 1000296 | Rail Timetable Solution (RTS) | Project 5 | Business Funded | Sponsor 21 | Project Manager 1 | Sub-Portfolio 7 | Open/Active | 173151.95 | 226776.71 | 157592.31 | 206845.67 | 189148.38 | 150683.39 | 142946.79 | 280195.12 | 247999.2 | 207438.55 |  |  | 1982778.07 | [10 empty] | 772016.43 | 471692.88 | 3226487.38 | 3619244 | 207438.55 | 358209.04 | 150770.49 | 0.4209 | 1982778.07 | 2725769.89 | 742991.82 | 0.27258 | 3226487.38 | 3619244 | 392756.62 | 0.10852
Inflight |  | Opex | 1000962 | 1000962 | Pricing changes in Network Access Billing System | Project 40 | Business Funded | Sponsor 29 | Project Manager 27 | Sub-Portfolio 7 | Requested | 4522.81 | 389.56 |  |  | 0 |  |  | 0 | 0 |  |  |  | 4912.37 | [13 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0
Inflight |  | Opex | AAA178 | 1001399 | Transit Planning Software (TPS) | Project 85 | Business Funded |  | Project Manager 14 | Sub-Portfolio 4 | Requested | 32625 | 36692.26 | 28486.61 | 48651.56 | 56300 | 14225 | 2100 | 0 | 0 |  |  |  | 219080.43
Inflight | Sydney Trains | Opex |  | 1001282 | Smart Asset Analytics (SAA) Strategic | Project 59 | Business Funded |  | Project Manager 14 | Sub-Portfolio 7 | Requested | 39007.97 | 31169.84 | 20753.32 | 19022.13 | 34354.84 | 51062.16 | 12015.7 | 157939.05 | 88970.43 | 200068.63 |  |  | 654364.07 | [10 empty] | 159104.01 | 159531.58 | 972999.66 | 1000000 | 200068.63 | 96426 | -103642.63 | -1.0748 | 654364.07 | 673126.65 | 18762.58 | 0.027874 | 972999.66 | 887296.14 | -85703.52 | -0.09659
Inflight | Sydney Trains | Opex |  | 1001373 | 1180 TCDC Yoyo Enhancements | Project 79 | Business Funded |  | Project Manager 38 | Sub-Portfolio 7 | Open/Active | 8474.49 | 17722.98 | 6518.83 |  | 0 | 1948.21 | 9947.74 | 25335.67 | 38858.38 | 26790.1 |  |  | 135596.4 | [10 empty] | 28510.11 | 25010.05 | 189116.56 | 208506.87 | 26790.1 | 32956.52 | 6166.42 | 0.18711 | 135596.4 | 137393.66 | 1797.26 | 0.013081 | 189116.56 | 208506.87 | 19390.31 | 0.092996
Inflight | Sydney Trains | Opex |  | 1001834 | 1284 IBM Planning Analytics (TM1) Upgrade | Project 145 | Business Funded |  | Project Manager 7 | Sub-Portfolio 7 | Open/Active | [7 empty] | 14321.38 | 19062.06 | 16404.81 |  |  | 49788.25 | [10 empty] | 23162.45 | 134530.87 | 207481.57 | 350000 | 16404.81 | 27060.47 | 10655.66 | 0.39377 | 49788.25 | 67080.12 | 17291.87 | 0.25778 | 207481.57 | 350000 | 142518.43 | 0.4072
Inflight | ITAS | Capex | 100075 | 1001617 | Integrated Contract & Fleet Mgmt Sys 2 | Project 110 | Capital Maintenance | Sponsor 18 | Project Manager 22 | Sub-Portfolio 8 | Open/Active | 61538.23 | 30215.22 | 154133.12 | 166432.69 | 198354.65 | 136957.37 | 213820.49 | 203559.18 | 184053.1 | 191530.05 |  |  | 1540594.1 | [10 empty] | 540296.49 | 1568479.8 | 3649370.39 | 4027260 | 191530.05 | 556772 | 365241.95 | 0.656 | 1540594.1 | 2707283.26 | 1166689.16 | 0.43094 | 3649370.39 | 4027260 | 47154.61 | 0.011709
Inflight | ITAS | Capex | AAA166 | 1000304 | Track Possessions Critical Risk Redn | Project 13 | Capital Maintenance | Sponsor 18 | Project Manager 22 | Sub-Portfolio 8 | Open/Active | -41627.3 | 177656.29 | 89337.76 | 89154.23 | 309655.44 | 242760.21 | 224022.88 | -154415.4 | 74935.85 | 18814.18 |  |  | 1030294.14 | [10 empty] | 0 | 0 | 1030294.14 | 1520000 | 18814.18 | 8000 | -10814.18 | -1.3518 | 1030294.14 | 1206304.14 | 176010 | 0.14591 | 1030294.14 | 1520000 | 149705.86 | 0.098491
Inflight | ITAS | Capex |  | 1001328 | Legacy Oracle & Solaris Decomm (GovDC) | Project 61 | Capital Maintenance |  | Project Manager 31 | Sub-Portfolio 8 | Open/Active | 77770.65 | 108501.03 | 170619.52 | 162889.49 | 232321.6 | 192563.98 | 111865.89 | 173648.67 | 148275.14 | 277524.35 |  |  | 1655980.32 | [10 empty] | 253094 | 594266.48 | 2503340.8 | 3210000 | 277524.35 | 425000 | 147475.65 | 0.347 | 1655980.32 | 2262980.69 | 607000.37 | 0.26823 | 2503340.8 | 3210000 | 348659.2 | 0.10862
Inflight | ITAS | Capex |  | 1001440 | RRR7-TEW Tech Platform Risk Elimination | Project 93 | Capital Maintenance |  | Project Manager 43 | Sub-Portfolio 8 | Open/Active | 37000 | 70207.47 | 102412.66 | 184525.7 | 170229 | 101467.13 | 162648.26 | 164370 | 192636.57 | -189732.3 |  |  | 995764.49 | [10 empty] | 275300.55 | 208981.83 | 1480046.87 | 990000 | -189732.3 | 0 | 189732.3 | 0 | 995764.49 | 1415659.83 | 419895.34 | 0.29661 | 1480046.87 | 990000 | 10252.13 | 0.010356
New | ITAS | Capex |  | 1001351 | Replatforming Critical Rail Safety-Squiz | Project 65 | Capital Maintenance |  | Project Manager 29 | Sub-Portfolio 8 | Open/Active | 8510 | 26263.75 | 43120.57 | 52312.53 | 49507.8 | 42556.96 | 25707.85 | 55868.98 | 77829.88 | 137925.77 |  |  | 519604.09 | [10 empty] | 92038.86 | 43575.82 | 655218.77 | 800000 | 137925.77 | 109306.64 | -28619.13 | -0.26182 | 519604.09 | 691973.46 | 172369.37 | 0.2491 | 655218.77 | 800000 | 144781.23 | 0.18098
New | ITAS | Capex |  | 1001350 | RRR6-Incident Management System (REM) | Project 64 | Capital Maintenance |  | Project Manager 44 | Sub-Portfolio 8 | Open/Active | 21537 | 49144.74 | 94883.96 | 167169.08 | 166539.35 | 111729.36 | 60394.34 | 98410.12 | 27934.65 | 20441.71 |  |  | 818184.31 | [10 empty] | 0 | 227628.73 | 1045813.04 | 2355000 | 20441.71 | 8835.13 | -11606.58 | -1.3137 | 818184.31 | 1487511.77 | 669327.46 | 0.44996 | 1045813.04 | 2355000 | 459368.96 | 0.19506
New | ITAS | Capex |  | 1001353 | Archiving Platform Info Archive Upgrade | Project 66 | Capital Maintenance |  | Project Manager 45 | Sub-Portfolio 8 | Open/Active | 5215.04 | 19447.25 | 45501.54 | 31028.52 | 25456.94 | 45728.53 | 23387.98 | 140803.11 | 181865.29 | 37810.89 |  |  | 556245.09 | [10 empty] | 113555.51 | 525748.84 | 1195549.44 | 1336934 | 37810.89 | 128631.7 | 90820.81 | 0.70605 | 556245.09 | 793511.42 | 237266.33 | 0.29901 | 1195549.44 | 1336934 | -9339.44 | -0.0069857
New | ITAS | Capex |  | 1001347 | RRR6 - Train Location System | Project 62 | Capital Maintenance |  | Project Manager 10 | Sub-Portfolio 8 | Open/Active |  |  | 4563.2 | 27786.5 | 32598.59 | 29317.64 | 32898.21 | 32528.28 | 34518.89 | -2467.96 |  |  | 191743.35 | [10 empty] | 41517.58 | 16290.48 | 249551.41 | 250000 | -2467.96 | 35000 | 37467.96 | 1.0705 | 191743.35 | 207264.3 | 15520.95 | 0.074885 | 249551.41 | 250000 | 448.59 | 0.0017944
New | ITAS | Capex |  | 1001361 | Gov DC Remediation - Legacy Sharepoint Migration | Project 74 | Capital Maintenance |  | Project Manager 28 | 0 |  |  |  |  | 5700 | 35685.94 | 43723.66 | 24009.54 | 37704.56 | 22405.53 | 14557.88 |  |  | 183787.11 | [10 empty] | 162688 | 154574 | 501049.11 |  | 14557.88 | 62255.48 | 47697.6 | 0.76616 | 183787.11 | 337878.22 | 154091.11 | 0.45606 | 501049.11 | 435535 | 43242.89 | 0.099287
Inflight | Greater Sydney | Capex | AAA41 | 1000298 | NSW Maritime Safety & Compliance (BOSN) | Project 7 | Capital Maintenance | Sponsor 19 | Project Manager 38 | Sub-Portfolio 4 | Open/Active | 0 | 0 |  | 12081.12 | 13791.21 | 11199.8 | 17957.48 | 16952.35 | 10088.7 | 6874.29 |  |  | 88944.95 | [10 empty] | 29733.71 | 230242.33 | 348920.99 | 400000 | 6874.29 | 20057.4 | 13183.11 | 0.65727 | 88944.95 | 153227.28 | 64282.33 | 0.41952 | 348920.99 | 400000 | 51079.01 | 0.1277
New | Greater Sydney | Capex |  | 1001363 | Maritime Customer Booking System Upgrade | Project 76 | Capital Maintenance |  | Project Manager 38 | Sub-Portfolio 4 | Open/Active | 4621.48 | 1959.76 | 5929.44 | 10143.13 | 13366.8 | 25351.48 | 7671.73 | 30635.86 | 9417.79 | 11158.92 |  |  | 120256.39 | [10 empty] | 37072.35 | 167703.52 | 325032.26 | 300000 | 11158.92 | 12835.6 | 1676.68 | 0.13063 | 120256.39 | 138897.44 | 18641.05 | 0.13421 | 325032.26 | 339000 | 13967.74 | 0.041203
New | Greater Sydney | Capex |  | 1001364 | Maritime State-wide Op Incident Mgt | Project 77 | Capital Maintenance |  | Project Manager 38 | Sub-Portfolio 4 | Open/Active | 93215.65 | 134063.67 | 63293.43 | 30200.71 | 49799.91 | 31483.59 | 39073.38 | 65854.28 | 30570.41 | 17563.51 |  |  | 555118.54 | [10 empty] | 30876.79 | 27480.8 | 613476.13 | 1100000 | 17563.51 | 74392.29 | 56828.78 | 0.76391 | 555118.54 | 743368.12 | 188249.58 | 0.25324 | 613476.13 | 751000 | 137523.87 | 0.18312
New | Greater Sydney | Capex |  | 1001349 | Technology Connectivity - Maritime & TMC | Project 63 | Capital Maintenance |  | Project Manager 18 | Sub-Portfolio 4 | Open/Active | 28337.41 | 33563.69 | 49834.37 | 49581.95 | 54079.86 | 31539.56 | 22189.3 | 13175 | 20668.13 | 12204.93 |  |  | 315174.2 | [10 empty] | 51138.24 | 1038767.64 | 1405080.08 | 1500000 | 12204.93 | 46086.13 | 33881.2 | 0.73517 | 315174.2 | 406216.22 | 91042.02 | 0.22412 | 1405080.08 | 1500000 | 94919.92 | 0.06328
New | Greater Sydney | Capex |  | 1001362 | Fare Compliance Sys-Opal Replacement | Project 75 | Minor Capital |  | Project Manager 18 | Sub-Portfolio 4 | Open/Active | 0 | 55315.6 | 74038.79 | 151882.37 | 127640.84 | 98152.1 | 94484.86 | 175875.15 | 168288.87 | 123130.96 |  |  | 1068809.54 | [10 empty] | 182641.88 | 183950.21 | 1435401.63 | 1600000 | 123130.96 | 161129.27 | 37998.31 | 0.23582 | 1068809.54 | 1416854.72 | 348045.18 | 0.24565 | 1435401.63 | 1600000 | -85401.63 | -0.053376
New | Sydney Trains | Capex |  | 1001358 | Transport VR Capability Enablement | Project 71 | Minor Capital |  | Project Manager 30 | Sub-Portfolio 7 | Open/Active |  |  | 4457.88 | 7642.08 | 3962.56 | 5359.12 | 16107.66 | 10178.31 | 5473.02 | 10363.86 |  |  | 63544.49 | [10 empty] | 145725.98 | 147744.2 | 357014.67 | 220000 | 10363.86 | 36186.01 | 25822.15 | 0.71359 | 63544.49 | 230000 | 166455.51 | 0.72372 | 357014.67 | 220000 | -57014.67 | -0.25916
New | ITAS | Capex |  | 1001360 | e-Observations Replatforming Safety & Hazard ID | Project 73 | Capital Maintenance |  | Project Manager 21 | Sub-Portfolio 8 | Open/Active | [6 empty] | 9449.64 | 24236.81 | 9798.7 | 11793.14 |  |  | 55278.29 | [10 empty] | 70453 | 57904 | 183635.29 |  | 11793.14 | 47500 | 35706.86 | 0.75172 | 55278.29 | 152077.64 | 96799.35 | 0.63651 | 183635.29 | 250000 | 66364.71 | 0.26546
New | ITAS | Capex |  | 1001359 | Windows 2012, Linux OS ver 6&7 upgrade v 0.1 | Project 72 | Capital Maintenance |  | Project Manager 21 | Sub-Portfolio 8 | Open/Active | [6 empty] | 16035.86 | 21937.6 | 31195.93 | 24116.29 |  |  | 93285.68 | [10 empty] | 54672 | 74672 | 222629.68 |  | 24116.29 | 71650 | 47533.71 | 0.66342 | 93285.68 | 196466.86 | 103181.18 | 0.52518 | 222629.68 | 350000 | 127370.32 | 0.36392
New | Greater Sydney | Capex |  | 1001647 | Maritime – Digital Wharf Signage (Phase 2) | Project 114 | Minor Capital |  | Project Manager 20 | Sub-Portfolio 4 | Open/Active | [8 empty] | 28238.23 | 21720 |  |  | 49958.23 | [10 empty] | 55439.63 | 47183.12 | 152580.98 |  | 0 | 48412.82 | 48412.82 | 1 | 49958.23 | 103809.57 | 53851.34 | 0.51875 | 152580.98 | 259814 | 107233.02 | 0.41273